## Weighting Workshops data
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION |  | Individual contributions prior to normalization
| CATEGORY Element | P1 |  |  | P2 |  |  | P3 |  |  | P4 |  |  | P5 |  |  | P6 |  |  | P7 |  |  | P8 |  |  | P9 |  |  | P10 |  |  | P11 |  |  | P12 |  |  | P13 |  |  | Yunus Docrat | P14 |  | Louw v Heerden | P15 |  | Marius Kruger | P16 |  | Strauss Oosthuizen | P17 |  | Henry Jonker | P18 |  | P Critcher | P19
A | PROJECT STRATEGY
A.1 | Project Justification |  | 2% | 8% |  | 2% | 10% |  | 5% | 20% |  | 7% | 25% |  | 0% | 1% |  | 5% | 25% |  | 1% | 25% |  | 5% | 25% |  | 2% | 8% |  | 3% | 12% |  | 5% | 10% |  | 5% | 15% |  | 2% | 5% |  | 0% | 3% |  | 1% | 10% |  | 2% | 20% |  | 0% | 50% |  | 2% | 15% |  | 2% | 5%
A.2 | Project Charter and Mandate |  | 4% | 9% |  | 2% | 5% |  | 5% | 15% |  | 7% | 25% |  | 0% | 1% |  | 2% | 10% |  | 2% | 20% |  | 5% | 25% |  | 3% | 9% |  | 2% | 12% |  | 3% | 10% |  | 5% | 10% |  | 1% | 2% |  | 0% | 3% |  | 2% | 20% |  | 2% | 10% |  | 0% | 20% |  | 5% | 10% |  | 5% | 10%
A.3 | Governance and control (internal approval process defined) |  | 5% | 10% |  | 2% | 7% |  | 5% | 10% |  | 5% | 20% |  | 0% | 1% |  | 2% | 25% |  | 1% | 5% |  | 5% | 25% |  | 5% | 10% |  | 2% | 10% |  | 3% | 15% |  | 5% | 25% |  | 1% | 2% |  | 0% | 4% |  | 2% | 20% |  | 5% | 15% |  | 0% | 20% |  | 5% | 15% |  | 5% | 10%
A.5 | Project Strategy |  | 2% | 6% |  | 2% | 5% |  | 8% | 10% |  | 5% | 30% |  | 0% | 1% |  | 1% | 5% |  | 1% | 10% |  | 5% | 25% |  | 6% | 12% |  | 3% | 8% |  | 5% | 10% |  | 5% | 10% |  | 3% | 7% |  | 0% | 2% |  | 1% | 30% |  | 5% | 15% |  | 0% | 30% |  | 2% | 8% |  | 1% | 5%
A.6 | Strategic fit of project in organisation |  | 1% | 6% |  | 1% | 10% |  | 8% | 5% |  | 5% | 25% |  | 1% | 1% |  | 1% | 5% |  | 1% | 15% |  | 5% | 25% |  | 4% | 8% |  | 2% | 8% |  | 1% | 15% |  | 0% | 5% |  | 1% | 3% |  | 0% | 2% |  | 1% | 15% |  | 2% | 30% |  | 2% | 30% |  | 2% | 5% |  | 1% | 7%
A.7 | Due diligence |  | 2% | 7% |  | 2% | 10% |  | 6% | 5% |  | 5% | 25% |  | 0% | 1% |  | 10% | 25% |  | 1% | 20% |  | 5% | 25% |  | 4% | 8% |  | 3% | 8% |  | 2% | 20% |  | 5% | 20% |  | 2% | 4% |  | 0% | 2% |  | 1% | 10% |  | 2% | 20% |  | 0% | 50% |  | 2% | 5% |  | 3% | 8%
A.8 | Partnership, joint ventures and shareholder buy in |  | 5% | 10% |  | 2% | 5% |  | 6% | 20% |  | 5% | 30% |  | 1% | 5% |  | 1% | 10% |  | 1% | 25% |  | 5% | 25% |  | 5% | 11% |  | 3% | 8% |  | 1% | 5% |  | 5% | 10% |  | 2% | 4% |  | 0% | 2% |  | 5% | 30% |  | 3% | 10% |  | 2% | 20% |  | 2% | 5% |  | 7% | 12%
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK
B.1 | Social Issues |  | 1% | 7% |  | 2% | 4% |  | 5% | 10% |  | 5% | 35% |  | 1% | 5% |  | 5% | 25% |  | 2% | 20% |  | 10% | 30% |  | 2% | 6% |  | 4% | 15% |  | 15% | 20% |  | 10% | 30% |  | 1% | 5% |  | 5% | 5% |  | 5% | 40% |  | 1% | 10% |  | 5% | 5% |  | 5% | 15% |  | 5% | 12%
B.2 | Geo-political risks |  | 2% | 7% |  | 2% | 4% |  | 5% | 10% |  | 5% | 35% |  | 1% | 3% |  | 2% | 15% |  | 3% | 30% |  | 10% | 30% |  | 2% | 6% |  | 4% | 6% |  | 4% | 11% |  | 5% | 30% |  | 1% | 2% |  | 5% | 5% |  | 3% | 30% |  | 1% | 10% |  | 2% | 5% |  | 5% | 8% |  | 4% | 9%
B.3 | Fiscal stability agreement |  | 3% | 8% |  | 2% | 5% |  | 8% | 10% |  | 5% | 35% |  | 1% | 3% |  | 2% | 5% |  | 3% | 20% |  | 10% | 50% |  | 1% | 2% |  | 2% | 5% |  | 2% | 8% |  | 0% | 8% |  | 1% | 2% |  | 5% | 5% |  | 1% | 20% |  | 2% | 8% |  | 2% | 5% |  | 2% | 8% |  | 6% | 8%
B.4 | Social License to Operate |  | 2% | 8% |  | 2% | 4% |  | 5% | 10% |  | 5% | 35% |  | 1% | 10% |  | 10% | 35% |  | 2% | 15% |  | 10% | 50% |  | 3% | 6% |  | 4% | 15% |  | 5% | 10% |  | 0% | 10% |  | 1% | 2% |  | 5% | 5% |  | 5% | 20% |  | 3% | 15% |  | 2% | 5% |  | 2% | 5% |  | 2% | 5%
B.5 | Violence and terrorism |  | 3% | 8% |  | 2% | 4% |  | 5% | 10% |  | 5% | 50% |  | 1% | 2% |  | 2% | 2% |  | 2% | 25% |  | 10% | 50% |  | 1% | 2% |  | 2% | 6% |  | 2% | 8% |  | 10% | 30% |  | 1% | 1% |  | 5% | 5% |  | 5% | 50% |  | 1% | 5% |  | 1% | 5% |  | 2% | 5% |  | 3% | 5%
B.6 | Ability to appoint expatriats |  | 5% | 10% |  | 1% | 5% |  | 8% | 10% |  | 5% | 35% |  | 1% | 2% |  | 1% | 1% |  | 5% | 30% |  | 10% | 30% |  | 1% | 2% |  | 2% | 7% |  | 2% | 6% |  | 15% | 35% |  | 1% | 3% |  | 2% | 2% |  | 10% | 30% |  | 1% | 5% |  | 5% | 5% |  | 2% | 6% |  | 5% | 11%
B.7 | Procurement of local and foreign materials, services and equipment |  | 5% | 10% |  | 2% | 10% |  | 8% | 10% |  | 5% | 40% |  | 0% | 3% |  | 1% | 10% |  | 5% | 30% |  | 10% | 25% |  | 3% | 6% |  | 2% | 10% |  | 10% | 20% |  | 10% | 25% |  | 1% | 2% |  | 2% | 2% |  | 1% | 10% |  | 5% | 15% |  | 2% | 5% |  | 2% | 5% |  | 4% | 7%
B.8 | Country infrastructure (power, roads, rail, water ports) |  | 4% | 9% |  | 2% | 10% |  | 5% | 10% |  | 5% | 35% |  | 0% | 5% |  | 1% | 15% |  | 5% | 20% |  | 10% | 50% |  | 4% | 8% |  | 2% | 15% |  | 3% | 10% |  | 10% | 20% |  | 1% | 2% |  | 5% | 2% |  | 2% | 10% |  | 3% | 10% |  | 2% | 5% |  | 2% | 8% |  | 5% | 11%
B.9 | Custom duties & logistic routes |  | 4% | 10% |  | 2% | 5% |  | 6% | 10% |  | 5% | 35% |  | 1% | 3% |  | 1% | 5% |  | 5% | 25% |  | 10% | 50% |  | 0% | 1% |  | 2% | 10% |  | 2% | 20% |  | 10% | 25% |  | 1% | 3% |  | 2% | 3% |  | 5% | 20% |  | 3% | 10% |  | 1% | 5% |  | 2% | 7% |  | 3% | 7%
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY
C.1 | Resouces secured (including land and mineral rights) |  | 1% | 10% |  | 2% | 10% |  | 10% | 20% |  | 5% | 35% |  | 0% | 5% |  | 2% | 35% |  | 5% | 30% |  | 10% | 50% |  | 2% | 6% |  | 1% | 50% |  | 1% | 10% |  | 0% | 20% |  | 1% | 4% |  | 2% | 5% |  | 1% | 10% |  | 5% | 20% |  | 0% | 50% |  | 1% | 5% |  | 4% | 11%
C.2 | Financing secured (Internal, external, equity, debt) |  | 2% | 9% |  | 1% | 5% |  | 10% | 20% |  | 5% | 35% |  | 0% | 5% |  | 1% | 10% |  | 2% | 15% |  | 10% | 50% |  | 4% | 8% |  | 1% | 50% |  | 3% | 11% |  | 0% | 5% |  | 1% | 5% |  | 2% | 5% |  | 3% | 25% |  | 5% | 15% |  | 7% | 50% |  | 1% | 4% |  | 3% | 7%
C.3 | Business Plan |  | 3% | 7% |  | 1% | 10% |  | 8% | 15% |  | 5% | 35% |  | 0% | 2% |  | 5% | 25% |  | 2% | 30% |  | 10% | 50% |  | 2% | 4% |  | 2% | 20% |  | 2% | 9% |  | 0% | 10% |  | 2% | 4% |  | 2% | 4% |  | 2% | 20% |  | 2% | 15% |  | 1% | 5% |  | 1% | 5% |  | 1% | 5%
C.4 | Economic Analysis |  | 4% | 10% |  | 1% | 10% |  | 7.5% | 10% |  | 5% | 35% |  | 0% | 2% |  | 5% | 25% |  | 2% | 20% |  | 10% | 30% |  | 1% | 2% |  | 5% | 15% |  | 2% | 10% |  | 5% | 15% |  | 2% | 3% |  | 2% | 5% |  | 5% | 30% |  | 1% | 15% |  | 2% | 30% |  | 1% | 5% |  | 2% | 7%
C.5 | Affordability / Feasibility |  | 3% | 7% |  | 1% | 10% |  | 10% | 20% |  | 5% | 35% |  | 0% | 3% |  | 5% | 25% |  | 2% | 30% |  | 10% | 50% |  | 3% | 6% |  | 5% | 25% |  | 2% | 10% |  | 0% | 1% |  | 1% | 3% |  | 2% | 5% |  | 1% | 15% |  | 1% | 15% |  | 5% | 40% |  | 1% | 5% |  | 3% | 6%
C.6 | Contingencies (Capex & Opex) |  | 5% | 10% |  | 5% | 20% |  | 5% | 10% |  | 5% | 25% |  | 3% | 35% |  | 10% | 35% |  | 5% | 30% |  | 10% | 25% |  | 2% | 4% |  | 3% | 20% |  | 1% | 10% |  | 10% | 20% |  | 5% | 15% |  | 8% | 15% |  | 5% | 20% |  | 10% | 30% |  | 7% | 30% |  | 5% | 15% |  | 5% | 10%
C.7 | Basis of Estimate |  | 3% | 8% |  | 2% | 7% |  | 5% | 10% |  | 5% | 25% |  | 2% | 5% |  | 10% | 35% |  | 5% | 35% |  | 10% | 20% |  | 2% | 4% |  | 3% | 15% |  | 1% | 11% |  | 5% | 10% |  | 1% | 2% |  | 2% | 5% |  | 1% | 25% |  | 5% | 25% |  | 7% | 50% |  | 2% | 5% |  | 4% | 9%
C.8 | Scenario planning |  | 2% | 7% |  | 1% | 2% |  | 8% | 10% |  | 5% | 25% |  | 2% | 5% |  | 5% | 15% |  | 5% | 20% |  | 10% | 35% |  | 1% | 2% |  | 2% | 10% |  | 2% | 12% |  | 0% | 15% |  | 2% | 6% |  | 0% | 2% |  | 5% | 10% |  | 5% | 20% |  | 0% | 25% |  | 2% | 4% |  | 3% | 5%
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT
D.1 | Metallurgical yield |  | 4% | 8% |  | 1% | 5% |  | 10% | 20% |  | 5% | 35% |  | 3% | 30% |  |  |  |  | 5% | 35% |  | 5% | 50% |  | 3% | 6% |  | 5% | 20% |  | 1% | 15% |  | 0% | 5% |  | 1% | 2% |  | 2% | 5% |  | 1% | 5% |  | 10% | 50% |  | 2% | 50% |  | 5% | 15% |  | 3% | 9%
D.2 | Reserve risks (including modifying factors) |  | 4% | 10% |  | 1% | 5% |  | 10% | 20% |  | 5% | 25% |  | 15% | 50% |  |  |  |  | 5% | 30% |  | 5% | 50% |  | 4% | 8% |  | 5% | 30% |  | 3% | 16% |  | 0% | 5% |  | 1% | 2% |  | 5% | 10% |  | 2% | 10% |  | 10% | 50% |  | 1% | 50% |  | 2% | 15% |  | 2% | 5%
D.3 | Grade engineering / control |  | 4% | 9% |  | 1% | 5% |  | 5% | 10% |  | 5% | 25% |  | 5% | 15% |  |  |  |  | 5% | 15% |  | 5% | 30% |  | 2% | 4% |  | 3% | 10% |  | 4% | 14% |  | 0% | 5% |  | 1% | 2% |  | 5% | 10% |  | 1% | 5% |  | 10% | 50% |  | 2% | 50% |  | 2% | 10% |  | 3% | 7%
D.4 | Prospect drilling standard / guideline |  | 3% | 8% |  | 1% | 7% |  | 10% | 15% |  | 5% | 25% |  | 3% | 5% |  |  |  |  | 5% | 10% |  | 5% | 30% |  | 1% | 2% |  | 2% | 15% |  | 2% | 13% |  | 0% | 15% |  | 1% | 2% |  | 2% | 2% |  | 2% | 15% |  | 5% | 40% |  | 1% | 30% |  | 2% | 10% |  | 2% | 10%
D.5 | Geological conditions (Geological model, structure, qualities) |  | 3% | 10% |  | 1% | 5% |  | 10% | 10% |  | 5% | 25% |  | 5% | 25% |  |  |  |  | 5% | 20% |  | 5% | 50% |  | 4% | 8% |  | 5% | 40% |  | 4% | 16% |  | 0% | 15% |  | 1% | 2% |  | 5% | 10% |  | 5% | 20% |  | 10% | 40% |  | 5% | 50% |  | 2% | 5% |  | 4% | 11%
D.6 | Hydrogeology |  | 2% | 8% |  | 1% | 5% |  | 10% | 10% |  | 5% | 25% |  | 5% | 10% |  |  |  |  | 2% | 7% |  | 5% | 30% |  | 1% | 2% |  | 5% | 15% |  | 5% | 15% |  | 5% | 15% |  | 1% | 2% |  | 2% | 5% |  | 5% | 20% |  | 5% | 25% |  | 1% | 25% |  | 2% | 8% |  | 5% | 8%
Total | CATEGORY D (Maximum = )
E | LIFE OF MINE PLANNING
E.1 | Mine design criteria |  | 3% | 10% |  | 1% | 7% |  | 7.5% | 10% |  | 5% | 25% |  | 1% | 5% |  | 2% | 15% |  | 5% | 20% |  | 10% | 30% |  | 2% | 4% |  | 2% | 25% |  | 2% | 14% |  | 5% | 10% |  | 1% | 2% |  | 2% | 4% |  | 2% | 10% |  | 5% | 25% |  | 1% | 50% |  | 5% | 10% |  | 3% | 9%
E.2 | Shaft/ramp design & men and material logistics |  | 3% | 10% |  | 2% | 5% |  | 7.5% | 5% |  | 5% | 25% |  | 0% | 1% |  | 2% | 15% |  | 5% | 15% |  | 10% | 30% |  | 2% | 4% |  | 2% | 25% |  | 2% | 16% |  | 5% | 25% |  | 1% | 2% |  | 2% | 4% |  | 2% | 15% |  | 5% | 15% |  | 1% | 50% |  | 2% | 5% |  | 4% | 10%
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | 2% | 8% |  | 2% | 5% |  | 5% | 10% |  | 5% | 25% |  | 0% | 5% |  | 5% | 20% |  | 2% | 10% |  | 10% | 30% |  | 2% | 4% |  | 2% | 25% |  | 2% | 14% |  | 0% | 5% |  | 1% | 2% |  | 2% | 4% |  | 1% | 20% |  | 5% | 30% |  | 1% | 50% |  | 2% | 5% |  | 1% | 5%
E.4 | Equipment selection to fit geological conditions and mining method |  | 2% | 8% |  | 2% | 5% |  | 7.5% | 5% |  | 5% | 25% |  | 1% | 5% |  | 5% | 20% |  | 5% | 20% |  | 10% | 30% |  | 2% | 4% |  | 2% | 20% |  | 1% | 9% |  | 0% | 5% |  | 1% | 2% |  | 2% | 4% |  | 1% | 5% |  | 5% | 30% |  | 1% | 50% |  | 2% | 5% |  | 2% | 7%
E.5 | Life-of-mine plan |  | 4% | 9% |  | 2% | 7% |  | 10% | 20% |  | 5% | 25% |  | 0% | 10% |  | 10% | 35% |  | 2% | 10% |  | 10% | 50% |  | 3% | 6% |  | 1% | 15% |  | 1% | 5% |  | 0% | 5% |  | 1% | 2% |  | 1% | 2% |  | 1% | 15% |  | 5% | 25% |  | 1% | 25% |  | 2% | 4% |  | 3% | 7%
E.6 | Waste management plan |  | 2% | 7% |  | 1% | 5% |  | 7.5% | 5% |  | 5% | 25% |  | 0% | 1% |  | 10% | 35% |  | 2% | 10% |  | 10% | 30% |  | 2% | 4% |  | 1% | 15% |  | 3% | 12% |  | 5% | 20% |  | 1% | 2% |  | 1% | 2% |  | 3% | 10% |  | 5% | 25% |  | 1% | 5% |  | 2% | 4% |  | 2% | 4%
E.7 | Ultimate pit limits designed |  | 2% | 7% |  | 1% | 5% |  | 10% | 10% |  | 5% | 25% |  | 3% | 10% |  | 2% | 15% |  | 2% | 5% |  | 10% | 30% |  | 2% | 4% |  | 1% | 15% |  | 1% | 8% |  | 0% | 5% |  | 1% | 2% |  | 1% | 2% |  | 1% | 5% |  | 5% | 25% |  | 5% | 50% |  | 2% | 10% |  | 3% | 5%
E.8 | Economic block values determination |  | 3% | 9% |  | 1% | 3% |  | 7.5% | 10% |  | 5% | 25% |  | 3% | 25% |  | 10% | 35% |  | 2% | 30% |  | 10% | 50% |  | 2% | 4% |  | 2% | 15% |  | 3% | 12% |  | 0% | 5% |  | 1% | 2% |  | 1% | 5% |  | 2% | 10% |  | 5% | 25% |  | 3% | 30% |  | 2% | 10% |  | 4% | 7%
E.9 | Beneficiation facilities LOM plan |  | 4% | 8% |  | 2% | 5% |  | 7.5% | 10% |  | 5% | 25% |  | 3% | 12% |  | 5% | 20% |  | 2% | 30% |  | 10% | 50% |  | 2% | 4% |  | 2% | 10% |  | 3% | 10% |  | 5% | 15% |  | 1% | 2% |  | 1% | 5% |  | 2% | 15% |  | 5% | 25% |  | 2% | 25% |  | 2% | 8% |  | 2% | 4%
E.10 | Materials handling LOM plan |  | 4% | 8% |  | 2% | 5% |  | 7.5% | 10% |  | 5% | 25% |  | 1% | 3% |  | 5% | 20% |  | 2% | 30% |  | 10% | 50% |  | 1% | 2% |  | 2% | 10% |  | 3% | 10% |  | 5% | 20% |  | 1% | 2% |  | 1% | 2% |  | 5% | 20% |  | 5% | 20% |  | 1% | 25% |  | 2% | 5% |  | 5% | 8%
Total | CATEGORY E (Maximum = )
F | OPERATING PHILOSOPHY
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | 3% | 10% |  | 2% | 4% |  | 7.5% | 10% |  | 5% | 20% |  | 0% | 5% |  | 1% | 5% |  | 2% | 10% |  | 5% | 20% |  | 3% | 6% |  | 2% | 8% |  | 2% | 8% |  | 0% | 5% |  | 1% | 2% |  | 1% | 2% |  | 3% | 10% |  | 3% | 15% |  | 5% | 40% |  | 2% | 5% |  | 2% | 9%
F.2 | Productivity / efficiency benchmarks |  | 2% | 9% |  | 2% | 5% |  | 5% | 5% |  | 5% | 20% |  | 1% | 3% |  | 1% | 1% |  | 2% | 5% |  | 5% | 15% |  | 3% | 6% |  | 2% | 6% |  | 3% | 12% |  | 2% | 10% |  | 2% | 4% |  | 0% | 2% |  | 2% | 15% |  | 4% | 25% |  | 1% | 5% |  | 5% | 10% |  | 2% | 7%
F.3 | Operating costs |  | 2% | 7% |  | 1% | 7% |  | 10% | 10% |  | 5% | 30% |  | 10% | 35% |  | 5% | 15% |  | 2% | 20% |  | 5% | 50% |  | 3% | 6% |  | 2% | 10% |  | 3% | 15% |  | 5% | 20% |  | 1% | 3% |  | 2% | 10% |  | 1% | 20% |  | 4% | 25% |  | 5% | 50% |  | 5% | 10% |  | 4% | 10%
F.4 | Production risks |  | 2% | 7% |  | 1% | 7% |  | 5% | 8% |  | 5% | 30% |  | 5% | 35% |  | 1% | 15% |  | 5% | 25% |  | 10% | 30% |  | 3% | 6% |  | 2% | 10% |  | 3% | 15% |  | 5% | 20% |  | 1% | 2% |  | 2% | 5% |  | 2% | 15% |  | 3% | 20% |  | 7% | 50% |  | 4% | 10% |  | 3% | 6%
F.5 | Catalogue of operating plans |  | 3% | 8% |  | 1% | 5% |  | 5% | 5% |  | 5% | 20% |  | 1% | 5% |  | 1% | 1% |  | 5% | 20% |  | 10% | 20% |  | 1% | 2% |  | 1% | 5% |  | 1% | 7% |  | 5% | 15% |  | 1% | 2% |  | 0% | 2% |  | 2% | 15% |  | 2% | 15% |  | 1% | 5% |  | 4% | 12% |  | 4% | 7%
F.6 | Haul roads |  | 2% | 8% |  | 1% | 4% |  | 5% | 10% |  | 5% | 25% |  | 1% | 4% |  | 1% | 5% |  | 5% | 10% |  | 10% | 35% |  | 2% | 4% |  | 2% | 7% |  | 2% | 9% |  | 0% | 25% |  | 1% | 2% |  | 1% | 2% |  | 1% | 10% |  | 2% | 20% |  | 0% | 25% |  | 1% | 8% |  | 3% | 8%
F.7 | Transportation strategy |  | 2% | 9% |  | 1% | 4% |  | 5% | 8% |  | 5% | 25% |  | 4% | 15% |  | 2% | 10% |  | 5% | 10% |  | 10% | 20% |  | 2% | 4% |  | 1% | 8% |  | 3% | 12% |  | 5% | 20% |  | 1% | 2% |  | 0% | 2% |  | 1% | 15% |  | 2% | 20% |  | 2% | 25% |  | 1% | 7% |  | 1% | 4%
F.8 | Contractual considerations |  | 2% | 10% |  | 1% | 4% |  | 5% | 8% |  | 5% | 20% |  | 1% | 8% |  | 2% | 10% |  | 5% | 20% |  | 5% | 10% |  | 2% | 4% |  | 2% | 6% |  | 4% | 15% |  | 5% | 15% |  | 2% | 4% |  | 0% | 2% |  | 5% | 20% |  | 2% | 20% |  | 2% | 25% |  | 2% | 4% |  | 2% | 5%
Total | CATEGORY F (Maximum = )
G | MARKET ANALYSIS AND STRATEGY
G.1 | Market Strategy & Sales Agreements |  | 2% | 8% |  | 1% | 5% |  | 10% | 10% |  | 5% | 25% |  | 1% | 10% |  | 10% | 35% |  | 5% | 30% |  | 10% | 50% |  | 4% | 8% |  | 5% | 15% |  | 1% | 8% |  | 0% | 5% |  | 1% | 2% |  | 0% | 5% |  | 1% | 5% |  | 2% | 25% |  | 5% | 35% |  | 2% | 10% |  | 1% | 3%
G.2 | Price risks |  | 4% | 10% |  | 2% | 7% |  | 7.5% | 7.5% |  | 5% | 30% |  | 5% | 35% |  | 10% | 35% |  | 5% | 25% |  | 10% | 50% |  | 5% | 10% |  | 5% | 10% |  | 3% | 13% |  | 0% | 5% |  | 1% | 2% |  | 5% | 15% |  | 2% | 10% |  | 5% | 25% |  | 10% | 35% |  | 2% | 8% |  | 3% | 8%
G.3 | Demand risks & replacement products / technologies |  | 3% | 9% |  | 3% | 7% |  | 7.5% | 7.5% |  | 5% | 30% |  | 5% | 25% |  | 10% | 35% |  | 5% | 30% |  | 10% | 50% |  | 3% | 6% |  | 2% | 10% |  | 2% | 15% |  | 0% | 5% |  | 1% | 2% |  | 5% | 10% |  | 1% | 5% |  | 5% | 15% |  | 10% | 50% |  | 2% | 10% |  | 1% | 3%
G.4 | Value-Analysis Process |  | 3% | 7% |  | 1% | 5% |  | 7.5% | 7.5% |  | 5% | 25% |  | 3% | 15% |  | 5% | 20% |  | 3% | 5% |  | 10% | 35% |  | 2% | 4% |  | 2% | 15% |  | 1% | 7% |  | 0% | 5% |  | 1% | 2% |  | 0% | 3% |  | 5% | 15% |  | 3% | 15% |  | 5% | 35% |  | 2% | 6% |  | 2% | 4%
G.5 | Hedging |  | 2% | 7% |  | 1% | 3% |  | 5% | 5% |  | 5% | 25% |  | 3% | 15% |  | 2% | 10% |  | 3% | 7% |  | 10% | 30% |  | 1% | 2% |  | 2% | 5% |  | 1% | 8% |  | 0% | 5% |  | 1% | 2% |  | 0% | 2% |  | 1% | 2% |  | 2% | 10% |  | 5% | 5% |  | 4% | 8% |  | 3% | 6%
G.6 | Competitor analysis |  | 3% | 7% |  | 1% | 3% |  | 5% | 5% |  | 5% | 20% |  | 1% | 8% |  | 1% | 5% |  | 2% | 5% |  | 10% | 30% |  | 3% | 6% |  | 2% | 6% |  | 1% | 5% |  | 0% | 1% |  | 1% | 2% |  | 0% | 3% |  | 5% | 15% |  | 2% | 15% |  | 2% | 5% |  |  |  |  | 2% | 7%
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
H | PROJECT CONSIDERATIONS
H.1 | Expected Project Life Cycle |  | 3% | 10% |  | 1% | 5% |  | 5% | 5% |  | 5% | 35% |  | 1% | 5% |  | 10% | 25% |  | 5% | 30% |  | 10% | 25% |  | 2% | 4% |  | 2% | 8% |  | 1% | 6% |  | 5% | 20% |  | 3% | 7% |  | 1% | 2% |  | 5% | 20% |  | 5% | 30% |  | 5% | 5% |  | 0% | 5% |  | 3% | 6%
H.2 | Assumption register |  | 2% | 6% |  | 1% | 2% |  | 5% | 5% |  | 5% | 15% |  | 3% | 15% |  | 2% | 5% |  | 5% | 10% |  | 10% | 25% |  | 1% | 2% |  | 1% | 5% |  | 1% | 3% |  | 1% | 15% |  | 2% | 5% |  | 1% | 2% |  | 2% | 15% |  | 2% | 10% |  | 3% | 35% |  | 5% | 10% |  | 4% | 7%
H.3 | Completion risks |  | 3% | 7% |  | 3% | 7% |  | 5% | 5% |  | 5% | 25% |  | 5% | 15% |  | 2% | 5% |  | 5% | 10% |  | 10% | 25% |  | 2% | 4% |  | 1% | 6% |  | 1% | 4% |  | 5% | 20% |  | 3% | 6% |  | 1% | 2% |  | 5% | 25% |  | 2% | 15% |  | 10% | 35% |  | 5% | 5% |  | 2% | 9%
H.4 | Project Design Criteria |  | 2% | 8% |  | 2% | 5% |  | 10% | 5% |  | 5% | 35% |  | 1% | 15% |  | 2% | 5% |  | 5% | 30% |  | 10% | 35% |  | 1% | 2% |  | 2% | 10% |  | 1% | 5% |  | 5% | 25% |  | 2% | 4% |  | 1% | 2% |  | 2% | 30% |  | 2% | 25% |  | 1% | 35% |  | 2% | 10% |  | 3% | 11%
H.5 | Scope of Work Overview |  | 2% | 8% |  | 1% | 7% |  | 7.5% | 20% |  | 5% | 35% |  | 3% | 25% |  | 2% | 5% |  | 5% | 30% |  | 10% | 50% |  | 3% | 6% |  | 2% | 10% |  | 1% | 10% |  | 5% | 30% |  | 2% | 5% |  | 5% | 10% |  | 5% | 30% |  | 5% | 30% |  | 2% | 35% |  | 2% | 15% |  | 3% | 10%
H.6 | Project Schedule |  | 4% | 10% |  | 2% | 10% |  | 7.5% | 20% |  | 5% | 35% |  | 5% | 25% |  | 10% | 25% |  | 2% | 25% |  | 10% | 35% |  | 4% | 8% |  | 2% | 10% |  | 1% | 10% |  | 5% | 30% |  | 4% | 10% |  | 2% | 10% |  | 5% | 45% |  | 5% | 30% |  | 5% | 35% |  | 2% | 15% |  | 2% | 8%
H.7 | Project Cost Estimate |  | 4% | 10% |  | 5% | 20% |  | 10% | 20% |  | 5% | 25% |  | 3% | 35% |  | 10% | 25% |  | 5% | 25% |  | 10% | 35% |  | 4% | 8% |  | 2% | 10% |  | 1% | 10% |  | 5% | 35% |  | 5% | 8% |  | 5% | 15% |  | 5% | 50% |  | 5% | 30% |  | 5% | 35% |  | 10% | 15% |  | 0% | 7%
H.8 | Investment Studies & Alternatives Assessments |  | 2% | 7% |  | 1% | 15% |  | 7.5% | 10% |  | 5% | 25% |  | 1% | 5% |  | 2% | 10% |  | 5% | 15% |  | 10% | 25% |  | 2% | 4% |  | 1% | 20% |  | 1% | 8% |  | 0% | 10% |  | 2% | 4% |  | 1% | 4% |  | 5% | 15% |  | 5% | 25% |  | 2% | 35% |  | 2% | 8% |  | 1% | 4%
H.9 | Key Team Member Coordination |  | 2% | 7% |  | 0% | 2% |  | 5% | 10% |  | 5% | 25% |  | 1% | 4% |  | 2% | 10% |  | 5% | 15% |  | 10% | 25% |  | 4% | 8% |  | 0% | 6% |  | 1% | 4% |  | 5% | 20% |  | 1% | 2% |  | 0% | 2% |  | 2% | 10% |  | 5% | 15% |  | 7% | 35% |  | 2% | 5% |  | 1% | 5%
H.10 | Evaluation of Compliance Requirements |  | 2% | 8% |  | 1% | 5% |  | 5% | 8% |  | 5% | 35% |  | 1% | 3% |  | 5% | 15% |  | 3% | 25% |  | 10% | 50% |  | 3% | 6% |  | 2% | 20% |  | 1% | 3% |  | 5% | 30% |  | 1% | 2% |  | 0% | 2% |  | 5% | 20% |  | 5% | 25% |  | 3% | 35% |  | 2% | 5% |  | 2% | 4%
H.11 | Lead / Discipline Scope of Work |  | 1% | 8% |  | 0% | 2% |  | 10% | 15% |  | 5% | 25% |  | 2% | 5% |  | 2% | 5% |  | 3% | 25% |  | 10% | 25% |  | 3% | 6% |  | 1% | 6% |  | 1% | 3% |  | 5% | 25% |  | 2% | 3% |  | 2% | 5% |  | 2% | 30% |  | 5% | 25% |  | 2% | 35% |  | 5% | 10% |  | 3% | 6%
H.12 | Housing and transport of employees |  | 3% | 10% |  | 0% | 3% |  | 7.5% | 10% |  | 5% | 25% |  | 1% | 4% |  | 2% | 5% |  | 3% | 15% |  | 10% | 25% |  | 2% | 4% |  | 2% | 8% |  | 1% | 3% |  | 5% | 10% |  | 1% | 2% |  | 2% | 3% |  | 1% | 5% |  | 2% | 10% |  | 1% | 35% |  | 2% | 5% |  | 2% | 7%
H.13 | Risk or impact on other projects / divisions |  | 2% | 7% |  | 0% | 1% |  | 7.5% | 5% |  | 5% | 25% |  | 1% | 5% |  | 2% | 5% |  | 3% | 10% |  | 10% | 25% |  | 2% | 4% |  | 2% | 6% |  | 1% | 5% |  | 5% | 10% |  | 1% | 2% |  | 1% | 2% |  | 1% | 5% |  | 2% | 10% |  | 1% | 35% |  | 2% | 8% |  | 3% | 10%
I | PROJECT SCOPE
I | PROJECT SCOPE
I.1 | Project Objectives Statement |  | 1% | 7% |  | 0% | 3% |  | 10% | 10% |  | 5% | 30% |  | 0% | 3% |  | 2% | 10% |  | 3% | 35% |  | 10% | 25% |  | 3% | 6% |  | 0% | 8% |  | 1% | 5% |  | 0% | 5% |  | 1% | 2% |  | 0% | 3% |  | 2% | 10% |  | 2% | 25% |  | 1% | 50% |  | 2% | 10% |  | 1% | 3%
I.2 | Site Characteristics Available vs. Required |  | 2% | 7% |  | 1% | 3% |  | 5% | 5% |  | 5% | 25% |  | 1% | 5% |  | 2% | 10% |  | 3% | 30% |  | 10% | 25% |  | 2% | 4% |  | 2% | 5% |  | 1% | 6% |  | 5% | 7% |  | 1% | 2% |  | 1% | 2% |  | 1% | 25% |  | 2% | 20% |  | 3% | 35% |  | 2% | 10% |  | 3% | 5%
I.3 | Project Scope definition |  | 2% | 9% |  | 1% | 5% |  | 10% | 15% |  | 5% | 35% |  | 3% | 20% |  | 10% | 25% |  | 3% | 35% |  | 10% | 25% |  | 3% | 6% |  | 2% | 10% |  | 1% | 8% |  | 5% | 30% |  | 2% | 4% |  | 2% | 10% |  | 5% | 30% |  | 5% | 25% |  | 2% | 40% |  | 5% | 15% |  | 2% | 7%
I.4 | WBS and WBS Dictionary |  | 2% | 8% |  | 2% | 5% |  | 7.5% | 10% |  | 5% | 25% |  | 1% | 10% |  | 10% | 25% |  | 3% | 35% |  | 10% | 25% |  | 2% | 4% |  | 2% | 10% |  | 1% | 10% |  | 2% | 30% |  | 2% | 4% |  | 0% | 5% |  | 2% | 40% |  | 5% | 25% |  | 1% | 35% |  | 2% | 15% |  | 4% | 6%
Total | CATEGORY I (Maximum = )
J | SOCIAL & ENVIRONMENTAL REQUIREMENTS
J.1 | Unique mine closure plan |  | 1% | 7% |  | 0% | 5% |  | 5% | 10% |  | 5% | 25% |  | 1% | 3% |  | 1% | 5% |  | 2% | 10% |  | 10% | 20% |  | 2% | 4% |  | 1% | 5% |  | 5% | 15% |  | 1% | 10% |  | 1% | 2% |  | 2% | 5% |  | 5% | 30% |  | 2% | 8% |  | 1% | 20% |  | 0% | 5% |  | 3% | 7%
J.2 | Land use plan post operations |  | 1% | 7% |  | 1% | 3% |  | 5% | 8% |  | 5% | 20% |  | 1% | 3% |  | 1% | 5% |  | 2% | 5% |  | 10% | 20% |  | 1% | 2% |  | 1% | 5% |  | 5% | 15% |  | 0% | 5% |  | 1% | 2% |  | 1% | 2% |  | 5% | 50% |  | 2% | 8% |  | 1% | 20% |  | 2% | 5% |  | 4% | 6%
J.3 | Social expectations register |  | 2% | 7% |  | 1% | 3% |  | 5% | 8% |  | 5% | 30% |  | 2% | 5% |  | 1% | 5% |  | 2% | 8% |  | 10% | 20% |  | 2% | 4% |  | 1% | 5% |  | 5% | 20% |  | 5% | 15% |  | 1% | 2% |  | 0% | 2% |  | 1% | 20% |  | 3% | 10% |  | 1% | 20% |  | 2% | 5% |  | 3% | 7%
J.4 | Relocation Action Plan |  | 2% | 9% |  | 2% | 5% |  | 7.5% | 8% |  | 5% | 40% |  | 2% | 5% |  | 10% | 35% |  | 2% | 30% |  | 10% | 20% |  | 3% | 6% |  | 2% | 10% |  | 15% | 30% |  | 10% | 30% |  | 1% | 2% |  | 2% | 5% |  | 2% | 20% |  | 3% | 10% |  | 1% | 20% |  | 2% | 8% |  | 2% | 5%
J.5 | Environmental expectations register |  | 1% | 8% |  | 1% | 5% |  | 5% | 5% |  | 5% | 25% |  | 2% | 8% |  | 5% | 15% |  | 2% | 20% |  | 10% | 20% |  | 2% | 4% |  | 1% | 10% |  | 5% | 13% |  | 5% | 15% |  | 1% | 2% |  | 0% | 3% |  | 5% | 15% |  | 3% | 15% |  | 1% | 20% |  | 2% | 5% |  | 0% | 3%
J.6 | Political expectations register |  | 2% | 10% |  | 1% | 3% |  | 5% | 5% |  | 5% | 25% |  | 3% | 8% |  | 1% | 5% |  | 2% | 8% |  | 10% | 20% |  | 4% | 8% |  | 1% | 6% |  | 5% | 15% |  | 5% | 20% |  | 1% | 2% |  | 0% | 2% |  | 2% | 20% |  | 1% | 10% |  | 1% | 20% |  | 2% | 5% |  | 1% | 4%
J.7 | Legal compliance register |  | 2% | 8% |  | 2% | 7% |  | 10% | 10% |  | 5% | 25% |  | 1% | 4% |  | 10% | 35% |  | 2% | 25% |  | 10% | 30% |  | 3% | 6% |  | 1% | 8% |  | 4% | 12% |  | 5% | 15% |  | 1% | 2% |  | 0% | 5% |  | 1% | 20% |  | 1% | 10% |  | 1% | 20% |  | 2% | 8% |  | 4% | 8%
J.8 | HSE risk register |  | 3% | 8% |  | 2% | 5% |  | 5% | 5% |  | 5% | 20% |  | 0% | 3% |  | 1% | 5% |  | 5% | 18% |  | 10% | 30% |  | 2% | 4% |  | 2% | 10% |  | 2% | 8% |  | 5% | 10% |  | 1% | 2% |  | 0% | 5% |  | 1% | 20% |  | 3% | 15% |  | 1% | 20% |  | 2% | 8% |  | 2% | 4%
J.9 | Community risk register |  | 2% | 7% |  | 2% | 5% |  | 5% | 5% |  | 5% | 25% |  | 3% | 8% |  | 2% | 10% |  | 2% | 15% |  | 10% | 30% |  | 4% | 8% |  | 2% | 6% |  | 10% | 20% |  | 1% | 15% |  | 1% | 2% |  | 0% | 5% |  | 5% | 25% |  | 3% | 10% |  | 1% | 20% |  | 2% | 8% |  | 3% | 8%
J.10 | Business risk register |  | 2% | 7% |  | 1% | 5% |  | 7.5% | 5% |  | 5% | 25% |  | 2% | 8% |  | 1% | 5% |  | 2% | 20% |  | 10% | 30% |  | 2% | 4% |  | 1% | 7% |  | 1% | 7% |  | 0% | 10% |  | 1% | 2% |  | 0% | 5% |  | 1% | 15% |  | 3% | 15% |  | 1% | 20% |  | 2% | 8% |  | 4% | 5%
J.11 | Developmental opportunity register |  | 2% | 7% |  | 0% | 3% |  | 5% | 5% |  | 5% | 25% |  | 1% | 3% |  | 1% | 5% |  | 5% | 10% |  | 10% | 20% |  | 1% | 2% |  | 0% | 3% |  | 4% | 14% |  | 5% | 20% |  | 1% | 2% |  | 0% | 5% |  | 1% | 10% |  | 3% | 15% |  | 1% | 20% |  | 2% | 5% |  | 3% | 6%
J.12 | Sustainability operating plan |  | 2% | 7% |  | 0% | 3% |  | 5% | 10% |  | 5% | 25% |  | 1% | 3% |  | 1% | 5% |  | 5% | 10% |  | 10% | 25% |  | 2% | 4% |  | 1% | 6% |  | 1% | 8% |  | 5% | 15% |  | 1% | 2% |  | 0% | 5% |  | 1% | 20% |  | 3% | 10% |  | 1% | 20% |  | 2% | 5% |  | 2% | 4%
J.13 | Stakeholder engagement plan |  | 4% | 9% |  | 1% | 3% |  | 10% | 10% |  | 5% | 25% |  | 3% | 5% |  | 1% | 5% |  | 2% | 10% |  | 10% | 25% |  | 2% | 4% |  | 0% | 7% |  | 5% | 16% |  | 2% | 10% |  | 1% | 2% |  | 0% | 5% |  | 1% | 20% |  | 2% | 10% |  | 1% | 20% |  | 2% | 10% |  | 1% | 4%
J.14 | Mine closure financial provision plan |  | 5% | 9% |  | 2% | 5% |  | 10% | 10% |  | 5% | 25% |  | 3% | 15% |  | 1% | 5% |  | 1% | 10% |  | 10% | 30% |  | 1% | 2% |  | 0% | 4% |  | 4% | 15% |  | 5% | 30% |  | 1% | 2% |  | 0% | 5% |  | 1% | 5% |  | 2% | 15% |  | 1% | 20% |  | 2% | 5% |  | 2% | 9%
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  | 2% | 8% |  | 1% | 3% |  | 5% | 10% |  | 5% | 20% |  | 1% | 10% |  | 1% | 5% |  | 2% | 10% |  | 5% | 30% |  | 1% | 2% |  | 0% | 4% |  | 1% | 9% |  | 0% | 10% |  | 1% | 2% |  | 0% | 5% |  | 2% | 10% |  | 2% | 10% |  | 1% | 20% |  | 2% | 8% |  | 2% | 4%
J.16 | Social investment plan |  | 3% | 7% |  | 0% | 2% |  | 5% | 10% |  | 5% | 30% |  | 1% | 3% |  | 1% | 5% |  | 2% | 8% |  | 5% | 20% |  | 2% | 4% |  | 0% | 6% |  | 5% | 14% |  | 5% | 30% |  | 1% | 2% |  | 0% | 5% |  | 1% | 20% |  | 2% | 10% |  | 1% | 20% |  | 2% | 5% |  | 3% | 6%
J.17 | Economic diversification plan |  | 2% | 7% |  | 0% | 2% |  | 5% | 10% |  | 5% | 25% |  | 1% | 2% |  | 1% | 5% |  | 1% | 5% |  | 5% | 20% |  | 2% | 4% |  | 0% | 4% |  | 3% | 10% |  | 5% | 30% |  | 1% | 2% |  | 0% | 5% |  | 1% | 15% |  | 2% | 10% |  | 1% | 20% |  | 2% | 5% |  | 3% | 5%
J.18 | Existing Environmental Conditions |  | 1% | 8% |  | 1% | 5% |  | 5% | 10% |  | 5% | 25% |  | 2% | 7% |  | 1% | 5% |  | 1% | 5% |  | 5% | 20% |  | 1% | 2% |  | 1% | 5% |  | 1% | 8% |  | 2% | 15% |  | 1% | 2% |  | 0% | 5% |  | 1% | 20% |  | 2% | 15% |  | 1% | 20% |  | 2% | 5% |  | 4% | 6%
J.19 | Environmental Process determined |  | 2% | 7% |  | 1% | 5% |  | 5% | 10% |  | 5% | 25% |  | 1% | 8% |  | 1% | 5% |  | 2% | 8% |  | 5% | 20% |  | 2% | 4% |  | 1% | 6% |  | 1% | 10% |  | 2% | 10% |  | 1% | 2% |  | 0% | 5% |  | 1% | 15% |  | 2% | 15% |  | 1% | 20% |  | 2% | 5% |  | 3% | 6%
J.20 | Environmental management plan |  | 1% | 7% |  | 2% | 5% |  | 5% | 10% |  | 5% | 25% |  | 3% | 12% |  | 1% | 5% |  | 1% | 5% |  | 5% | 20% |  | 2% | 4% |  | 1% | 6% |  | 2% | 12% |  | 5% | 25% |  | 1% | 2% |  | 0% | 5% |  | 5% | 60% |  | 2% | 15% |  | 1% | 20% |  | 2% | 8% |  | 2% | 4%
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
K | SITE INFORMATION
K.1 | Site Layout |  | 2% | 8% |  | 2% | 7% |  | 5% | 5% |  | 5% | 25% |  | 1% | 5% |  | 2% | 15% |  | 1% | 10% |  | 10% | 50% |  | 1% | 2% |  | 1% | 5% |  | 1% | 5% |  | 2% | 10% |  | 2% | 3% |  | 2% | 5% |  | 5% | 20% |  | 5% | 25% |  | 2% | 40% |  | 3% | 8% |  | 3% | 5%
K.2 | Site Surveys |  | 2% | 8% |  | 1% | 5% |  | 5% | 5% |  | 5% | 25% |  | 1% | 5% |  | 2% | 15% |  | 1% | 5% |  | 10% | 50% |  | 1% | 2% |  | 1% | 5% |  | 1% | 6% |  | 5% | 15% |  | 2% | 5% |  | 2% | 5% |  | 2% | 15% |  | 3% | 20% |  | 2% | 40% |  | 1% | 5% |  | 2% | 4%
K.3 | Governing Regulatory Requirements |  | 4% | 10% |  | 0% | 2% |  | 10% | 10% |  | 5% | 35% |  | 0% | 5% |  | 1% | 25% |  | 1% | 20% |  | 10% | 30% |  | 2% | 4% |  | 1% | 5% |  | 1% | 6% |  | 1% | 5% |  | 1% | 2% |  | 2% | 5% |  | 1% | 15% |  | 3% | 20% |  | 2% | 40% |  | 1% | 8% |  | 3% | 6%
K.4 | Utility Sources with Supply Conditions |  | 2% | 9% |  | 2% | 5% |  | 5% | 5% |  | 5% | 30% |  | 2% | 5% |  | 2% | 20% |  | 2% | 25% |  | 10% | 25% |  | 1% | 2% |  | 1% | 5% |  | 1% | 7% |  | 1% | 5% |  | 1% | 2% |  | 2% | 5% |  | 1% | 20% |  | 3% | 20% |  | 5% | 50% |  | 2% | 5% |  | 3% | 7%
K.5 | Fire Protection, emergency procedure & Safety Considerations |  | 1% | 6% |  | 1% | 5% |  | 10% | 10% |  | 5% | 25% |  | 1% | 5% |  | 1% | 5% |  | 2% | 10% |  | 10% | 20% |  | 1% | 2% |  | 1% | 4% |  | 1% | 5% |  | 5% | 10% |  | 1% | 2% |  | 2% | 5% |  | 1% | 10% |  | 3% | 20% |  | 1% | 5% |  | 2% | 5% |  | 4% | 9%
K.6 | Special Water and Waste Treatment Requirements |  | 2% | 7% |  | 2% | 6% |  | 5% | 5% |  | 5% | 25% |  | 1% | 5% |  | 1% | 5% |  | 2% | 10% |  | 10% | 25% |  | 2% | 4% |  | 1% | 4% |  | 1% | 5% |  | 0% | 5% |  | 1% | 2% |  | 2% | 5% |  | 3% | 15% |  | 3% | 20% |  | 0% | 50% |  | 2% | 5% |  | 4% | 7%
K.7 | Property Descriptions |  | 1% | 6% |  | 1% | 2% |  | 5% | 5% |  | 5% | 20% |  | 2% | 5% |  | 1% | 2% |  | 2% | 8% |  | 10% | 20% |  | 1% | 2% |  | 0% | 3% |  | 1% | 3% |  | 0% | 0% |  | 1% | 2% |  | 2% | 5% |  | 1% | 10% |  | 1% | 10% |  | 0% | 5% |  | 2% | 4% |  | 1% | 4%
K.8 | Right-of-Way Mapping & Site Issues |  | 2% | 7% |  | 1% | 4% |  | 5% | 5% |  | 5% | 25% |  | 1% | 6% |  | 1% | 2% |  | 2% | 8% |  | 10% | 30% |  | 1% | 2% |  | 1% | 5% |  | 1% | 4% |  | 0% | 2% |  | 1% | 2% |  | 2% | 5% |  | 2% | 10% |  | 2% | 20% |  | 1% | 50% |  | 2% | 5% |  | 2% | 3%
K.9 | Land Rights |  | 3% | 10% |  | 3% | 7% |  | 10% | 10% |  | 5% | 35% |  | 3% | 9% |  | 1% | 20% |  | 2% | 15% |  | 10% | 50% |  | 3% | 6% |  | 0% | 6% |  | 1% | 8% |  | 0% | 5% |  | 1% | 2% |  | 2% | 5% |  | 1% | 15% |  | 2% | 20% |  | 1% | 50% |  | 2% | 10% |  | 2% | 5%
Total | CATEGORY K (Maximum = )
L | PROJECT DESIGN PARAMETERS
L.1 | Design Criteria |  | 2% | 8% |  | 3% | 7% |  | 7.5% | 10% |  | 5% | 35% |  | 1% | 3% |  | 1% | 3% |  | 2% | 10% |  | 5% | 30% |  | 1% | 2% |  | 1% | 8% |  | 1% | 10% |  | 1% | 15% |  | 3% | 5% |  | 2% | 5% |  | 5% | 15% |  | 2% | 25% |  | 1% | 35% |  | 2% | 8% |  | 1% | 4%
L.2 | Civil/Site Design |  | 2% | 7% |  | 5% | 10% |  | 7.5% | 10% |  | 5% | 25% |  | 2% | 8% |  | 1% | 3% |  | 2% | 15% |  | 5% | 30% |  | 2% | 4% |  | 1% | 6% |  | 1% | 8% |  | 1% | 10% |  | 3% | 5% |  | 2% | 5% |  | 5% | 20% |  | 2% | 25% |  | 1% | 35% |  | 2% | 5% |  | 2% | 5%
L.3 | Geotechnical investigation for structures |  | 1% | 7% |  | 5% | 10% |  | 5% | 7% |  | 5% | 25% |  | 1% | 5% |  | 5% | 25% |  | 2% | 15% |  | 5% | 30% |  | 2% | 4% |  | 1% | 10% |  | 2% | 13% |  | 0% | 5% |  | 3% | 5% |  | 2% | 5% |  | 10% | 30% |  | 2% | 25% |  | 1% | 35% |  | 2% | 5% |  | 1% | 6%
L.4 | Architectural Design |  | 1% | 6% |  | 2% | 5% |  | 5% | 7% |  | 5% | 20% |  | 0% | 3% |  | 1% | 3% |  | 2% | 10% |  | 5% | 30% |  | 1% | 2% |  | 1% | 6% |  | 1% | 4% |  | 0% | 5% |  | 3% | 5% |  | 1% | 2% |  | 10% | 20% |  | 2% | 25% |  | 1% | 35% |  | 2% | 4% |  | 3% | 7%
L.5 | Structural Design |  | 2% | 7% |  | 3% | 6% |  | 7.5% | 10% |  | 5% | 30% |  | 2% | 6% |  | 1% | 3% |  | 2% | 20% |  | 5% | 30% |  | 2% | 4% |  | 1% | 6% |  | 1% | 4% |  | 5% | 10% |  | 3% | 5% |  | 2% | 5% |  | 10% | 30% |  | 2% | 25% |  | 1% | 35% |  | 2% | 5% |  | 2% | 5%
L.6 | Mechanical Design |  | 2% | 7% |  | 3% | 6% |  | 7.5% | 10% |  | 5% | 30% |  | 2% | 8% |  | 1% | 3% |  | 2% | 20% |  | 5% | 30% |  | 2% | 4% |  | 1% | 6% |  | 1% | 4% |  | 5% | 10% |  | 3% | 5% |  | 2% | 5% |  | 5% | 15% |  | 2% | 25% |  | 1% | 35% |  | 2% | 5% |  | 3% | 7%
L.7 | Electrical Design |  | 2% | 7% |  | 4% | 8% |  | 7.5% | 10% |  | 5% | 30% |  | 1% | 5% |  | 1% | 3% |  | 2% | 15% |  | 5% | 30% |  | 2% | 4% |  | 1% | 6% |  | 1% | 4% |  | 5% | 10% |  | 3% | 5% |  | 2% | 5% |  | 10% | 40% |  | 2% | 25% |  | 1% | 35% |  | 2% | 5% |  | 4% | 9%
L.8 | Constructability Analysis |  | 3% | 8% |  | 5% | 10% |  | 5% | 6% |  | 5% | 30% |  | 2% | 10% |  | 1% | 3% |  | 3% | 25% |  | 5% | 30% |  | 2% | 4% |  | 1% | 6% |  | 3% | 12% |  | 5% | 15% |  | 3% | 5% |  | 2% | 5% |  | 10% | 30% |  | 3% | 20% |  | 1% | 35% |  | 2% | 4% |  | 3% | 6%
L.9 | Process Design |  | 2% | 10% |  | 5% | 15% |  | 10% | 10% |  | 5% | 25% |  | 3% | 15% |  | 5% | 25% |  | 5% | 30% |  | 5% | 30% |  | 3% | 6% |  | 1% | 10% |  | 3% | 14% |  | 5% | 20% |  | 3% | 5% |  | 2% | 5% |  | 5% | 20% |  | 3% | 20% |  | 1% | 35% |  | 2% | 10% |  | 2% | 7%
L.10 | Specifications |  | 2% | 8% |  | 2% | 7% |  | 7.5% | 10% |  | 5% | 25% |  | 1% | 5% |  | 1% | 3% |  | 1% | 8% |  | 5% | 30% |  | 2% | 4% |  | 1% | 6% |  | 1% | 5% |  | 0% | 10% |  | 3% | 5% |  | 2% | 5% |  | 10% | 30% |  | 2% | 25% |  | 1% | 35% |  | 2% | 5% |  | 3% | 8%
L.11 | Specialty Items List |  | 1% | 6% |  | 1% | 3% |  | 5% | 5% |  | 5% | 25% |  | 0% | 2% |  | 1% | 3% |  | 3% | 10% |  | 5% | 30% |  | 1% | 2% |  | 1% | 6% |  | 1% | 4% |  | 2% | 10% |  | 3% | 5% |  | 2% | 5% |  | 10% | 20% |  | 2% | 25% |  | 1% | 35% |  | 2% | 3% |  | 3% | 11%
L.12 | Instrument Index |  | 2% | 7% |  | 5% | 10% |  | 7.5% | 10% |  | 5% | 25% |  | 0% | 3% |  | 1% | 3% |  | 3% | 8% |  | 5% | 30% |  | 0% | 1% |  | 1% | 5% |  | 1% | 8% |  | 1% | 5% |  | 3% | 5% |  | 2% | 5% |  | 10% | 20% |  | 2% | 15% |  | 1% | 35% |  | 1% | 3% |  | 4% | 8%
L.13 | Control Philosophy & systems |  | 2% | 7% |  | 3% | 8% |  | 7.5% | 10% |  | 5% | 25% |  | 1% | 5% |  | 1% | 3% |  | 1% | 8% |  | 5% | 30% |  | 3% | 6% |  | 1% | 5% |  | 1% | 10% |  | 0% | 10% |  | 3% | 5% |  | 2% | 5% |  | 10% | 30% |  | 2% | 15% |  | 1% | 35% |  | 1% | 4% |  | 5% | 11%
L.14 | Logic Diagrams |  | 2% | 7% |  | 3% | 8% |  | 7.5% | 10% |  | 5% | 25% |  | 0% | 2% |  | 1% | 3% |  | 1% | 8% |  | 5% | 30% |  | 1% | 2% |  | 1% | 5% |  | 1% | 8% |  | 0% | 5% |  | 3% | 5% |  | 2% | 5% |  | 10% | 30% |  | 2% | 15% |  | 1% | 35% |  | 1% | 3% |  | 3% | 8%
L.15 | IM (information management) |  | 2% | 7% |  | 2% | 5% |  | 7.5% | 10% |  | 5% | 25% |  | 1% | 3% |  | 1% | 3% |  | 3% | 15% |  | 5% | 30% |  | 1% | 2% |  | 1% | 5% |  | 1% | 10% |  | 0% | 1% |  | 3% | 5% |  | 2% | 5% |  | 5% | 25% |  | 2% | 15% |  | 1% | 35% |  | 1% | 3% |  | 3% | 5%
L.16 | Control of Access |  | 1% | 6% |  | 1% | 5% |  | 5% | 10% |  | 5% | 25% |  | 0% | 1% |  | 1% | 3% |  | 2% | 10% |  | 5% | 30% |  | 1% | 2% |  | 1% | 4% |  | 1% | 5% |  | 0% | 5% |  | 3% | 5% |  | 2% | 5% |  | 2% | 10% |  | 2% | 10% |  | 1% | 35% |  | 0% | 2% |  | 3% | 6%
L.17 | Safety & Hazards |  | 1% | 6% |  | 4% | 10% |  | 10% | 10% |  | 5% | 25% |  | 1% | 2% |  | 1% | 3% |  | 2% | 10% |  | 5% | 30% |  | 2% | 4% |  | 1% | 6% |  | 1% | 10% |  | 0% | 5% |  | 3% | 5% |  | 2% | 5% |  | 10% | 30% |  | 2% | 15% |  | 1% | 35% |  | 1% | 3% |  | 2% | 6%
L.18 | Operations/Maintenance |  | 1% | 6% |  | 2% | 5% |  | 5% | 10% |  | 5% | 25% |  | 2% | 6% |  | 1% | 3% |  | 2% | 8% |  | 5% | 30% |  | 2% | 4% |  | 1% | 6% |  | 1% | 7% |  | 0% | 5% |  | 3% | 5% |  | 2% | 5% |  | 10% | 40% |  | 3% | 20% |  | 1% | 35% |  | 2% | 8% |  | 2% | 9%
L.19 | Ventilation Engineering |  | 2% | 8% |  | 2% | 5% |  | 7.5% | 8% |  | 5% | 25% |  | 1% | 3% |  | 1% | 3% |  | 2% | 10% |  | 5% | 30% |  | 1% | 2% |  | 2% | 20% |  | 1% | 8% |  | 5% | 10% |  | 3% | 5% |  | 2% | 5% |  | 10% | 20% |  | 2% | 15% |  | 1% | 35% |  | 2% | 8% |  | 4% | 9%
L.20 | Rock Engineering |  | 2% | 8% |  | 4% | 10% |  | 7.5% | 8% |  | 5% | 25% |  | 3% | 8% |  | 1% | 3% |  | 2% | 10% |  | 5% | 30% |  | 0% | 1% |  | 2% | 20% |  | 3% | 12% |  | 5% | 10% |  | 3% | 5% |  | 2% | 5% |  | 15% | 40% |  | 3% | 20% |  | 1% | 35% |  | 2% | 6% |  | 2% | 5%
L.21 | Water balances |  | 2% | 8% |  | 2% | 7% |  | 7.5% | 8% |  | 5% | 25% |  | 2% | 6% |  | 5% | 15% |  | 2% | 10% |  | 5% | 30% |  | 2% | 4% |  | 1% | 6% |  | 1% | 10% |  | 0% | 5% |  | 3% | 5% |  | 2% | 5% |  | 10% | 30% |  | 3% | 20% |  | 1% | 35% |  | 2% | 6% |  | 2% | 7%
L.22 | Energy efficiency / carbon footprint |  | 1% | 6% |  | 1% | 5% |  | 7.5% | 8% |  | 5% | 25% |  | 0% | 2% |  | 5% | 15% |  | 1% | 5% |  | 5% | 30% |  | 1% | 2% |  | 1% | 5% |  | 1% | 5% |  | 0% | 1% |  | 3% | 5% |  | 1% | 2% |  | 15% | 40% |  | 2% | 10% |  | 1% | 35% |  | 2% | 5% |  | 3% | 6%
L.23 | Tailings handling and storage |  | 2% | 8% |  | 3% | 10% |  | 7.5% | 8% |  | 5% | 25% |  | 3% | 9% |  | 5% | 15% |  | 2% | 10% |  | 5% | 30% |  | 2% | 4% |  | 1% | 15% |  | 1% | 6% |  | 5% | 15% |  | 3% | 5% |  | 2% | 8% |  | 10% | 30% |  | 2% | 10% |  | 1% | 35% |  | 2% | 5% |  | 4% | 10%
L.24 | Stormwater handling / surface hydrology |  | 2% | 8% |  | 3% | 10% |  | 7.5% | 8% |  | 5% | 25% |  | 2% | 6% |  | 5% | 15% |  | 1% | 5% |  | 5% | 30% |  | 1% | 2% |  | 1% | 6% |  | 1% | 5% |  | 0% | 10% |  | 3% | 5% |  | 2% | 5% |  | 10% | 25% |  | 2% | 10% |  | 1% | 35% |  | 2% | 4% |  | 3% | 7%
L.25 | Internal technical audits |  | 1% | 6% |  | 1% | 3% |  | 5% | 8% |  | 5% | 20% |  | 0% | 2% |  | 1% | 3% |  | 1% | 3% |  | 5% | 30% |  | 3% | 6% |  | 0% | 4% |  | 1% | 6% |  | 0% | 1% |  | 3% | 5% |  | 2% | 5% |  | 5% | 15% |  | 2% | 10% |  | 1% | 35% |  | 2% | 2% |  | 1% | 3%
L.26 | External technical audits |  | 1% | 6% |  | 1% | 3% |  | 5% | 8% |  | 5% | 20% |  | 0% | 2% |  | 1% | 3% |  | 1% | 3% |  | 5% | 30% |  | 1% | 2% |  | 0% | 4% |  | 1% | 6% |  | 0% | 1% |  | 3% | 5% |  | 1% | 2% |  | 5% | 20% |  | 2% | 15% |  | 1% | 35% |  | 2% | 2% |  | 3% | 7%
Total | CATEGORY L (Maximum = )
M | VALUE IMPROVING PRACTICES
M.1 | Process Simplification |  | 2% | 7% |  | 2% | 5% |  | 5% | 5% |  | 5% | 25% |  | 0% | 3% |  | 1% | 3% |  | 2% | 20% |  | 5% | 20% |  | 1% | 2% |  | 0% | 2% |  | 1% | 8% |  | 0% | 5% |  | 2% | 5% |  | 1% | 2% |  | 10% | 40% |  | 3% | 25% |  | 0% | 0% |  | 2% | 4% |  | 3% | 6%
M.2 | Design & Material Alternatives Considered/Rejected |  | 2% | 7% |  | 1% | 4% |  | 5% | 5% |  | 5% | 20% |  | 0% | 3% |  | 1% | 3% |  | 2% | 10% |  | 5% | 15% |  | 2% | 4% |  | 0% | 2% |  | 1% | 8% |  | 1% | 5% |  | 2% | 4% |  | 1% | 2% |  | 15% | 30% |  | 3% | 25% |  | 1% | 25% |  | 2% | 4% |  | 2% | 5%
M.3 | Technology trends |  | 2% | 7% |  | 2% | 5% |  | 7.5% | 7.5% |  | 5% | 20% |  | 1% | 3% |  | 1% | 3% |  | 2% | 8% |  | 5% | 15% |  | 2% | 4% |  | 0% | 2% |  | 1% | 7% |  | 0% | 5% |  | 1% | 3% |  | 1% | 2% |  | 10% | 30% |  | 3% | 20% |  | 2% | 25% |  | 2% | 3% |  | 4% | 8%
M.4 | Design to capacity |  | 2% | 7% |  | 2% | 8% |  | 10% | 10% |  | 5% | 25% |  | 1% | 4% |  | 1% | 3% |  | 2% | 10% |  | 5% | 20% |  | 2% | 4% |  | 0% | 2% |  | 1% | 8% |  | 1% | 5% |  | 1% | 2% |  | 1% | 2% |  | 5% | 15% |  | 2% | 15% |  | 2% | 25% |  | 2% | 4% |  | 2% | 4%
M.5 | Classes of facillity quality |  | 2% | 7% |  | 1% | 3% |  | 5% | 5% |  | 5% | 25% |  | 0% | 2% |  | 1% | 3% |  | 1% | 10% |  | 5% | 15% |  | 1% | 2% |  | 0% | 4% |  | 1% | 7% |  | 5% | 10% |  | 1% | 2% |  | 1% | 2% |  | 5% | 20% |  | 4% | 20% |  | 0% | 0% |  | 0% | 2% |  | 0% | 3%
M.6 | Energy optimisation |  | 2% | 6% |  | 1% | 3% |  | 5% | 5% |  | 5% | 20% |  | 0% | 2% |  | 1% | 3% |  | 2% | 8% |  | 5% | 15% |  | 2% | 4% |  | 0% | 2% |  | 1% | 9% |  | 5% | 15% |  | 1% | 3% |  | 1% | 2% |  | 10% | 20% |  | 4% | 20% |  | 0% | 0% |  | 0% | 2% |  | 2% | 5%
M.7 | Waste minimisation |  | 1% | 6% |  | 2% | 4% |  | 7.5% | 7.5% |  | 5% | 20% |  | 1% | 5% |  | 1% | 3% |  | 2% | 10% |  | 5% | 25% |  | 2% | 4% |  | 0% | 2% |  | 1% | 9% |  | 0% | 5% |  | 1% | 2% |  | 1% | 2% |  | 10% | 20% |  | 3% | 20% |  | 0% | 0% |  | 0% | 4% |  | 2% | 7%
M.8 | 3D / 4D design |  | 2% | 6% |  | 2% | 8% |  | 10% | 10% |  | 5% | 25% |  | 1% | 3% |  | 1% | 3% |  | 2% | 20% |  | 5% | 10% |  | 1% | 2% |  | 0% | 2% |  | 1% | 9% |  | 0% | 10% |  | 3% | 6% |  | 1% | 2% |  | 10% | 30% |  | 2% | 15% |  | 0% | 0% |  | 0% | 3% |  | 1% | 5%
M.9 | Cleaner Production |  | 2% | 7% |  | 1% | 3% |  | 5% | 5% |  | 5% | 25% |  | 0% | 2% |  | 1% | 3% |  | 1% | 10% |  | 5% | 15% |  | 2% | 4% |  | 0% | 2% |  | 1% | 8% |  | 5% | 10% |  | 2% | 4% |  | 1% | 2% |  | 5% | 10% |  | 2% | 15% |  | 0% | 0% |  | 0% | 2% |  | 3% | 8%
M.10 | Innovation and knowledge management planning |  | 2% | 6% |  | 1% | 4% |  | 7.5% | 7.5% |  | 5% | 20% |  | 0% | 1% |  | 1% | 3% |  | 2% | 10% |  | 5% | 10% |  | 1% | 2% |  | 0% | 2% |  | 1% | 10% |  | 0% | 5% |  | 2% | 5% |  | 1% | 2% |  | 10% | 30% |  | 4% | 15% |  | 0% | 0% |  | 2% | 4% |  | 2% | 4%
M.11 | Six Sigma |  | 1% | 6% |  | 1% | 4% |  | 5% | 5% |  | 5% | 25% |  | 0% | 1% |  | 1% | 3% |  | 2% | 10% |  | 2% | 5% |  | 0% | 1% |  | 0% | 2% |  | 2% | 11% |  | 0% | 10% |  | 2% | 5% |  | 1% | 2% |  | 15% | 20% |  | 2% | 15% |  | 0% | 0% |  | 2% | 4% |  | 2% | 5%
M.12 | Lean Manufacturing |  | 1% | 6% |  | 2% | 5% |  | 5% | 5% |  | 5% | 20% |  | 0% | 1% |  | 1% | 3% |  | 3% | 8% |  | 2% | 5% |  | 0% | 1% |  | 0% | 2% |  | 1% | 8% |  | 0% | 5% |  | 2% | 5% |  | 1% | 2% |  | 10% | 30% |  | 2% | 15% |  | 0% | 0% |  | 1% | 3% |  | 1% | 5%
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
N | PROCUREMENT STRATEGY
N.1 | Identify Long Lead/Critical Equipment and Materials |  | 3% | 8% |  | 1% | 7% |  | 7.5% | 7.5% |  | 5% | 35% |  | 2% | 8% |  | 5% | 15% |  | 1% | 5% |  | 5% | 10% |  | 3% | 6% |  | 1% | 5% |  | 2% | 10% |  | 2% | 15% |  | 1% | 2% |  | 1% | 5% |  | 5% | 20% |  | 2% | 20% |  | 5% | 50% |  | 2% | 5% |  | 2% | 6%
N.2 | Procurement Procedures and Plans |  | 2% | 8% |  | 1% | 5% |  | 10% | 10% |  | 5% | 25% |  | 1% | 6% |  | 2% | 10% |  | 2% | 5% |  | 10% | 15% |  | 2% | 4% |  | 1% | 5% |  | 1% | 8% |  | 0% | 10% |  | 1% | 4% |  | 1% | 5% |  | 5% | 10% |  | 2% | 25% |  | 1% | 10% |  | 2% | 4% |  | 1% | 3%
N.3 | Procurement Responsibility Matrix |  | 2% | 7% |  | 1% | 5% |  | 10% | 10% |  | 5% | 30% |  | 0% | 2% |  | 1% | 3% |  | 1% | 4% |  | 10% | 10% |  | 1% | 2% |  | 0% | 3% |  | 1% | 7% |  | 0% | 10% |  | 1% | 3% |  | 1% | 5% |  | 2% | 10% |  | 3% | 20% |  | 1% | 10% |  | 2% | 3% |  | 0% | 1%
N.4 | Draft contracts & proforma bidders pack |  | 3% | 8% |  | 2% | 7% |  | 10% | 10% |  | 5% | 25% |  | 1% | 4% |  | 1% | 3% |  | 1% | 7% |  | 10% | 15% |  | 2% | 4% |  | 0% | 3% |  | 1% | 7% |  | 2% | 15% |  | 3% | 7% |  | 1% | 5% |  | 1% | 5% |  | 2% | 15% |  | 1% | 10% |  | 2% | 4% |  | 2% | 5%
N.5 | Contracting strategy |  | 3% | 9% |  | 2% | 7% |  | 7.5% | 7.5% |  | 5% | 30% |  | 2% | 8% |  | 2% | 5% |  | 1% | 7% |  | 10% | 30% |  | 2% | 4% |  | 1% | 5% |  | 1% | 8% |  | 0% | 15% |  | 3% | 7% |  | 1% | 5% |  | 3% | 10% |  | 2% | 20% |  | 5% | 25% |  | 2% | 5% |  | 4% | 10%
N.6 | Procurement operation plan (POP) |  | 2% | 8% |  | 2% | 7% |  | 10% | 10% |  | 5% | 25% |  | 1% | 4% |  | 2% | 10% |  | 1% | 8% |  | 10% | 20% |  | 2% | 4% |  | 1% | 5% |  | 1% | 8% |  | 0% | 10% |  | 2% | 5% |  | 2% | 5% |  | 2% | 15% |  | 2% | 20% |  | 1% | 10% |  | 2% | 5% |  | 2% | 8%
Total | CATEGORY N (Maximum = )
O | DELIVERABLES
O.1 | CADD/Model Requirements |  | 1% | 8% |  | 1% | 3% |  | 7.5% | 7.5% |  | 5% | 20% |  | 0% | 2% |  | 1% | 3% |  | 1% | 5% |  | 5% | 15% |  | 1% | 2% |  | 0% | 4% |  | 1% | 6% |  | 5% | 10% |  | 2% | 5% |  | 1% | 3% |  | 20% | 30% |  | 2% | 15% |  | 0% | 15% |  | 2% | 4% |  | 2% | 5%
O.2 | Deliverables Defined |  | 2% | 8% |  | 3% | 8% |  | 10% | 10% |  | 5% | 30% |  | 0% | 1% |  | 1% | 3% |  | 1% | 10% |  | 5% | 20% |  | 2% | 4% |  | 0% | 6% |  | 1% | 7% |  | 0% | 25% |  | 3% | 7% |  | 1% | 3% |  | 10% | 20% |  | 3% | 25% |  | 1% | 25% |  | 2% | 4% |  | 3% | 6%
O.3 | Distribution Matrix |  | 1% | 6% |  | 1% | 2% |  | 7.5% | 7.5% |  | 5% | 20% |  | 0% | 0% |  | 1% | 3% |  | 1% | 8% |  | 5% | 15% |  | 1% | 2% |  | 0% | 4% |  | 1% | 6% |  | 0% | 5% |  | 2% | 4% |  | 1% | 3% |  | 10% | 20% |  | 2% | 15% |  | 0% | 5% |  | 1% | 3% |  | 2% | 4%
O.4 | Documentation/Deliverables |  | 2% | 7% |  | 3% | 8% |  | 7.5% | 7.5% |  | 5% | 25% |  | 0% | 1% |  | 2% | 10% |  | 1% | 5% |  | 5% | 15% |  | 1% | 2% |  | 0% | 4% |  | 1% | 5% |  | 0% | 2% |  | 3% | 6% |  | 1% | 3% |  | 5% | 15% |  | 2% | 20% |  | 1% | 15% |  | 1% | 3% |  | 4% | 7%
Total | CATEGORY O (Maximum = )
P | PROJECT CONTROLS
P.1 | Project Quality Assurance and Control |  | 2% | 8% |  | 1% | 5% |  | 10% | 10% |  | 5% | 25% |  | 0% | 2% |  | 5% | 20% |  | 2% | 15% |  | 5% | 20% |  | 2% | 4% |  | 1% | 5% |  | 1% | 5% |  | 5% | 15% |  | 3% | 7% |  | 0% | 3% |  | 5% | 10% |  | 5% | 20% |  | 7% | 35% |  | 2% | 4% |  | 1% | 3%
P.2 | Project Cost Control |  | 2% | 9% |  | 1% | 5% |  | 10% | 10% |  | 5% | 25% |  | 1% | 3% |  | 5% | 35% |  | 2% | 10% |  | 5% | 20% |  | 5% | 10% |  | 0% | 4% |  | 1% | 7% |  | 0% | 30% |  | 1% | 3% |  | 0% | 3% |  | 10% | 25% |  | 3% | 20% |  | 7% | 35% |  | 2% | 4% |  | 3% | 6%
P.3 | Project Schedule Control |  | 2% | 9% |  | 2% | 6% |  | 10% | 10% |  | 5% | 25% |  | 1% | 5% |  | 5% | 35% |  | 2% | 15% |  | 5% | 20% |  | 5% | 10% |  | 0% | 4% |  | 1% | 7% |  | 0% | 25% |  | 1% | 4% |  | 0% | 3% |  | 10% | 30% |  | 3% | 20% |  | 7% | 35% |  | 2% | 6% |  | 4% | 6%
P.4 | Risk Management |  | 3% | 8% |  | 3% | 8% |  | 5% | 15% |  | 5% | 25% |  | 2% | 5% |  | 2% | 15% |  | 2% | 10% |  | 5% | 20% |  | 2% | 4% |  | 1% | 4% |  | 1% | 8% |  | 5% | 15% |  | 3% | 6% |  | 0% | 3% |  | 5% | 15% |  | 2% | 20% |  | 7% | 35% |  | 2% | 4% |  | 4% | 7%
P.5 | Safety, Health, Hygiene and security Management |  | 2% | 6% |  | 3% | 8% |  | 10% | 10% |  | 5% | 25% |  | 1% | 5% |  | 5% | 35% |  | 1% | 5% |  | 5% | 20% |  | 6% | 12% |  | 1% | 5% |  | 1% | 5% |  | 0% | 10% |  | 2% | 5% |  | 0% | 3% |  | 5% | 10% |  | 2% | 20% |  | 5% | 25% |  | 2% | 6% |  | 2% | 8%
P.6 | Environmental Management |  | 3% | 8% |  | 2% | 8% |  | 5% | 5% |  | 5% | 25% |  | 1% | 5% |  | 2% | 15% |  | 1% | 5% |  | 5% | 20% |  | 3% | 6% |  | 1% | 4% |  | 1% | 5% |  | 0% | 10% |  | 1% | 2% |  | 0% | 3% |  | 5% | 20% |  | 2% | 20% |  | 5% | 35% |  | 2% | 4% |  | 4% | 9%
P.7 | Project Change Control |  | 3% | 10% |  | 5% | 10% |  | 7.5% | 7.5% |  | 5% | 25% |  | 2% | 6% |  | 10% | 35% |  | 2% | 15% |  | 5% | 20% |  | 3% | 6% |  | 1% | 5% |  | 1% | 5% |  | 0% | 30% |  | 1% | 3% |  | 1% | 3% |  | 10% | 40% |  | 2% | 20% |  | 7% | 35% |  | 2% | 5% |  | 5% | 8%
P.8 | Project Audits |  | 2% | 6% |  | 2% | 7% |  | 5% | 5% |  | 5% | 25% |  | 0% | 2% |  | 2% | 5% |  | 1% | 6% |  | 5% | 20% |  | 0% | 1% |  | 1% | 4% |  | 1% | 4% |  | 5% | 10% |  | 1% | 2% |  | 0% | 3% |  | 5% | 10% |  | 2% | 15% |  | 2% | 35% |  | 2% | 4% |  | 2% | 4%
P.9 | Decision register |  | 2% | 9% |  | 2% | 10% |  | 5% | 5% |  | 5% | 25% |  | 1% | 4% |  | 2% | 5% |  | 1% | 16% |  | 5% | 20% |  | 2% | 4% |  | 1% | 4% |  | 1% | 4% |  | 0% | 15% |  | 1% | 2% |  | 0% | 3% |  | 5% | 10% |  | 2% | 10% |  | 7% | 35% |  | 2% | 6% |  | 4% | 7%
Total | CATEGORY P (Maximum = )
Q | PROJECT EXECUTION PLAN
Q.1 | Engineering / Construction Plan & Approach |  | 3% | 9% |  | 2% | 10% |  | 10% | 10% |  | 5% | 25% |  | 2% | 10% |  | 2% | 5% |  | 4% | 20% |  | 5% | 20% |  | 3% | 6% |  | 1% | 6% |  | 1% | 7% |  | 5% | 15% |  | 2% | 5% |  | 0% | 3% |  | 5% | 25% |  | 4% | 25% |  | 5% | 25% |  | 2% | 6% |  | 3% | 8%
Q.2 | Project Organization |  | 2% | 6% |  | 5% | 10% |  | 7.5% | 7.5% |  | 5% | 25% |  | 1% | 5% |  | 2% | 5% |  | 2% | 20% |  | 5% | 20% |  | 4% | 8% |  | 1% | 8% |  | 1% | 9% |  | 0% | 20% |  | 4% | 9% |  | 0% | 3% |  | 5% | 10% |  | 3% | 20% |  | 5% | 25% |  | 2% | 5% |  | 2% | 4%
Q.3 | Responsibility matrix RACI |  | 2% | 7% |  | 2% | 8% |  | 7.5% | 7.5% |  | 5% | 25% |  | 0% | 2% |  | 2% | 5% |  | 2% | 15% |  | 5% | 20% |  | 2% | 4% |  | 1% | 6% |  | 1% | 9% |  | 0% | 10% |  | 3% | 5% |  | 0% | 3% |  | 5% | 10% |  | 2% | 20% |  | 5% | 20% |  | 2% | 8% |  | 2% | 3%
Q.4 | Document Management Plan |  | 1% | 6% |  | 1% | 5% |  | 5% | 5% |  | 5% | 25% |  | 0% | 1% |  | 2% | 5% |  | 2% | 8% |  | 5% | 20% |  | 1% | 2% |  | 1% | 4% |  | 1% | 4% |  | 0% | 5% |  | 2% | 4% |  | 0% | 3% |  | 1% | 5% |  | 2% | 20% |  | 1% | 15% |  | 2% | 5% |  | 1% | 2%
Q.5 | Communication management plan |  | 3% | 7% |  | 2% | 7% |  | 5% | 5% |  | 5% | 25% |  | 0% | 1% |  | 2% | 5% |  | 2% | 6% |  | 5% | 20% |  | 2% | 4% |  | 1% | 4% |  | 1% | 5% |  | 0% | 5% |  | 2% | 4% |  | 0% | 3% |  | 5% | 10% |  | 2% | 20% |  | 10% | 35% |  | 2% | 5% |  | 1% | 2%
Q.6 | Project Delivery Method |  | 1% | 8% |  | 2% | 8% |  | 5% | 5% |  | 5% | 30% |  | 2% | 8% |  | 2% | 5% |  | 2% | 8% |  | 5% | 20% |  | 3% | 6% |  | 1% | 6% |  | 1% | 9% |  | 0% | 10% |  | 3% | 7% |  | 0% | 3% |  | 5% | 20% |  | 2% | 25% |  | 5% | 25% |  | 2% | 6% |  | 3% | 5%
Q.7 | Design / Construction Plan and Approach |  | 2% | 8% |  | 2% | 8% |  | 10% | 10% |  | 5% | 25% |  | 2% | 6% |  | 2% | 5% |  | 2% | 30% |  | 5% | 20% |  | 3% | 6% |  | 1% | 6% |  | 1% | 9% |  | 5% | 15% |  | 3% | 7% |  | 0% | 3% |  | 5% | 10% |  | 2% | 20% |  | 5% | 25% |  | 2% | 5% |  | 2% | 4%
Q.8 | Safety Procedures |  | 1% | 7% |  | 2% | 8% |  | 10% | 10% |  | 5% | 25% |  | 1% | 4% |  | 2% | 5% |  | 2% | 8% |  | 5% | 20% |  | 3% | 6% |  | 1% | 6% |  | 1% | 5% |  | 0% | 10% |  | 2% | 5% |  | 0% | 3% |  | 5% | 20% |  | 3% | 15% |  | 1% | 5% |  | 2% | 4% |  | 4% | 8%
Q.9 | Intercompany Agreements |  | 2% | 8% |  | 1% | 8% |  | 5% | 5% |  | 5% | 20% |  | 0% | 2% |  | 2% | 5% |  | 1% | 5% |  | 5% | 20% |  | 2% | 4% |  | 1% | 4% |  | 1% | 4% |  | 0% | 5% |  | 1% | 2% |  | 0% | 3% |  | 2% | 10% |  | 2% | 10% |  | 2% | 25% |  | 2% | 4% |  | 2% | 5%
Q.10 | Deliverables for Design and Construction |  | 2% | 8% |  | 2% | 8% |  | 7.5% | 7.5% |  | 5% | 25% |  | 2% | 7% |  | 10% | 25% |  | 2% | 20% |  | 5% | 20% |  | 3% | 6% |  | 1% | 3% |  | 1% | 7% |  | 5% | 25% |  | 2% | 4% |  | 0% | 3% |  | 5% | 20% |  | 3% | 25% |  | 1% | 25% |  | 2% | 4% |  | 3% | 9%
Q.11 | Labour and Skilled resources plan |  | 2% | 9% |  | 2% | 8% |  | 5% | 5% |  | 5% | 25% |  | 2% | 12% |  | 5% | 10% |  | 2% | 10% |  | 5% | 20% |  | 3% | 6% |  | 1% | 3% |  | 1% | 10% |  | 5% | 15% |  | 2% | 4% |  | 0% | 3% |  | 5% | 10% |  | 3% | 20% |  | 10% | 50% |  | 2% | 4% |  | 3% | 7%
Total | CATEGORY Q (Maximum = )
R | HANDOVER & OPERATIONAL READINESS
R.1 | Commissioning plan |  | 2% | 8% |  | 5% | 10% |  | 10% | 10% |  | 5% | 25% |  | 2% | 4% |  | 10% | 25% |  | 2% | 15% |  | 5% | 20% |  | 4% | 8% |  | 1% | 4% |  | 1% | 9% |  | 5% | 15% |  | 2% | 5% |  | 0% | 3% |  | 5% | 15% |  | 3% | 20% |  | 5% | 25% |  | 2% | 5% |  | 1% | 4%
R.2 | Startup Requirements & plans |  | 2% | 7% |  | 2% | 8% |  | 7.5% | 7.5% |  | 5% | 25% |  | 1% | 3% |  | 5% | 15% |  | 2% | 20% |  | 5% | 20% |  | 3% | 6% |  | 1% | 4% |  | 2% | 10% |  | 5% | 25% |  | 3% | 4% |  | 0% | 3% |  | 2% | 10% |  | 3% | 20% |  | 5% | 25% |  | 2% | 4% |  | 1% | 3%
R.3 | Training Requirements |  | 2% | 7% |  | 1% | 5% |  | 7.5% | 7.5% |  | 5% | 25% |  | 1% | 2% |  | 5% | 15% |  | 2% | 15% |  | 10% | 30% |  | 1% | 2% |  | 1% | 4% |  | 2% | 9% |  | 0% | 10% |  | 1% | 2% |  | 0% | 3% |  | 5% | 10% |  | 3% | 20% |  | 5% | 25% |  | 0% | 4% |  | 2% | 5%
R.4 | Substantial Completion Requirements |  | 2% | 7% |  | 1% | 5% |  | 7.5% | 7.5% |  | 5% | 25% |  | 1% | 2% |  | 5% | 15% |  | 2% | 15% |  | 5% | 20% |  | 1% | 2% |  | 1% | 4% |  | 2% | 9% |  | 5% | 20% |  | 2% | 4% |  | 0% | 3% |  | 5% | 15% |  | 3% | 20% |  | 5% | 25% |  | 0% | 5% |  | 3% | 5%
R.5 | Deliverables for Project Commissioning / Closeout |  | 2% | 8% |  | 2% | 6% |  | 7.5% | 7.5% |  | 5% | 25% |  | 1% | 2% |  | 2% | 10% |  | 3% | 25% |  | 5% | 20% |  | 2% | 4% |  | 1% | 4% |  | 1% | 6% |  | 0% | 15% |  | 2% | 4% |  | 0% | 3% |  | 2% | 10% |  | 3% | 20% |  | 5% | 25% |  | 0% | 4% |  | 3% | 7%
R.6 | Long term supply chain contracts |  | 3% | 8% |  | 2% | 6% |  | 5% | 5% |  | 5% | 25% |  | 1% | 2% |  | 2% | 5% |  | 1% | 10% |  | 10% | 35% |  | 3% | 6% |  | 1% | 4% |  | 2% | 9% |  | 0% | 10% |  | 1% | 2% |  | 0% | 3% |  | 5% | 10% |  | 3% | 20% |  | 5% | 25% |  | 0% | 5% |  | 2% | 5%
R.7 | Resourcing & staffing for operation |  | 4% | 8% |  | 2% | 6% |  | 5% | 5% |  | 5% | 25% |  | 2% | 4% |  | 5% | 15% |  | 2% | 10% |  | 10% | 35% |  | 2% | 4% |  | 1% | 5% |  | 2% | 10% |  | 5% | 10% |  | 1% | 2% |  | 0% | 3% |  | 1% | 5% |  | 3% | 20% |  | 5% | 25% |  | 0% | 4% |  | 3% | 6%
R.8 | Maintenance schedules |  | 2% | 7% |  | 1% | 5% |  | 5% | 5% |  | 5% | 25% |  | 1% | 2% |  | 2% | 5% |  | 1% | 7% |  | 5% | 35% |  | 1% | 2% |  | 1% | 5% |  | 1% | 7% |  | 0% | 10% |  | 1% | 2% |  | 0% | 3% |  | 5% | 15% |  | 2% | 10% |  | 5% | 25% |  | 0% | 4% |  | 3% | 4%
R.9 | Critical spares |  | 4% | 8% |  | 1% | 5% |  | 7.5% | 7.5% |  | 5% | 25% |  | 1% | 3% |  | 2% | 5% |  | 1% | 7% |  | 5% | 25% |  | 1% | 2% |  | 1% | 4% |  | 1% | 6% |  | 5% | 15% |  | 1% | 2% |  | 2% | 3% |  | 2% | 10% |  | 2% | 15% |  | 5% | 25% |  | 1% | 5% |  | 2% | 4%
R.10 | Startup consumables |  | 3% | 7% |  | 1% | 5% |  | 5% | 5% |  | 5% | 25% |  | 0% | 1% |  | 2% | 5% |  | 1% | 8% |  | 5% | 20% |  | 2% | 4% |  | 1% | 4% |  | 1% | 8% |  | 5% | 10% |  | 1% | 2% |  | 1% | 3% |  | 5% | 15% |  | 2% | 10% |  | 5% | 25% |  | 1% | 3% |  | 3% | 5%
R.11 | Operational systems and procedures to support each department |  | 2% | 8% |  | 1% | 5% |  | 7.5% | 7.5% |  | 5% | 25% |  | 1% | 3% |  | 1% | 3% |  | 1% | 18% |  | 5% | 30% |  | 2% | 4% |  | 1% | 4% |  | 1% | 8% |  | 0% | 5% |  | 1% | 2% |  | 0% | 3% |  | 10% | 20% |  | 2% | 10% |  | 5% | 25% |  | 1% | 4% |  | 1% | 3%
R.12 | Environmental Management Plan for Operations (EMP) |  | 2% | 7% |  | 1% | 5% |  | 7.5% | 7.5% |  | 5% | 25% |  | 1% | 3% |  | 5% | 15% |  | 1% | 15% |  | 5% | 30% |  | 3% | 6% |  | 1% | 4% |  | 1% | 7% |  | 5% | 15% |  | 1% | 2% |  | 0% | 3% |  | 10% | 30% |  | 2% | 25% |  | 5% | 25% |  | 2% | 4% |  | 2% | 5%
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
|  |  | 1% | 10% |  | 0% | 20% |  | 5% | 20% |  | 5% | 50% |  | 0% | 50% |  | 1% | 35% |  | 1% | 35% |  | 2% | 50% |  | 0% | 12% |  | 0% | 50% |  | 1% | 30% |  | 0% | 35% |  | 1% | 15% |  | 0% | 15% |  | 1% | 60% |  | 1% | 50% |  | 0% | 50% |  | 0% | 15% |  | 0% | 12%
| Normalising Factor |  |  | 10 |  |  | 5 |  |  | 5 |  |  | 2 |  |  | 2 |  |  | 2.8571 |  |  | 2.8571 |  |  | 2 |  |  | 8.3333 |  |  | 2 |  |  | 3.3333 |  |  | 2.8571 |  |  | 6.6667 |  |  | 6.6667 |  |  | 1.6667 |  |  | 2 |  |  | 2 |  |  | 6.6667 |  |  | 8.3333
Note on D178: Level 0: Element not applicable
Note on E178: Level 1: Element completely defined
Note on F178: Level 5: Element has poor or incomplete definition
Note on G178: Level 0: Element not applicable
Note on H178: Level 1: Element completely defined
Note on I178: Level 5: Element has poor or incomplete definition
Note on V178: Level 0: Element not applicable
Note on W178: Level 1: Element completely defined
Note on X178: Level 5: Element has poor or incomplete definition
Note on Y178: Level 0: Element not applicable
Note on Z178: Level 1: Element completely defined
Note on AA178: Level 5: Element has poor or incomplete definition
Note on AB178: Level 0: Element not applicable
Note on AC178: Level 1: Element completely defined
Note on AD178: Level 5: Element has poor or incomplete definition
Note on AE178: Level 0: Element not applicable
Note on AF178: Level 1: Element completely defined
Note on AG178: Level 5: Element has poor or incomplete definition
Note on AH178: Level 0: Element not applicable
Note on AI178: Level 1: Element completely defined
Note on AJ178: Level 5: Element has poor or incomplete definition
Note on AK178: Level 0: Element not applicable
Note on AL178: Level 1: Element completely defined
Note on AM178: Level 5: Element has poor or incomplete definition
Note on AN178: Level 0: Element not applicable
Note on AO178: Level 1: Element completely defined
Note on AP178: Level 5: Element has poor or incomplete definition
Note on AQ178: Level 0: Element not applicable
Note on AR178: Level 1: Element completely defined
Note on AS178: Level 5: Element has poor or incomplete definition
Note on D186: Level 0: Element not applicable
Note on E186: Level 1: Element completely defined
Note on F186: Level 5: Element has poor or incomplete definition
Note on G186: Level 0: Element not applicable
Note on H186: Level 1: Element completely defined
Note on I186: Level 5: Element has poor or incomplete definition
Note on V186: Level 0: Element not applicable
Note on W186: Level 1: Element completely defined
Note on X186: Level 5: Element has poor or incomplete definition
Note on Y186: Level 0: Element not applicable
Note on Z186: Level 1: Element completely defined
Note on AA186: Level 5: Element has poor or incomplete definition
Note on AB186: Level 0: Element not applicable
Note on AC186: Level 1: Element completely defined
Note on AD186: Level 5: Element has poor or incomplete definition
Note on AE186: Level 0: Element not applicable
Note on AF186: Level 1: Element completely defined
Note on AG186: Level 5: Element has poor or incomplete definition
Note on AH186: Level 0: Element not applicable
Note on AI186: Level 1: Element completely defined
Note on AJ186: Level 5: Element has poor or incomplete definition
Note on AK186: Level 0: Element not applicable
Note on AL186: Level 1: Element completely defined
Note on AM186: Level 5: Element has poor or incomplete definition
Note on AN186: Level 0: Element not applicable
Note on AO186: Level 1: Element completely defined
Note on AP186: Level 5: Element has poor or incomplete definition
Note on AQ186: Level 0: Element not applicable
Note on AR186: Level 1: Element completely defined
Note on AS186: Level 5: Element has poor or incomplete definition
Note on D192: Level 0: Element not applicable
Note on E192: Level 1: Element completely defined
Note on F192: Level 5: Element has poor or incomplete definition
Note on G192: Level 0: Element not applicable
Note on H192: Level 1: Element completely defined
Note on I192: Level 5: Element has poor or incomplete definition
Note on V192: Level 0: Element not applicable
Note on W192: Level 1: Element completely defined
Note on X192: Level 5: Element has poor or incomplete definition
Note on Y192: Level 0: Element not applicable
Note on Z192: Level 1: Element completely defined
Note on AA192: Level 5: Element has poor or incomplete definition
Note on AB192: Level 0: Element not applicable
Note on AC192: Level 1: Element completely defined
Note on AD192: Level 5: Element has poor or incomplete definition
Note on AE192: Level 0: Element not applicable
Note on AF192: Level 1: Element completely defined
Note on AG192: Level 5: Element has poor or incomplete definition
Note on AH192: Level 0: Element not applicable
Note on AI192: Level 1: Element completely defined
Note on AJ192: Level 5: Element has poor or incomplete definition
Note on AK192: Level 0: Element not applicable
Note on AL192: Level 1: Element completely defined
Note on AM192: Level 5: Element has poor or incomplete definition
Note on AN192: Level 0: Element not applicable
Note on AO192: Level 1: Element completely defined
Note on AP192: Level 5: Element has poor or incomplete definition
Note on AQ192: Level 0: Element not applicable
Note on AR192: Level 1: Element completely defined
Note on AS192: Level 5: Element has poor or incomplete definition
Note on D203: Level 0: Element not applicable
Note on E203: Level 1: Element completely defined
Note on F203: Level 5: Element has poor or incomplete definition
Note on G203: Level 0: Element not applicable
Note on H203: Level 1: Element completely defined
Note on I203: Level 5: Element has poor or incomplete definition
Note on V203: Level 0: Element not applicable
Note on W203: Level 1: Element completely defined
Note on X203: Level 5: Element has poor or incomplete definition
Note on Y203: Level 0: Element not applicable
Note on Z203: Level 1: Element completely defined
Note on AA203: Level 5: Element has poor or incomplete definition
Note on AB203: Level 0: Element not applicable
Note on AC203: Level 1: Element completely defined
Note on AD203: Level 5: Element has poor or incomplete definition
Note on AE203: Level 0: Element not applicable
Note on AF203: Level 1: Element completely defined
Note on AG203: Level 5: Element has poor or incomplete definition
Note on AH203: Level 0: Element not applicable
Note on AI203: Level 1: Element completely defined
Note on AJ203: Level 5: Element has poor or incomplete definition
Note on AK203: Level 0: Element not applicable
Note on AL203: Level 1: Element completely defined
Note on AM203: Level 5: Element has poor or incomplete definition
Note on AN203: Level 0: Element not applicable
Note on AO203: Level 1: Element completely defined
Note on AP203: Level 5: Element has poor or incomplete definition
Note on AQ203: Level 0: Element not applicable
Note on AR203: Level 1: Element completely defined
Note on AS203: Level 5: Element has poor or incomplete definition
Note on D216: Level 0: Element not applicable
Note on E216: Level 1: Element completely defined
Note on F216: Level 5: Element has poor or incomplete definition
Note on G216: Level 0: Element not applicable
Note on H216: Level 1: Element completely defined
Note on I216: Level 5: Element has poor or incomplete definition
Note on V216: Level 0: Element not applicable
Note on W216: Level 1: Element completely defined
Note on X216: Level 5: Element has poor or incomplete definition
Note on Y216: Level 0: Element not applicable
Note on Z216: Level 1: Element completely defined
Note on AA216: Level 5: Element has poor or incomplete definition
Note on AB216: Level 0: Element not applicable
Note on AC216: Level 1: Element completely defined
Note on AD216: Level 5: Element has poor or incomplete definition
Note on AE216: Level 0: Element not applicable
Note on AF216: Level 1: Element completely defined
Note on AG216: Level 5: Element has poor or incomplete definition
Note on AH216: Level 0: Element not applicable
Note on AI216: Level 1: Element completely defined
Note on AJ216: Level 5: Element has poor or incomplete definition
Note on AK216: Level 0: Element not applicable
Note on AL216: Level 1: Element completely defined
Note on AM216: Level 5: Element has poor or incomplete definition
Note on AN216: Level 0: Element not applicable
Note on AO216: Level 1: Element completely defined
Note on AP216: Level 5: Element has poor or incomplete definition
Note on AQ216: Level 0: Element not applicable
Note on AR216: Level 1: Element completely defined
Note on AS216: Level 5: Element has poor or incomplete definition

## Verification data
Identifier | Name | PDRI Score | Greenfield? | Planned duration | Actual duration | Original cost | Actual cost | Change orders | Value of CO | Duration change | Increase?
J1 | James Marzocca | 147.002 | 0 | 29 | 28 | 13000000000 | 12400000000 | 40 | 450000000 | 0 | 0
J2 | Louw v Heerden | 188.5285 | 1 | 44 | 48 | 3340000000 | 3290000000 | 46 | 385000000 | 4 | 1
J3 | Floyd Botha | 198.6126 | 1 | 53 | 60 | 17480000000 | 19370000000 | 200 | 2200000000 | 7 | 1
J4 | Danie Oosthuisen | 203.1326 | 0 | 18 | 25 | 1660000000 | 1610000000 | 4 | 34000000 | 0 | 1
J5 | Marius Kruger | 228.0045 | 1 | 48 | 69 | 5461695342 | 5034554888 | 145 | 1057989667 | 21 | 1
J6 | Phillip Venter | 230.8922 | 1 | 22 | 22 | 958000000 | 924000000 | 48 | 101000000 | 0 | 0
J7 | Kobus Brits | 285.0886 | 1 | 24 | 26 | 5850000000 | 5850000000 | 100 | 650000000 | 0 | 1
J8 | Andy Dunn | 297.9891 | 1 | 18 | 22 | 3200000000 | 3600000000 | 150 | 400000000 | 4 | 1
J9 | PCC MM | 306.7051 | 1 | 36 | 46 | [5 empty] | 1
J10 | Lourens de Bruyn | 337.1234 | 0 | 24 | 42 | 1710000000 | 1950000000 | 1070 | 249000000 | 18 | 1
J11 | Henry Jonker | 347.6032 | 1 | 26 | 32 | 4500000000 | 4300000000 |  |  | 6 | 1
J12 | Hentie Fourie | 356.3889 | 1 | 36 | 48 | 1000000000 | 850000000 | 1000 | -235000000 | 12 | 1
J13 | Hopewell Sifeni | 365.8753 | 1 | 24 | 24 | 1500000000 | 1500000000 | 200 | 80000000 | 3 | 0
J14 | Pieter Brink | 380.9985 | 1 | 48 | 45 | 9000000000 | 8500000000
J15 | P Critcher | 401.6235 | 1 | 38 | 65 | 16016000000 | 16702000000 | 1386 | 686000000 | 24 | 1
J16 | Johan Bloemhof | 440.2209 | 0 | 10 | 13 | 4200000000 | 3800000000 | 1000 | 500000000 | 36 | 1
J17 | Willie Human | 487.6393 | 0 | 123 | 132 | 4200000000 | 2700000000 | 339 | 1740000000 | 0 | 1
J18 | R Grunewald | 275.1483 | 0 | 32 | 31 | 83000000 | 82900000 | 4 | 1600000 | 0 | 0
J19 | J v Dyk | 613.9911 | 0 | 10 | 10 | 200000000 | 194000000 | 5 | 8000000 | 0 | 1
J20 | Esparon | 294.6293 | 1 | 33 | 31 | 6734563200 | 7179364800 | 126 | 444801600 | 3 | 1
J21 | Meyer | 115.0946 | 0 | 84 | 84 | 9000000000 | 9000000000 | 1500 | 0 | 0 | 0
J22 | Moss | 426.1062 | 0 | 42 | 65 | 921600000 | 1512000000 |  |  |  | 1
J23 | Maluleke | 321.4715 | 1 | 48 | 60 | 7000000000 | 7500000000 | 50 | 800000000 | 14.4 | 1
J24 | Feroz | 493.5428 | 1 | 42 | 60 | 50400000000 | 86400000000 | 1000 | 28800000000 | 18 | 1
J25 | Archer | 105.7042 | 1 | 40 | 42 | 79200000000 | 77760000000 |  | 1440000000 | 0 | 1
J26 | SEP | 583.708 | 0 |  |  | 2966000000 | 4059000000 |  |  | 8 | 1
J27 | SSP | 165.542 | 1 | 48 | 45 | 8500000000 | 8500000000 |  |  | 0 | 0

## J1
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | X
A.2 | Project Charter and Mandate |  |  | X
A.3 | Governance and control (internal approval process defined) |  | X
A.5 | Project Strategy |  | X
A.6 | Strategic fit of project in organisation |  | X
A.7 | Due diligence |  |  | X
A.8 | Partnership, joint ventures and shareholder buy in | X
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  | X
B.2 | Geo-political risks |  | X
B.3 | Fiscal stability agreement |  | X
B.4 | Social License to Operate |  | X
B.5 | Violence and terrorism | X
B.6 | Ability to appoint expatriats | X
B.7 | Procurement of local and foreign materials, services and equipment |  | X
B.8 | Country infrastructure (power, roads, rail, water ports) |  | X
B.9 | Custom duties & logistic routes |  | X
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  |  | X
C.2 | Financing secured (Internal, external, equity, debt) |  |  | X
C.3 | Business Plan |  |  | X
C.4 | Economic Analysis |  | X
C.5 | Affordability / Feasibility |  | X
C.6 | Contingencies (Capex & Opex) |  | X
C.7 | Basis of Estimate |  | X
C.8 | Scenario planning |  | X
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | X
D.2 | Reserve risks (including modifying factors) |  | X
D.3 | Grade engineering / control |  | X
D.4 | Prospect drilling standard / guideline | X
D.5 | Geological conditions (Geological model, structure, qualities) | X
D.6 | Hydrogeology |  |  | X
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria | X
E.2 | Shaft/ramp design & men and material logistics | X
E.3 | Mining methods (drilling, blasting, loading, hauling) | X
E.4 | Equipment selection to fit geological conditions and mining method | X
E.5 | Life-of-mine plan | X
E.6 | Waste management plan |  | X
E.7 | Ultimate pit limits designed | X
E.8 | Economic block values determination | X
E.9 | Beneficiation facilities LOM plan |  |  | X
E.10 | Materials handling LOM plan |  | X
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | X
F.2 | Productivity / efficiency benchmarks |  |  | X
F.3 | Operating costs |  |  | X
F.4 | Production risks |  |  | X
F.5 | Catalogue of operating plans |  |  | X
F.6 | Haul roads |  | X
F.7 | Transportation strategy |  | X
F.8 | Contractual considerations |  | X
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  | X
G.2 | Price risks |  |  | X
G.3 | Demand risks & replacement products / technologies |  |  |  | X
G.4 | Value-Analysis Process |  |  |  | X
G.5 | Hedging |  |  |  | X
G.6 | Competitor analysis |  |  | X
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  | X
H.2 | Assumption register |  |  |  | X
H.3 | Completion risks |  | X
H.4 | Project Design Criteria |  | X
H.5 | Scope of Work Overview |  | X
H.6 | Project Schedule |  | X
H.7 | Project Cost Estimate |  | X
H.8 | Investment Studies & Alternatives Assessments |  |  |  | X
H.9 | Key Team Member Coordination |  | X
H.10 | Evaluation of Compliance Requirements |  |  | X
H.11 | Lead / Discipline Scope of Work |  | X
H.12 | Housing and transport of employees |  | X
H.13 | Risk or impact on other projects / divisions |  |  | X
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | X
I.2 | Site Characteristics Available vs. Required |  | X
I.3 | Project Scope definition |  | X
I.4 | WBS and WBS Dictionary |  | X
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan | X
J.2 | Land use plan post operations | X
J.3 | Social expectations register |  | X
J.4 | Relocation Action Plan | X
J.5 | Environmental expectations register |  | X
J.6 | Political expectations register |  |  | X
J.7 | Legal compliance register |  | X
J.8 | HSE risk register |  | X
J.9 | Community risk register |  | X
J.10 | Business risk register |  |  | X
J.11 | Developmental opportunity register |  |  |  | X
J.12 | Sustainability operating plan |  |  | X
J.13 | Stakeholder engagement plan |  | X
J.14 | Mine closure financial provision plan | X
J.15 | Closure plan review and updates scheduled during Life of Mine plan | X
J.16 | Social investment plan |  |  | X
J.17 | Economic diversification plan | X
J.18 | Existing Environmental Conditions |  | X
J.19 | Environmental Process determined |  | X
J.20 | Environmental management plan |  | X
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  | X
K.2 | Site Surveys |  | X
K.3 | Governing Regulatory Requirements |  | X
K.4 | Utility Sources with Supply Conditions |  | X
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  | X
K.6 | Special Water and Waste Treatment Requirements |  | X
K.7 | Property Descriptions |  | X
K.8 | Right-of-Way Mapping & Site Issues |  | X
K.9 | Land Rights | X
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  | X
L.2 | Civil/Site Design |  | X
L.3 | Geotechnical investigation for structures |  | X
L.4 | Architectural Design |  | X
L.5 | Structural Design |  | X
L.6 | Mechanical Design |  | X
L.7 | Electrical Design |  | X
L.8 | Constructability Analysis |  | X
L.9 | Process Design |  | X
L.10 | Specifications |  | X
L.11 | Specialty Items List |  | X
L.12 | Instrument Index |  | X
L.13 | Control Philosophy & systems |  | X
L.14 | Logic Diagrams |  | X
L.15 | IM (information management) |  | X
L.16 | Control of Access |  | X
L.17 | Safety & Hazards |  | X
L.18 | Operations/Maintenance |  |  | X
L.19 | Ventilation Engineering |  | X
L.20 | Rock Engineering | X
L.21 | Water balances |  | X
L.22 | Energy efficiency / carbon footprint |  |  | X
L.23 | Tailings handling and storage |  |  | X
L.24 | Stormwater handling / surface hydrology |  | X
L.25 | Internal technical audits |  |  | X
L.26 | External technical audits |  |  | X
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  | X
M.2 | Design & Material Alternatives Considered/Rejected |  | X
M.3 | Technology trends |  |  |  | X
M.4 | Design to capacity |  | X
M.5 | Classes of facillity quality |  | X
M.6 | Energy optimisation |  |  |  | X
M.7 | Waste minimisation |  |  |  | X
M.8 | 3D / 4D design |  | X
M.9 | Cleaner Production |  |  |  | X
M.10 | Innovation and knowledge management planning |  |  |  | X
M.11 | Six Sigma | X
M.12 | Lean Manufacturing |  | X
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | X
N.2 | Procurement Procedures and Plans |  |  | X
N.3 | Procurement Responsibility Matrix |  |  |  | X
N.4 | Draft contracts & proforma bidders pack |  |  | X
N.5 | Contracting strategy |  | X
N.6 | Procurement operation plan (POP) |  | X
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  | X
O.2 | Deliverables Defined |  | X
O.3 | Distribution Matrix |  | X
O.4 | Documentation/Deliverables |  | X
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  | X
P.2 | Project Cost Control |  | X
P.3 | Project Schedule Control |  | X
P.4 | Risk Management |  |  |  | X
P.5 | Safety, Health, Hygiene and security Management |  | X
P.6 | Environmental Management |  |  |  | X
P.7 | Project Change Control |  | X
P.8 | Project Audits |  |  |  | X
P.9 | Decision register |  |  | X
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  | X
Q.2 | Project Organization |  | X
Q.3 | Responsibility matrix RACI |  |  | X
Q.4 | Document Management Plan |  | X
Q.5 | Communication management plan |  | X
Q.6 | Project Delivery Method |  | X
Q.7 | Design / Construction Plan and Approach |  | X
Q.8 | Safety Procedures |  | X
Q.9 | Intercompany Agreements | X
Q.10 | Deliverables for Design and Construction |  | X
Q.11 | Labour and Skilled resources plan |  | X
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan
R.2 | Startup Requirements & plans |  | X
R.3 | Training Requirements |  |  | X
R.4 | Substantial Completion Requirements |  | X
R.5 | Deliverables for Project Commissioning / Closeout |  | X
R.6 | Long term supply chain contracts |  |  |  | X
R.7 | Resourcing & staffing for operation |  |  | X
R.8 | Maintenance schedules |  |  |  | X
R.9 | Critical spares |  |  |  | X
R.10 | Startup consumables |  |  | X
R.11 | Operational systems and procedures to support each department |  |  |  | X
R.12 | Environmental Management Plan for Operations (EMP) |  |  | X
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J2
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  | x
A.2 | Project Charter and Mandate |  |  | x
A.3 | Governance and control (internal approval process defined) |  | x
A.5 | Project Strategy |  |  | x
A.6 | Strategic fit of project in organisation |  | x
A.7 | Due diligence |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  | x
B.2 | Geo-political risks |  | x
B.3 | Fiscal stability agreement |  | x
B.4 | Social License to Operate |  |  | x
B.5 | Violence and terrorism |  | x
B.6 | Ability to appoint expatriats |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  | x
B.9 | Custom duties & logistic routes |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  | x
C.3 | Business Plan |  | x
C.4 | Economic Analysis |  | x
C.5 | Affordability / Feasibility |  | x
C.6 | Contingencies (Capex & Opex) |  | x
C.7 | Basis of Estimate |  | x
C.8 | Scenario planning |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  | x
D.3 | Grade engineering / control | x
D.4 | Prospect drilling standard / guideline | x
D.5 | Geological conditions (Geological model, structure, qualities) | x
D.6 | Hydrogeology |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  | x
E.2 | Shaft/ramp design & men and material logistics |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  | x
E.5 | Life-of-mine plan |  |  | x
E.6 | Waste management plan |  | x
E.7 | Ultimate pit limits designed |  | x
E.8 | Economic block values determination |  | x
E.9 | Beneficiation facilities LOM plan |  |  | x
E.10 | Materials handling LOM plan |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | x
F.2 | Productivity / efficiency benchmarks |  |  | x
F.3 | Operating costs |  |  | x
F.4 | Production risks |  |  | x
F.5 | Catalogue of operating plans |  |  | x
F.6 | Haul roads |  | x
F.7 | Transportation strategy |  | x
F.8 | Contractual considerations |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | x
G.2 | Price risks |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  | x
G.4 | Value-Analysis Process |  |  | x
G.5 | Hedging |  | x
G.6 | Competitor analysis | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  | x
H.2 | Assumption register |  |  | x
H.3 | Completion risks |  | x
H.4 | Project Design Criteria |  |  | x
H.5 | Scope of Work Overview |  |  | x
H.6 | Project Schedule |  |  |  | x
H.7 | Project Cost Estimate |  | x
H.8 | Investment Studies & Alternatives Assessments |  |  | x
H.9 | Key Team Member Coordination |  |  | x
H.10 | Evaluation of Compliance Requirements |  | x
H.11 | Lead / Discipline Scope of Work |  |  | x
H.12 | Housing and transport of employees |  | x
H.13 | Risk or impact on other projects / divisions |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | x
I.2 | Site Characteristics Available vs. Required |  |  | x
I.3 | Project Scope definition |  |  | x
I.4 | WBS and WBS Dictionary |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  | x
J.2 | Land use plan post operations |  |  | x
J.3 | Social expectations register |  | x
J.4 | Relocation Action Plan | x
J.5 | Environmental expectations register |  |  | x
J.6 | Political expectations register | x
J.7 | Legal compliance register |  |  |  | x
J.8 | HSE risk register |  |  | x
J.9 | Community risk register | x
J.10 | Business risk register |  | x
J.11 | Developmental opportunity register | x
J.12 | Sustainability operating plan | x
J.13 | Stakeholder engagement plan |  | x
J.14 | Mine closure financial provision plan |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  | x
J.16 | Social investment plan |  | x
J.17 | Economic diversification plan | x
J.18 | Existing Environmental Conditions |  |  | x
J.19 | Environmental Process determined |  |  | x
J.20 | Environmental management plan |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  | x
K.2 | Site Surveys |  |  |  | x
K.3 | Governing Regulatory Requirements |  |  | x
K.4 | Utility Sources with Supply Conditions |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  | x
K.6 | Special Water and Waste Treatment Requirements |  | x
K.7 | Property Descriptions |  | x
K.8 | Right-of-Way Mapping & Site Issues |  |  | x
K.9 | Land Rights |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  | x
L.2 | Civil/Site Design |  |  | x
L.3 | Geotechnical investigation for structures |  |  |  | x
L.4 | Architectural Design |  |  | x
L.5 | Structural Design |  |  | x
L.6 | Mechanical Design |  | x
L.7 | Electrical Design |  |  |  | x
L.8 | Constructability Analysis |  |  | x
L.9 | Process Design |  | x
L.10 | Specifications |  |  | x
L.11 | Specialty Items List |  |  | x
L.12 | Instrument Index |  |  |  | x
L.13 | Control Philosophy & systems |  |  | x
L.14 | Logic Diagrams |  |  | x
L.15 | IM (information management) |  | x
L.16 | Control of Access |  | x
L.17 | Safety & Hazards |  | x
L.18 | Operations/Maintenance |  |  | x
L.19 | Ventilation Engineering |  | x
L.20 | Rock Engineering |  |  |  | x
L.21 | Water balances |  |  | x
L.22 | Energy efficiency / carbon footprint |  |  | x
L.23 | Tailings handling and storage | x
L.24 | Stormwater handling / surface hydrology |  |  | x
L.25 | Internal technical audits |  |  | x
L.26 | External technical audits |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  | x
M.3 | Technology trends |  | x
M.4 | Design to capacity |  | x
M.5 | Classes of facillity quality |  | x
M.6 | Energy optimisation |  |  | x
M.7 | Waste minimisation | x
M.8 | 3D / 4D design | x
M.9 | Cleaner Production | x
M.10 | Innovation and knowledge management planning |  |  | x
M.11 | Six Sigma |  | x
M.12 | Lean Manufacturing |  | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | x
N.2 | Procurement Procedures and Plans |  | x
N.3 | Procurement Responsibility Matrix |  | x
N.4 | Draft contracts & proforma bidders pack |  | x
N.5 | Contracting strategy |  | x
N.6 | Procurement operation plan (POP) |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  | x
O.2 | Deliverables Defined |  | x
O.3 | Distribution Matrix |  | x
O.4 | Documentation/Deliverables |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  | x
P.2 | Project Cost Control |  | x
P.3 | Project Schedule Control |  |  |  | x
P.4 | Risk Management |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  | x
P.6 | Environmental Management |  |  | x
P.7 | Project Change Control |  | x
P.8 | Project Audits |  | x
P.9 | Decision register |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | x
Q.2 | Project Organization |  | x
Q.3 | Responsibility matrix RACI |  | x
Q.4 | Document Management Plan |  | x
Q.5 | Communication management plan |  |  | x
Q.6 | Project Delivery Method |  |  | x
Q.7 | Design / Construction Plan and Approach |  | x
Q.8 | Safety Procedures |  |  | x
Q.9 | Intercompany Agreements | x
Q.10 | Deliverables for Design and Construction |  | x
Q.11 | Labour and Skilled resources plan |  |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  | x
R.2 | Startup Requirements & plans |  |  |  | x
R.3 | Training Requirements |  |  |  | x
R.4 | Substantial Completion Requirements |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  | x
R.6 | Long term supply chain contracts | x
R.7 | Resourcing & staffing for operation | x
R.8 | Maintenance schedules | x |  | x
R.9 | Critical spares |  | x
R.10 | Startup consumables |  | x
R.11 | Operational systems and procedures to support each department |  |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J3
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | X
A.2 | Project Charter and Mandate |  | X
A.3 | Governance and control (internal approval process defined) |  |  | X
A.5 | Project Strategy |  |  |  | X
A.6 | Strategic fit of project in organisation |  | X
A.7 | Due diligence |  |  | X
A.8 | Partnership, joint ventures and shareholder buy in |  | X
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  | X
B.2 | Geo-political risks |  | X
B.3 | Fiscal stability agreement |  | X
B.4 | Social License to Operate |  | X
B.5 | Violence and terrorism | X
B.6 | Ability to appoint expatriats |  | X
B.7 | Procurement of local and foreign materials, services and equipment |  |  | X
B.8 | Country infrastructure (power, roads, rail, water ports) |  | X
B.9 | Custom duties & logistic routes |  | X
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | X
C.2 | Financing secured (Internal, external, equity, debt) |  | X
C.3 | Business Plan |  | X
C.4 | Economic Analysis |  | X
C.5 | Affordability / Feasibility |  | X
C.6 | Contingencies (Capex & Opex) |  |  |  |  | X
C.7 | Basis of Estimate |  |  | X
C.8 | Scenario planning |  |  |  |  | X
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  | X
D.2 | Reserve risks (including modifying factors) |  |  | X
D.3 | Grade engineering / control |  | X
D.4 | Prospect drilling standard / guideline |  |  |  | X
D.5 | Geological conditions (Geological model, structure, qualities) |  |  |  |  | X
D.6 | Hydrogeology |  |  |  | X
Total | CATEGORY D (Maximum = )
E | LIFE OF MINE PLANNING | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  | X
E.2 | Shaft/ramp design & men and material logistics |  | X
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | X
E.4 | Equipment selection to fit geological conditions and mining method |  | X
E.5 | Life-of-mine plan |  | X
E.6 | Waste management plan |  | X
E.7 | Ultimate pit limits designed |  |  | X
E.8 | Economic block values determination |  | X
E.9 | Beneficiation facilities LOM plan |  | X
E.10 | Materials handling LOM plan |  | X
Total | CATEGORY E (Maximum = )
F | OPERATING PHILOSOPHY | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | X
F.2 | Productivity / efficiency benchmarks |  |  | X
F.3 | Operating costs |  |  | X
F.4 | Production risks |  |  | X
F.5 | Catalogue of operating plans |  |  | X
F.6 | Haul roads |  | X
F.7 | Transportation strategy |  | X
F.8 | Contractual considerations |  | X
Total | CATEGORY F (Maximum = )
G | MARKET ANALYSIS AND STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | X
G.2 | Price risks |  | X
G.3 | Demand risks & replacement products / technologies |  | X
G.4 | Value-Analysis Process |  |  |  | X
G.5 | Hedging | X
G.6 | Competitor analysis | X
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
H | PROJECT CONSIDERATIONS | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  | X
H.2 | Assumption register |  |  |  | X
H.3 | Completion risks |  |  |  |  | X
H.4 | Project Design Criteria |  |  | X
H.5 | Scope of Work Overview |  | X
H.6 | Project Schedule |  |  |  | X
H.7 | Project Cost Estimate |  |  |  |  | X
H.8 | Investment Studies & Alternatives Assessments |  | X
H.9 | Key Team Member Coordination |  |  |  |  | X
H.10 | Evaluation of Compliance Requirements |  | X
H.11 | Lead / Discipline Scope of Work |  |  |  | X
H.12 | Housing and transport of employees |  | X
H.13 | Risk or impact on other projects / divisions |  | X
I | PROJECT SCOPE
I | PROJECT SCOPE | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | X
I.2 | Site Characteristics Available vs. Required |  | X
I.3 | Project Scope definition |  | X
I.4 | WBS and WBS Dictionary |  |  | X
Total | CATEGORY I (Maximum = )
J | SOCIAL & ENVIRONMENTAL REQUIREMENTS | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan | X
J.2 | Land use plan post operations | X
J.3 | Social expectations register | X
J.4 | Relocation Action Plan | X
J.5 | Environmental expectations register | X
J.6 | Political expectations register | X
J.7 | Legal compliance register |  | X
J.8 | HSE risk register |  | X
J.9 | Community risk register |  | X
J.10 | Business risk register |  |  | X
J.11 | Developmental opportunity register |  |  | X
J.12 | Sustainability operating plan |  |  | X
J.13 | Stakeholder engagement plan |  | X
J.14 | Mine closure financial provision plan |  |  | X
J.15 | Closure plan review and updates scheduled during Life of Mine plan | X
J.16 | Social investment plan | X
J.17 | Economic diversification plan | X
J.18 | Existing Environmental Conditions |  | X
J.19 | Environmental Process determined |  | X
J.20 | Environmental management plan |  | X
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
K | SITE INFORMATION | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  |  | X
K.2 | Site Surveys |  |  |  |  | X
K.3 | Governing Regulatory Requirements |  | X
K.4 | Utility Sources with Supply Conditions |  |  | X
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  |  | X
K.6 | Special Water and Waste Treatment Requirements |  | X
K.7 | Property Descriptions |  | X
K.8 | Right-of-Way Mapping & Site Issues |  | X
K.9 | Land Rights |  | X
Total | CATEGORY K (Maximum = )
L | PROJECT DESIGN PARAMETERS | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  | X
L.2 | Civil/Site Design |  |  | X
L.3 | Geotechnical investigation for structures |  |  |  |  | X
L.4 | Architectural Design |  |  | X
L.5 | Structural Design |  |  | X
L.6 | Mechanical Design |  | X
L.7 | Electrical Design |  |  |  | X
L.8 | Constructability Analysis |  |  |  | X
L.9 | Process Design |  | X
L.10 | Specifications |  |  | X
L.11 | Specialty Items List |  |  |  | X
L.12 | Instrument Index |  |  | X
L.13 | Control Philosophy & systems |  |  | X
L.14 | Logic Diagrams |  |  | X
L.15 | IM (information management) |  |  | X
L.16 | Control of Access |  | X
L.17 | Safety & Hazards |  | X
L.18 | Operations/Maintenance |  |  | X
L.19 | Ventilation Engineering |  | X
L.20 | Rock Engineering |  |  |  | X
L.21 | Water balances |  |  |  | X
L.22 | Energy efficiency / carbon footprint |  | X
L.23 | Tailings handling and storage |  | X
L.24 | Stormwater handling / surface hydrology |  | X
L.25 | Internal technical audits |  |  | X
L.26 | External technical audits |  |  | X
Total | CATEGORY L (Maximum = )
M | VALUE IMPROVING PRACTICES | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  | X
M.2 | Design & Material Alternatives Considered/Rejected |  | X
M.3 | Technology trends |  | X
M.4 | Design to capacity |  | X
M.5 | Classes of facillity quality |  | X
M.6 | Energy optimisation |  | X
M.7 | Waste minimisation |  | X
M.8 | 3D / 4D design |  | X
M.9 | Cleaner Production |  | X
M.10 | Innovation and knowledge management planning |  |  | X
M.11 | Six Sigma | X
M.12 | Lean Manufacturing |  |  | X
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
N | PROCUREMENT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | X
N.2 | Procurement Procedures and Plans |  |  | X
N.3 | Procurement Responsibility Matrix |  | X
N.4 | Draft contracts & proforma bidders pack |  | X
N.5 | Contracting strategy |  | X
N.6 | Procurement operation plan (POP) |  |  | X
Total | CATEGORY N (Maximum = )
O | DELIVERABLES | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  | X
O.2 | Deliverables Defined |  |  | X
O.3 | Distribution Matrix |  |  | X
O.4 | Documentation/Deliverables |  | X
Total | CATEGORY O (Maximum = )
P | PROJECT CONTROLS | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  | X
P.2 | Project Cost Control |  | X
P.3 | Project Schedule Control |  | X
P.4 | Risk Management |  | X
P.5 | Safety, Health, Hygiene and security Management |  | X
P.6 | Environmental Management |  | X
P.7 | Project Change Control |  | X
P.8 | Project Audits |  | X
P.9 | Decision register |  | X
Total | CATEGORY P (Maximum = )
Q | PROJECT EXECUTION PLAN | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | X
Q.2 | Project Organization |  |  | X
Q.3 | Responsibility matrix RACI |  | X
Q.4 | Document Management Plan |  | X
Q.5 | Communication management plan |  | X
Q.6 | Project Delivery Method |  | X
Q.7 | Design / Construction Plan and Approach |  | X
Q.8 | Safety Procedures |  | X
Q.9 | Intercompany Agreements |  | X
Q.10 | Deliverables for Design and Construction |  | X
Q.11 | Labour and Skilled resources plan |  | X
Total | CATEGORY Q (Maximum = )
R | HANDOVER & OPERATIONAL READINESS | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  | X
R.2 | Startup Requirements & plans |  |  | X
R.3 | Training Requirements |  |  | X
R.4 | Substantial Completion Requirements |  | X
R.5 | Deliverables for Project Commissioning / Closeout |  | X
R.6 | Long term supply chain contracts |  |  | X
R.7 | Resourcing & staffing for operation |  |  | X
R.8 | Maintenance schedules |  |  |  | X
R.9 | Critical spares |  | X
R.10 | Startup consumables |  | X
R.11 | Operational systems and procedures to support each department |  | X
R.12 | Environmental Management Plan for Operations (EMP) |  | X
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J4
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | X
A.2 | Project Charter and Mandate |  |  |  | X
A.3 | Governance and control (internal approval process defined) |  |  |  | X
A.5 | Project Strategy |  |  |  | X
A.6 | Strategic fit of project in organisation |  | X
A.7 | Due diligence |  |  | X
A.8 | Partnership, joint ventures and shareholder buy in |  | X
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  | X
B.2 | Geo-political risks |  | X
B.3 | Fiscal stability agreement |  | X
B.4 | Social License to Operate |  | X
B.5 | Violence and terrorism |  | X
B.6 | Ability to appoint expatriats |  | X
B.7 | Procurement of local and foreign materials, services and equipment |  | X
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  |  | X
B.9 | Custom duties & logistic routes |  | X
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | X
C.2 | Financing secured (Internal, external, equity, debt) |  | X
C.3 | Business Plan |  | X
C.4 | Economic Analysis |  | X
C.5 | Affordability / Feasibility |  | X
C.6 | Contingencies (Capex & Opex) |  | X
C.7 | Basis of Estimate |  | X
C.8 | Scenario planning |  |  | X
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  | X
D.2 | Reserve risks (including modifying factors) |  | X
D.3 | Grade engineering / control | X
D.4 | Prospect drilling standard / guideline | X
D.5 | Geological conditions (Geological model, structure, qualities) | X
D.6 | Hydrogeology | X
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  | X
E.2 | Shaft/ramp design & men and material logistics |  | X
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | X
E.4 | Equipment selection to fit geological conditions and mining method |  | X
E.5 | Life-of-mine plan |  | X
E.6 | Waste management plan | X
E.7 | Ultimate pit limits designed | X
E.8 | Economic block values determination | X
E.9 | Beneficiation facilities LOM plan |  | X
E.10 | Materials handling LOM plan |  | X
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | X
F.2 | Productivity / efficiency benchmarks |  |  | X
F.3 | Operating costs |  |  | X
F.4 | Production risks |  |  | X
F.5 | Catalogue of operating plans | X
F.6 | Haul roads | X
F.7 | Transportation strategy |  | X
F.8 | Contractual considerations |  | X
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements | X
G.2 | Price risks | X
G.3 | Demand risks & replacement products / technologies | X
G.4 | Value-Analysis Process |  | X
G.5 | Hedging | X
G.6 | Competitor analysis | X
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  | X
H.2 | Assumption register |  |  |  | X
H.3 | Completion risks |  |  |  | X
H.4 | Project Design Criteria |  |  | X
H.5 | Scope of Work Overview |  |  |  | X
H.6 | Project Schedule |  |  | X
H.7 | Project Cost Estimate |  |  | X
H.8 | Investment Studies & Alternatives Assessments |  | X
H.9 | Key Team Member Coordination |  | X
H.10 | Evaluation of Compliance Requirements |  | X
H.11 | Lead / Discipline Scope of Work |  |  | X
H.12 | Housing and transport of employees |  | X
H.13 | Risk or impact on other projects / divisions |  |  |  | X
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  | X
I.2 | Site Characteristics Available vs. Required |  |  | X
I.3 | Project Scope definition |  |  | X
I.4 | WBS and WBS Dictionary |  |  | X
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan | X
J.2 | Land use plan post operations | X
J.3 | Social expectations register | X
J.4 | Relocation Action Plan | X
J.5 | Environmental expectations register | X
J.6 | Political expectations register | X
J.7 | Legal compliance register | X
J.8 | HSE risk register |  |  | X
J.9 | Community risk register | X
J.10 | Business risk register |  |  | X
J.11 | Developmental opportunity register | X
J.12 | Sustainability operating plan | X
J.13 | Stakeholder engagement plan |  |  |  | X
J.14 | Mine closure financial provision plan | X
J.15 | Closure plan review and updates scheduled during Life of Mine plan | X
J.16 | Social investment plan | X
J.17 | Economic diversification plan | X
J.18 | Existing Environmental Conditions | X
J.19 | Environmental Process determined |  |  | X
J.20 | Environmental management plan |  |  | X
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  | X
K.2 | Site Surveys |  |  |  | X
K.3 | Governing Regulatory Requirements |  | X
K.4 | Utility Sources with Supply Conditions |  | X
K.5 | Fire Protection, emergency procedure & Safety Considerations |  | X
K.6 | Special Water and Waste Treatment Requirements |  | X
K.7 | Property Descriptions |  | X
K.8 | Right-of-Way Mapping & Site Issues |  |  |  | X
K.9 | Land Rights |  | X
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  | X
L.2 | Civil/Site Design |  |  | X
L.3 | Geotechnical investigation for structures |  | X
L.4 | Architectural Design |  |  | X
L.5 | Structural Design |  |  | X
L.6 | Mechanical Design |  |  | X
L.7 | Electrical Design |  |  | X
L.8 | Constructability Analysis |  |  |  | X
L.9 | Process Design |  |  | X
L.10 | Specifications |  |  |  | X
L.11 | Specialty Items List |  |  |  | X
L.12 | Instrument Index |  |  |  | X
L.13 | Control Philosophy & systems |  |  | X
L.14 | Logic Diagrams |  |  | X
L.15 | IM (information management) |  |  | X
L.16 | Control of Access |  |  | X
L.17 | Safety & Hazards |  |  | X
L.18 | Operations/Maintenance |  |  |  | X
L.19 | Ventilation Engineering | X
L.20 | Rock Engineering | X
L.21 | Water balances |  |  | X
L.22 | Energy efficiency / carbon footprint |  |  | X
L.23 | Tailings handling and storage |  | X
L.24 | Stormwater handling / surface hydrology |  | X
L.25 | Internal technical audits |  |  | X
L.26 | External technical audits |  |  | X
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  |  | X
M.2 | Design & Material Alternatives Considered/Rejected |  |  | X
M.3 | Technology trends |  |  | X
M.4 | Design to capacity |  | X
M.5 | Classes of facillity quality |  | X
M.6 | Energy optimisation |  | X
M.7 | Waste minimisation |  | X
M.8 | 3D / 4D design |  |  | X
M.9 | Cleaner Production |  | X
M.10 | Innovation and knowledge management planning |  |  | X
M.11 | Six Sigma |  |  | X
M.12 | Lean Manufacturing |  |  |  | X
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | X
N.2 | Procurement Procedures and Plans |  |  | X
N.3 | Procurement Responsibility Matrix |  |  | X
N.4 | Draft contracts & proforma bidders pack |  |  |  | X
N.5 | Contracting strategy |  |  |  | X
N.6 | Procurement operation plan (POP) |  |  |  | X
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  |  | X
O.2 | Deliverables Defined |  |  |  | X
O.3 | Distribution Matrix |  |  | X
O.4 | Documentation/Deliverables |  |  | X
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  |  | X
P.2 | Project Cost Control |  |  | X
P.3 | Project Schedule Control |  |  | X
P.4 | Risk Management |  |  |  | X
P.5 | Safety, Health, Hygiene and security Management |  | X
P.6 | Environmental Management |  | X
P.7 | Project Change Control |  | X
P.8 | Project Audits |  | X
P.9 | Decision register |  |  |  | X
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  |  | X
Q.2 | Project Organization |  |  |  | X
Q.3 | Responsibility matrix RACI |  |  |  | X
Q.4 | Document Management Plan |  |  |  |  | X
Q.5 | Communication management plan |  |  |  |  | X
Q.6 | Project Delivery Method |  |  | X
Q.7 | Design / Construction Plan and Approach |  |  | X
Q.8 | Safety Procedures |  | X
Q.9 | Intercompany Agreements |  | X
Q.10 | Deliverables for Design and Construction |  |  | X
Q.11 | Labour and Skilled resources plan |  |  | X
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  | X
R.2 | Startup Requirements & plans |  |  | X
R.3 | Training Requirements |  |  | X
R.4 | Substantial Completion Requirements |  | X
R.5 | Deliverables for Project Commissioning / Closeout |  | X
R.6 | Long term supply chain contracts | X
R.7 | Resourcing & staffing for operation |  | X
R.8 | Maintenance schedules |  | X
R.9 | Critical spares |  |  | X
R.10 | Startup consumables |  |  | X
R.11 | Operational systems and procedures to support each department |  | X
R.12 | Environmental Management Plan for Operations (EMP) |  | X
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J5
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | X
A.2 | Project Charter and Mandate |  | X
A.3 | Governance and control (internal approval process defined) |  | X
A.5 | Project Strategy |  | X
A.6 | Strategic fit of project in organisation |  | X
A.7 | Due diligence |  |  | X
A.8 | Partnership, joint ventures and shareholder buy in | X
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  | X
B.2 | Geo-political risks |  |  |  | X
B.3 | Fiscal stability agreement |  | X
B.4 | Social License to Operate |  | X
B.5 | Violence and terrorism |  |  |  |  | X
B.6 | Ability to appoint expatriats |  |  |  | X
B.7 | Procurement of local and foreign materials, services and equipment |  |  | X
B.8 | Country infrastructure (power, roads, rail, water ports) |  | X
B.9 | Custom duties & logistic routes | X
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | X
C.2 | Financing secured (Internal, external, equity, debt) |  | X
C.3 | Business Plan |  | X
C.4 | Economic Analysis |  | X
C.5 | Affordability / Feasibility |  | X
C.6 | Contingencies (Capex & Opex) |  |  | X
C.7 | Basis of Estimate |  |  | X
C.8 | Scenario planning |  |  | X
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  | X
D.2 | Reserve risks (including modifying factors) |  | X
D.3 | Grade engineering / control |  | X
D.4 | Prospect drilling standard / guideline |  | X
D.5 | Geological conditions (Geological model, structure, qualities) |  | X
D.6 | Hydrogeology |  |  |  |  | X
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  | X
E.2 | Shaft/ramp design & men and material logistics |  | X
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | X
E.4 | Equipment selection to fit geological conditions and mining method |  | X
E.5 | Life-of-mine plan |  | X
E.6 | Waste management plan |  | X
E.7 | Ultimate pit limits designed |  | X
E.8 | Economic block values determination |  | X
E.9 | Beneficiation facilities LOM plan |  | X
E.10 | Materials handling LOM plan |  | X
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | X
F.2 | Productivity / efficiency benchmarks |  | X
F.3 | Operating costs |  | X
F.4 | Production risks |  | X
F.5 | Catalogue of operating plans |  | X
F.6 | Haul roads | X
F.7 | Transportation strategy |  | X
F.8 | Contractual considerations |  |  | X
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | X
G.2 | Price risks |  | X
G.3 | Demand risks & replacement products / technologies |  | X
G.4 | Value-Analysis Process |  | X
G.5 | Hedging | X
G.6 | Competitor analysis | X
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  | X
H.2 | Assumption register |  |  | X
H.3 | Completion risks |  |  |  |  | X
H.4 | Project Design Criteria |  |  |  | X
H.5 | Scope of Work Overview |  |  | X
H.6 | Project Schedule |  |  |  | X
H.7 | Project Cost Estimate |  | X
H.8 | Investment Studies & Alternatives Assessments |  |  | X
H.9 | Key Team Member Coordination |  |  |  | X
H.10 | Evaluation of Compliance Requirements |  | X
H.11 | Lead / Discipline Scope of Work |  |  | X
H.12 | Housing and transport of employees |  | X
H.13 | Risk or impact on other projects / divisions |  | X
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | X
I.2 | Site Characteristics Available vs. Required |  |  |  | X
I.3 | Project Scope definition |  | X
I.4 | WBS and WBS Dictionary |  | X
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  | X
J.2 | Land use plan post operations |  |  | X
J.3 | Social expectations register |  |  |  | X
J.4 | Relocation Action Plan |  |  | X
J.5 | Environmental expectations register |  | X
J.6 | Political expectations register |  |  |  | X
J.7 | Legal compliance register |  | X
J.8 | HSE risk register |  |  | X
J.9 | Community risk register |  |  | X
J.10 | Business risk register |  | X
J.11 | Developmental opportunity register |  |  | X
J.12 | Sustainability operating plan |  |  | X
J.13 | Stakeholder engagement plan |  |  |  | X
J.14 | Mine closure financial provision plan |  | X
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  | X
J.16 | Social investment plan |  | X
J.17 | Economic diversification plan |  |  |  | X
J.18 | Existing Environmental Conditions |  | X
J.19 | Environmental Process determined |  | X
J.20 | Environmental management plan |  | X
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  | X
K.2 | Site Surveys |  |  | X
K.3 | Governing Regulatory Requirements |  | X
K.4 | Utility Sources with Supply Conditions |  | X
K.5 | Fire Protection, emergency procedure & Safety Considerations |  | X
K.6 | Special Water and Waste Treatment Requirements |  | X
K.7 | Property Descriptions |  | X
K.8 | Right-of-Way Mapping & Site Issues |  |  | X
K.9 | Land Rights |  | X
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  |  | X
L.2 | Civil/Site Design |  |  |  | X
L.3 | Geotechnical investigation for structures |  |  |  | X
L.4 | Architectural Design |  |  |  | X
L.5 | Structural Design |  | X
L.6 | Mechanical Design |  |  | X
L.7 | Electrical Design |  |  |  |  | X
L.8 | Constructability Analysis |  |  |  | X
L.9 | Process Design |  |  | X
L.10 | Specifications |  |  |  | X
L.11 | Specialty Items List |  |  | X
L.12 | Instrument Index |  |  | X
L.13 | Control Philosophy & systems |  |  | X
L.14 | Logic Diagrams |  |  | X
L.15 | IM (information management) |  |  | X
L.16 | Control of Access |  |  | X
L.17 | Safety & Hazards |  |  | X
L.18 | Operations/Maintenance |  |  | X
L.19 | Ventilation Engineering |  | X
L.20 | Rock Engineering |  | X
L.21 | Water balances |  | X
L.22 | Energy efficiency / carbon footprint |  | X
L.23 | Tailings handling and storage |  |  | X
L.24 | Stormwater handling / surface hydrology |  |  |  |  | X
L.25 | Internal technical audits |  | X
L.26 | External technical audits |  | X
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  | X
M.2 | Design & Material Alternatives Considered/Rejected |  | X
M.3 | Technology trends |  | X
M.4 | Design to capacity |  | X
M.5 | Classes of facillity quality |  | X
M.6 | Energy optimisation |  |  | X
M.7 | Waste minimisation |  | X
M.8 | 3D / 4D design |  |  |  | X
M.9 | Cleaner Production |  |  | X
M.10 | Innovation and knowledge management planning |  |  | X
M.11 | Six Sigma |  |  | X
M.12 | Lean Manufacturing |  |  | X
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | X
N.2 | Procurement Procedures and Plans |  |  |  | X
N.3 | Procurement Responsibility Matrix |  |  | X
N.4 | Draft contracts & proforma bidders pack |  |  |  | X
N.5 | Contracting strategy |  |  | X
N.6 | Procurement operation plan (POP) |  |  | X
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  |  | X
O.2 | Deliverables Defined |  | X
O.3 | Distribution Matrix |  |  | X
O.4 | Documentation/Deliverables |  |  | X
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  | X
P.2 | Project Cost Control |  | X
P.3 | Project Schedule Control |  |  |  | X
P.4 | Risk Management |  |  |  | X
P.5 | Safety, Health, Hygiene and security Management |  | X
P.6 | Environmental Management |  | X
P.7 | Project Change Control |  | X
P.8 | Project Audits |  | X
P.9 | Decision register |  | X
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | X
Q.2 | Project Organization |  | X
Q.3 | Responsibility matrix RACI |  | X
Q.4 | Document Management Plan |  | X
Q.5 | Communication management plan |  |  | X
Q.6 | Project Delivery Method | X
Q.7 | Design / Construction Plan and Approach |  |  | X
Q.8 | Safety Procedures |  | X
Q.9 | Intercompany Agreements |  | X
Q.10 | Deliverables for Design and Construction |  |  |  | X
Q.11 | Labour and Skilled resources plan |  |  |  | X
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  | X
R.2 | Startup Requirements & plans |  |  |  | X
R.3 | Training Requirements |  |  |  | X
R.4 | Substantial Completion Requirements |  |  | X
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  | X
R.6 | Long term supply chain contracts |  |  |  | X
R.7 | Resourcing & staffing for operation |  |  |  | X
R.8 | Maintenance schedules |  |  | X
R.9 | Critical spares |  |  | X
R.10 | Startup consumables |  |  |  | X
R.11 | Operational systems and procedures to support each department |  |  | X
R.12 | Environmental Management Plan for Operations (EMP) |  | X
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J6
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | x
A.2 | Project Charter and Mandate |  |  |  | x
A.3 | Governance and control (internal approval process defined) |  |  |  | x
A.5 | Project Strategy |  |  | x
A.6 | Strategic fit of project in organisation |  |  | x
A.7 | Due diligence |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  |  |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  | x
B.2 | Geo-political risks |  |  | x
B.3 | Fiscal stability agreement |  |  | x
B.4 | Social License to Operate |  |  | x
B.5 | Violence and terrorism |  | x
B.6 | Ability to appoint expatriats |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  | x
B.9 | Custom duties & logistic routes |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  | x
C.3 | Business Plan |  | x
C.4 | Economic Analysis |  | x
C.5 | Affordability / Feasibility |  | x
C.6 | Contingencies (Capex & Opex) |  |  | x
C.7 | Basis of Estimate |  |  | x
C.8 | Scenario planning |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  | x
D.3 | Grade engineering / control |  |  | x
D.4 | Prospect drilling standard / guideline |  |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  | x
D.6 | Hydrogeology |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  | x
E.2 | Shaft/ramp design & men and material logistics |  |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  | x
E.5 | Life-of-mine plan |  | x
E.6 | Waste management plan |  |  | x
E.7 | Ultimate pit limits designed |  |  | x
E.8 | Economic block values determination |  |  | x
E.9 | Beneficiation facilities LOM plan |  |  | x
E.10 | Materials handling LOM plan |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | x
F.2 | Productivity / efficiency benchmarks |  |  | x
F.3 | Operating costs |  | x
F.4 | Production risks |  |  | x
F.5 | Catalogue of operating plans |  |  |  | x
F.6 | Haul roads |  |  | x
F.7 | Transportation strategy |  | x
F.8 | Contractual considerations |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | x
G.2 | Price risks |  |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  | x
G.4 | Value-Analysis Process |  |  |  | x
G.5 | Hedging |  |  |  | x
G.6 | Competitor analysis |  |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  | x
H.2 | Assumption register |  |  | x
H.3 | Completion risks |  | x
H.4 | Project Design Criteria |  |  | x
H.5 | Scope of Work Overview |  |  | x
H.6 | Project Schedule |  | x
H.7 | Project Cost Estimate |  |  | x
H.8 | Investment Studies & Alternatives Assessments |  |  | x
H.9 | Key Team Member Coordination |  |  | x
H.10 | Evaluation of Compliance Requirements |  | x
H.11 | Lead / Discipline Scope of Work |  | x
H.12 | Housing and transport of employees |  | x
H.13 | Risk or impact on other projects / divisions | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  | x
I.2 | Site Characteristics Available vs. Required |  |  | x
I.3 | Project Scope definition |  | x
I.4 | WBS and WBS Dictionary |  |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  | x
J.2 | Land use plan post operations |  |  |  | x
J.3 | Social expectations register |  |  | x
J.4 | Relocation Action Plan |  |  | x
J.5 | Environmental expectations register |  | x
J.6 | Political expectations register |  |  |  |  | x
J.7 | Legal compliance register |  | x
J.8 | HSE risk register |  | x
J.9 | Community risk register |  |  | x
J.10 | Business risk register |  |  |  | x
J.11 | Developmental opportunity register |  |  |  | x
J.12 | Sustainability operating plan |  |  | x
J.13 | Stakeholder engagement plan |  |  |  | x
J.14 | Mine closure financial provision plan |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  | x
J.16 | Social investment plan |  | x
J.17 | Economic diversification plan |  |  | x
J.18 | Existing Environmental Conditions |  |  | x
J.19 | Environmental Process determined |  |  | x
J.20 | Environmental management plan |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  | x
K.2 | Site Surveys |  | x
K.3 | Governing Regulatory Requirements |  | x
K.4 | Utility Sources with Supply Conditions |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  | x
K.6 | Special Water and Waste Treatment Requirements |  | x
K.7 | Property Descriptions |  | x
K.8 | Right-of-Way Mapping & Site Issues |  | x
K.9 | Land Rights |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  | x
L.2 | Civil/Site Design |  | x
L.3 | Geotechnical investigation for structures |  |  | x
L.4 | Architectural Design |  |  | x
L.5 | Structural Design |  | x
L.6 | Mechanical Design |  | x
L.7 | Electrical Design |  | x
L.8 | Constructability Analysis |  |  | x
L.9 | Process Design |  | x
L.10 | Specifications |  |  | x
L.11 | Specialty Items List |  |  | x
L.12 | Instrument Index |  | x
L.13 | Control Philosophy & systems |  | x
L.14 | Logic Diagrams |  | x
L.15 | IM (information management) |  |  | x
L.16 | Control of Access |  | x
L.17 | Safety & Hazards |  | x
L.18 | Operations/Maintenance |  |  | x
L.19 | Ventilation Engineering | x
L.20 | Rock Engineering |  |  | x
L.21 | Water balances |  | x
L.22 | Energy efficiency / carbon footprint |  |  | x
L.23 | Tailings handling and storage |  |  | x
L.24 | Stormwater handling / surface hydrology |  | x
L.25 | Internal technical audits |  |  | x
L.26 | External technical audits |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  | x
M.3 | Technology trends |  |  | x
M.4 | Design to capacity |  |  | x
M.5 | Classes of facillity quality |  |  | x
M.6 | Energy optimisation |  |  | x
M.7 | Waste minimisation |  |  | x
M.8 | 3D / 4D design |  |  | x
M.9 | Cleaner Production |  |  | x
M.10 | Innovation and knowledge management planning |  |  |  | x
M.11 | Six Sigma |  |  | x
M.12 | Lean Manufacturing | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | x
N.2 | Procurement Procedures and Plans |  |  | x
N.3 | Procurement Responsibility Matrix |  |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  | x
N.5 | Contracting strategy |  | x
N.6 | Procurement operation plan (POP) |  |  |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  | x
O.2 | Deliverables Defined |  | x
O.3 | Distribution Matrix |  |  | x
O.4 | Documentation/Deliverables |  |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  | x
P.2 | Project Cost Control |  |  | x
P.3 | Project Schedule Control |  | x
P.4 | Risk Management |  | x
P.5 | Safety, Health, Hygiene and security Management |  | x
P.6 | Environmental Management |  | x
P.7 | Project Change Control |  |  | x
P.8 | Project Audits |  |  | x
P.9 | Decision register |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | x
Q.2 | Project Organization |  |  | x
Q.3 | Responsibility matrix RACI |  |  | x
Q.4 | Document Management Plan |  |  |  | x
Q.5 | Communication management plan |  |  |  | x
Q.6 | Project Delivery Method |  |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  | x
Q.8 | Safety Procedures |  | x
Q.9 | Intercompany Agreements |  | x
Q.10 | Deliverables for Design and Construction |  | x
Q.11 | Labour and Skilled resources plan |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  | x
R.2 | Startup Requirements & plans |  |  | x
R.3 | Training Requirements |  |  | x
R.4 | Substantial Completion Requirements |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  | x
R.6 | Long term supply chain contracts |  |  | x
R.7 | Resourcing & staffing for operation |  |  |  | x
R.8 | Maintenance schedules |  |  | x
R.9 | Critical spares |  |  | x
R.10 | Startup consumables |  |  | x
R.11 | Operational systems and procedures to support each department |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J7
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | x
A.2 | Project Charter and Mandate |  |  | x
A.3 | Governance and control (internal approval process defined) |  |  |  | x
A.5 | Project Strategy |  |  | x
A.6 | Strategic fit of project in organisation |  | x
A.7 | Due diligence |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  | x
B.2 | Geo-political risks |  | x
B.3 | Fiscal stability agreement |  |  |  | x
B.4 | Social License to Operate |  |  | x
B.5 | Violence and terrorism |  | x
B.6 | Ability to appoint expatriats |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  |  |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  | x
B.9 | Custom duties & logistic routes |  |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  | x
C.3 | Business Plan |  | x
C.4 | Economic Analysis |  | x
C.5 | Affordability / Feasibility |  | x
C.6 | Contingencies (Capex & Opex) |  |  | x
C.7 | Basis of Estimate |  |  |  | x
C.8 | Scenario planning |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  |  | x
D.3 | Grade engineering / control |  |  |  | x
D.4 | Prospect drilling standard / guideline |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  |  |  | x
D.6 | Hydrogeology |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  | x
E.2 | Shaft/ramp design & men and material logistics |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  |  | x
E.5 | Life-of-mine plan |  | x
E.6 | Waste management plan |  |  |  | x
E.7 | Ultimate pit limits designed |  |  | x
E.8 | Economic block values determination |  |  |  | x
E.9 | Beneficiation facilities LOM plan |  |  | x
E.10 | Materials handling LOM plan |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | x
F.2 | Productivity / efficiency benchmarks |  |  | x
F.3 | Operating costs |  |  |  | x
F.4 | Production risks |  |  |  | x
F.5 | Catalogue of operating plans |  |  |  |  | x
F.6 | Haul roads |  |  | x
F.7 | Transportation strategy |  | x
F.8 | Contractual considerations |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | x
G.2 | Price risks |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  | x
G.4 | Value-Analysis Process |  |  | x
G.5 | Hedging |  |  |  | x
G.6 | Competitor analysis |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  | x
H.2 | Assumption register |  | x
H.3 | Completion risks |  |  | x
H.4 | Project Design Criteria |  | x
H.5 | Scope of Work Overview |  | x
H.6 | Project Schedule |  |  |  |  | x
H.7 | Project Cost Estimate |  |  |  | x
H.8 | Investment Studies & Alternatives Assessments |  | x
H.9 | Key Team Member Coordination |  |  |  | x
H.10 | Evaluation of Compliance Requirements |  | x
H.11 | Lead / Discipline Scope of Work |  |  |  | x
H.12 | Housing and transport of employees |  | x
H.13 | Risk or impact on other projects / divisions |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | x
I.2 | Site Characteristics Available vs. Required |  | x
I.3 | Project Scope definition |  | x
I.4 | WBS and WBS Dictionary |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  |  | x
J.2 | Land use plan post operations |  |  |  |  | x
J.3 | Social expectations register |  | x
J.4 | Relocation Action Plan |  | x
J.5 | Environmental expectations register |  | x
J.6 | Political expectations register |  | x
J.7 | Legal compliance register |  | x
J.8 | HSE risk register |  | x
J.9 | Community risk register |  | x
J.10 | Business risk register |  | x
J.11 | Developmental opportunity register |  | x
J.12 | Sustainability operating plan |  | x
J.13 | Stakeholder engagement plan |  | x
J.14 | Mine closure financial provision plan |  |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  | x
J.16 | Social investment plan |  | x
J.17 | Economic diversification plan |  | x
J.18 | Existing Environmental Conditions |  |  | x
J.19 | Environmental Process determined |  |  |  | x
J.20 | Environmental management plan |  |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  | x
K.2 | Site Surveys |  |  | x
K.3 | Governing Regulatory Requirements |  | x
K.4 | Utility Sources with Supply Conditions |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  |  | x
K.6 | Special Water and Waste Treatment Requirements |  |  | x
K.7 | Property Descriptions |  |  | x
K.8 | Right-of-Way Mapping & Site Issues |  |  |  | x
K.9 | Land Rights |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  | x
L.2 | Civil/Site Design |  |  | x
L.3 | Geotechnical investigation for structures |  | x
L.4 | Architectural Design |  |  | x
L.5 | Structural Design |  |  | x
L.6 | Mechanical Design |  |  | x
L.7 | Electrical Design |  |  | x
L.8 | Constructability Analysis |  |  |  | x
L.9 | Process Design |  |  | x
L.10 | Specifications |  | x
L.11 | Specialty Items List |  |  | x
L.12 | Instrument Index |  |  |  | x
L.13 | Control Philosophy & systems |  |  | x
L.14 | Logic Diagrams |  |  | x
L.15 | IM (information management) |  |  |  |  | x
L.16 | Control of Access |  | x
L.17 | Safety & Hazards |  | x
L.18 | Operations/Maintenance |  |  |  | x
L.19 | Ventilation Engineering | x
L.20 | Rock Engineering | x
L.21 | Water balances |  |  |  | x
L.22 | Energy efficiency / carbon footprint |  |  |  | x
L.23 | Tailings handling and storage |  |  |  | x
L.24 | Stormwater handling / surface hydrology |  |  |  | x
L.25 | Internal technical audits |  |  |  |  | x
L.26 | External technical audits |  |  |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  | x
M.3 | Technology trends |  | x
M.4 | Design to capacity |  |  |  | x
M.5 | Classes of facillity quality |  |  |  | x
M.6 | Energy optimisation |  |  | x
M.7 | Waste minimisation |  |  |  | x
M.8 | 3D / 4D design |  |  | x
M.9 | Cleaner Production |  |  |  |  | x
M.10 | Innovation and knowledge management planning |  |  |  | x
M.11 | Six Sigma |  |  |  |  | x
M.12 | Lean Manufacturing |  |  |  |  | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  |  | x
N.2 | Procurement Procedures and Plans |  |  | x
N.3 | Procurement Responsibility Matrix |  | x
N.4 | Draft contracts & proforma bidders pack |  |  | x
N.5 | Contracting strategy |  | x
N.6 | Procurement operation plan (POP) |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  | x
O.2 | Deliverables Defined |  | x
O.3 | Distribution Matrix |  | x
O.4 | Documentation/Deliverables |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  |  | x
P.2 | Project Cost Control |  | x
P.3 | Project Schedule Control |  |  | x
P.4 | Risk Management |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  | x
P.6 | Environmental Management |  |  | x
P.7 | Project Change Control |  | x
P.8 | Project Audits |  |  | x
P.9 | Decision register |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | x
Q.2 | Project Organization |  | x
Q.3 | Responsibility matrix RACI |  | x
Q.4 | Document Management Plan |  |  |  | x
Q.5 | Communication management plan |  | x
Q.6 | Project Delivery Method |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  | x
Q.8 | Safety Procedures |  | x
Q.9 | Intercompany Agreements |  | x
Q.10 | Deliverables for Design and Construction |  | x
Q.11 | Labour and Skilled resources plan |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  | x
R.2 | Startup Requirements & plans |  |  |  |  | x
R.3 | Training Requirements |  |  |  |  | x
R.4 | Substantial Completion Requirements |  |  |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  | x
R.6 | Long term supply chain contracts |  |  | x
R.7 | Resourcing & staffing for operation |  |  |  | x
R.8 | Maintenance schedules |  |  |  |  | x
R.9 | Critical spares |  |  |  | x
R.10 | Startup consumables |  |  |  | x
R.11 | Operational systems and procedures to support each department |  |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J8
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  | x
A.2 | Project Charter and Mandate |  |  | x
A.3 | Governance and control (internal approval process defined) |  |  | x
A.5 | Project Strategy |  |  | x
A.6 | Strategic fit of project in organisation |  |  | x
A.7 | Due diligence |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  | x
B.2 | Geo-political risks |  |  | x
B.3 | Fiscal stability agreement |  |  | x
B.4 | Social License to Operate |  |  | x
B.5 | Violence and terrorism |  |  | x
B.6 | Ability to appoint expatriats |  |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  | x
B.9 | Custom duties & logistic routes |  |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  |  | x
C.3 | Business Plan |  |  | x
C.4 | Economic Analysis |  |  | x
C.5 | Affordability / Feasibility |  |  | x
C.6 | Contingencies (Capex & Opex) |  |  | x
C.7 | Basis of Estimate |  |  | x
C.8 | Scenario planning |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  | x
D.3 | Grade engineering / control |  |  | x
D.4 | Prospect drilling standard / guideline |  |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  |  | x
D.6 | Hydrogeology |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  | x
E.2 | Shaft/ramp design & men and material logistics |  |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  |  | x
E.5 | Life-of-mine plan |  |  | x
E.6 | Waste management plan |  |  | x
E.7 | Ultimate pit limits designed |  |  | x
E.8 | Economic block values determination |  |  | x
E.9 | Beneficiation facilities LOM plan |  |  | x
E.10 | Materials handling LOM plan |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  | x
F.2 | Productivity / efficiency benchmarks |  |  | x
F.3 | Operating costs |  |  | x
F.4 | Production risks |  |  | x
F.5 | Catalogue of operating plans |  |  | x
F.6 | Haul roads |  |  | x
F.7 | Transportation strategy |  |  | x
F.8 | Contractual considerations |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  | x
G.2 | Price risks |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  | x
G.4 | Value-Analysis Process |  |  | x
G.5 | Hedging |  |  | x
G.6 | Competitor analysis |  |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  | x
H.2 | Assumption register |  |  | x
H.3 | Completion risks |  |  | x
H.4 | Project Design Criteria |  |  | x
H.5 | Scope of Work Overview |  |  |  | x
H.6 | Project Schedule |  |  |  | x
H.7 | Project Cost Estimate |  |  |  | x
H.8 | Investment Studies & Alternatives Assessments | x
H.9 | Key Team Member Coordination |  |  | x
H.10 | Evaluation of Compliance Requirements |  |  | x
H.11 | Lead / Discipline Scope of Work |  |  | x
H.12 | Housing and transport of employees |  |  | x
H.13 | Risk or impact on other projects / divisions |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  | x
I.2 | Site Characteristics Available vs. Required |  |  | x
I.3 | Project Scope definition |  |  | x
I.4 | WBS and WBS Dictionary |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  | x
J.2 | Land use plan post operations |  |  | x
J.3 | Social expectations register |  |  | x
J.4 | Relocation Action Plan |  |  | x
J.5 | Environmental expectations register |  |  | x
J.6 | Political expectations register |  |  | x
J.7 | Legal compliance register |  |  | x
J.8 | HSE risk register |  |  | x
J.9 | Community risk register |  |  | x
J.10 | Business risk register |  |  | x
J.11 | Developmental opportunity register |  |  | x
J.12 | Sustainability operating plan |  |  | x
J.13 | Stakeholder engagement plan |  |  | x
J.14 | Mine closure financial provision plan |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  | x
J.16 | Social investment plan |  |  | x
J.17 | Economic diversification plan |  |  | x
J.18 | Existing Environmental Conditions |  |  | x
J.19 | Environmental Process determined |  |  | x
J.20 | Environmental management plan |  |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  |  | x
K.2 | Site Surveys |  |  |  | x
K.3 | Governing Regulatory Requirements |  |  | x
K.4 | Utility Sources with Supply Conditions |  |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  | x
K.6 | Special Water and Waste Treatment Requirements |  |  | x
K.7 | Property Descriptions |  |  | x
K.8 | Right-of-Way Mapping & Site Issues | x
K.9 | Land Rights | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  | x
L.2 | Civil/Site Design |  |  |  | x
L.3 | Geotechnical investigation for structures |  |  |  | x
L.4 | Architectural Design |  |  | x
L.5 | Structural Design |  |  | x
L.6 | Mechanical Design |  |  | x
L.7 | Electrical Design |  |  | x
L.8 | Constructability Analysis |  |  | x
L.9 | Process Design |  |  | x
L.10 | Specifications |  |  | x
L.11 | Specialty Items List |  |  | x
L.12 | Instrument Index |  |  | x
L.13 | Control Philosophy & systems |  |  | x
L.14 | Logic Diagrams |  |  | x
L.15 | IM (information management) |  |  | x
L.16 | Control of Access |  |  | x
L.17 | Safety & Hazards |  |  | x
L.18 | Operations/Maintenance |  |  | x
L.19 | Ventilation Engineering |  |  | x
L.20 | Rock Engineering |  |  | x
L.21 | Water balances |  |  | x
L.22 | Energy efficiency / carbon footprint |  |  | x
L.23 | Tailings handling and storage |  |  | x
L.24 | Stormwater handling / surface hydrology |  |  | x
L.25 | Internal technical audits |  |  | x
L.26 | External technical audits |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification | x
M.2 | Design & Material Alternatives Considered/Rejected | x
M.3 | Technology trends | x
M.4 | Design to capacity | x
M.5 | Classes of facillity quality | x
M.6 | Energy optimisation | x
M.7 | Waste minimisation | x
M.8 | 3D / 4D design | x
M.9 | Cleaner Production | x
M.10 | Innovation and knowledge management planning | x
M.11 | Six Sigma | x
M.12 | Lean Manufacturing | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | x
N.2 | Procurement Procedures and Plans |  |  | x
N.3 | Procurement Responsibility Matrix |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  | x
N.5 | Contracting strategy |  |  | x
N.6 | Procurement operation plan (POP) |  |  |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  | x
O.2 | Deliverables Defined |  |  | x
O.3 | Distribution Matrix |  |  | x
O.4 | Documentation/Deliverables |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  | x
P.2 | Project Cost Control |  |  | x
P.3 | Project Schedule Control |  |  | x
P.4 | Risk Management |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  | x
P.6 | Environmental Management |  |  | x
P.7 | Project Change Control |  |  | x
P.8 | Project Audits |  |  | x
P.9 | Decision register |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  |  | x
Q.2 | Project Organization |  |  |  | x
Q.3 | Responsibility matrix RACI |  |  |  | x
Q.4 | Document Management Plan |  |  | x
Q.5 | Communication management plan |  |  | x
Q.6 | Project Delivery Method |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  | x
Q.8 | Safety Procedures |  |  | x
Q.9 | Intercompany Agreements |  |  | x
Q.10 | Deliverables for Design and Construction |  |  | x
Q.11 | Labour and Skilled resources plan |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  | x
R.2 | Startup Requirements & plans |  |  | x
R.3 | Training Requirements |  |  | x
R.4 | Substantial Completion Requirements |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  | x
R.6 | Long term supply chain contracts |  |  | x
R.7 | Resourcing & staffing for operation |  |  | x
R.8 | Maintenance schedules |  |  | x
R.9 | Critical spares |  |  | x
R.10 | Startup consumables |  |  | x
R.11 | Operational systems and procedures to support each department |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J9
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  | x
A.2 | Project Charter and Mandate |  |  | x
A.3 | Governance and control (internal approval process defined) |  |  |  | x
A.5 | Project Strategy |  |  | x
A.6 | Strategic fit of project in organisation |  |  | x
A.7 | Due diligence |  |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  | x
B.2 | Geo-political risks |  | x
B.3 | Fiscal stability agreement |  | x
B.4 | Social License to Operate |  | x
B.5 | Violence and terrorism |  | x
B.6 | Ability to appoint expatriats |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  | x
B.9 | Custom duties & logistic routes |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  | x
C.3 | Business Plan |  | x
C.4 | Economic Analysis |  |  | x
C.5 | Affordability / Feasibility |  |  | x
C.6 | Contingencies (Capex & Opex) |  |  | x
C.7 | Basis of Estimate |  |  | x
C.8 | Scenario planning |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  | x
D.3 | Grade engineering / control |  |  | x
D.4 | Prospect drilling standard / guideline |  |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  |  | x
D.6 | Hydrogeology |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  | x
E.2 | Shaft/ramp design & men and material logistics |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  |  | x
E.5 | Life-of-mine plan |  | x
E.6 | Waste management plan |  |  | x
E.7 | Ultimate pit limits designed |  | x
E.8 | Economic block values determination |  | x
E.9 | Beneficiation facilities LOM plan |  |  | x
E.10 | Materials handling LOM plan |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  | x
F.2 | Productivity / efficiency benchmarks |  |  | x
F.3 | Operating costs |  | x
F.4 | Production risks |  | x
F.5 | Catalogue of operating plans |  |  | x
F.6 | Haul roads |  | x
F.7 | Transportation strategy |  | x
F.8 | Contractual considerations |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  | x
G.2 | Price risks |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  | x
G.4 | Value-Analysis Process |  |  | x
G.5 | Hedging |  |  | x
G.6 | Competitor analysis |  |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  |  | x
H.2 | Assumption register |  |  |  | x
H.3 | Completion risks |  |  |  | x
H.4 | Project Design Criteria |  |  |  | x
H.5 | Scope of Work Overview |  |  |  |  | x
H.6 | Project Schedule |  |  |  |  | x
H.7 | Project Cost Estimate |  |  | x
H.8 | Investment Studies & Alternatives Assessments |  |  | x
H.9 | Key Team Member Coordination |  |  | x
H.10 | Evaluation of Compliance Requirements |  |  | x
H.11 | Lead / Discipline Scope of Work |  |  |  | x
H.12 | Housing and transport of employees |  |  | x
H.13 | Risk or impact on other projects / divisions |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  | x
I.2 | Site Characteristics Available vs. Required |  |  | x
I.3 | Project Scope definition |  |  |  | x
I.4 | WBS and WBS Dictionary |  |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  | x
J.2 | Land use plan post operations |  |  | x
J.3 | Social expectations register |  |  | x
J.4 | Relocation Action Plan |  |  | x
J.5 | Environmental expectations register |  |  | x
J.6 | Political expectations register |  |  | x
J.7 | Legal compliance register |  |  | x
J.8 | HSE risk register |  |  | x
J.9 | Community risk register |  | x
J.10 | Business risk register |  |  | x
J.11 | Developmental opportunity register |  |  |  | x
J.12 | Sustainability operating plan |  |  | x
J.13 | Stakeholder engagement plan |  | x
J.14 | Mine closure financial provision plan |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  | x
J.16 | Social investment plan |  |  | x
J.17 | Economic diversification plan |  | x
J.18 | Existing Environmental Conditions |  |  | x
J.19 | Environmental Process determined |  |  |  | x
J.20 | Environmental management plan |  |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  |  | x
K.2 | Site Surveys |  |  |  | x
K.3 | Governing Regulatory Requirements |  |  | x
K.4 | Utility Sources with Supply Conditions |  |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  | x
K.6 | Special Water and Waste Treatment Requirements |  |  | x
K.7 | Property Descriptions |  |  | x
K.8 | Right-of-Way Mapping & Site Issues |  | x
K.9 | Land Rights |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  | x
L.2 | Civil/Site Design |  |  |  | x
L.3 | Geotechnical investigation for structures |  |  | x
L.4 | Architectural Design |  |  |  | x
L.5 | Structural Design |  |  | x
L.6 | Mechanical Design |  |  | x
L.7 | Electrical Design |  |  | x
L.8 | Constructability Analysis |  |  | x
L.9 | Process Design |  |  |  | x
L.10 | Specifications |  |  | x
L.11 | Specialty Items List |  |  | x
L.12 | Instrument Index |  |  | x
L.13 | Control Philosophy & systems |  |  | x
L.14 | Logic Diagrams |  |  | x
L.15 | IM (information management) |  |  | x
L.16 | Control of Access |  | x
L.17 | Safety & Hazards |  |  |  | x
L.18 | Operations/Maintenance |  |  |  | x
L.19 | Ventilation Engineering |  |  | x
L.20 | Rock Engineering |  |  |  | x
L.21 | Water balances |  | x
L.22 | Energy efficiency / carbon footprint |  |  | x
L.23 | Tailings handling and storage |  |  | x
L.24 | Stormwater handling / surface hydrology |  | x
L.25 | Internal technical audits |  |  |  | x
L.26 | External technical audits |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  | x
M.3 | Technology trends |  |  | x
M.4 | Design to capacity |  |  |  | x
M.5 | Classes of facillity quality |  |  | x
M.6 | Energy optimisation |  |  | x
M.7 | Waste minimisation |  |  |  | x
M.8 | 3D / 4D design |  |  | x
M.9 | Cleaner Production |  |  | x
M.10 | Innovation and knowledge management planning |  |  | x
M.11 | Six Sigma |  |  | x
M.12 | Lean Manufacturing |  |  | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  |  | x
N.2 | Procurement Procedures and Plans |  |  | x
N.3 | Procurement Responsibility Matrix |  |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  | x
N.5 | Contracting strategy |  |  |  | x
N.6 | Procurement operation plan (POP) |  |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  | x
O.2 | Deliverables Defined |  |  | x
O.3 | Distribution Matrix |  |  | x
O.4 | Documentation/Deliverables |  |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  | x
P.2 | Project Cost Control |  |  | x
P.3 | Project Schedule Control |  |  | x
P.4 | Risk Management |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  | x
P.6 | Environmental Management |  |  |  | x
P.7 | Project Change Control |  |  | x
P.8 | Project Audits |  |  | x
P.9 | Decision register |  |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | x
Q.2 | Project Organization |  |  | x
Q.3 | Responsibility matrix RACI |  |  | x
Q.4 | Document Management Plan |  |  | x
Q.5 | Communication management plan |  |  | x
Q.6 | Project Delivery Method |  |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  |  | x
Q.8 | Safety Procedures |  |  | x
Q.9 | Intercompany Agreements |  |  | x
Q.10 | Deliverables for Design and Construction |  |  | x
Q.11 | Labour and Skilled resources plan |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan
R.2 | Startup Requirements & plans |  |  |  | x
R.3 | Training Requirements |  |  |  | x
R.4 | Substantial Completion Requirements |  |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  | x
R.6 | Long term supply chain contracts |  |  | x
R.7 | Resourcing & staffing for operation |  |  | x
R.8 | Maintenance schedules |  |  | x
R.9 | Critical spares |  |  | x
R.10 | Startup consumables |  |  | x
R.11 | Operational systems and procedures to support each department |  |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  |  |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J10
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  | x
A.2 | Project Charter and Mandate |  |  | x
A.3 | Governance and control (internal approval process defined) |  |  | x
A.5 | Project Strategy |  |  | x
A.6 | Strategic fit of project in organisation |  | x
A.7 | Due diligence |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  |  |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  | x
B.2 | Geo-political risks |  |  | x
B.3 | Fiscal stability agreement |  | x
B.4 | Social License to Operate |  | x
B.5 | Violence and terrorism |  |  | x
B.6 | Ability to appoint expatriats |  |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  | x
B.9 | Custom duties & logistic routes |  |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  |  | x
C.3 | Business Plan |  | x
C.4 | Economic Analysis |  |  | x
C.5 | Affordability / Feasibility |  |  | x
C.6 | Contingencies (Capex & Opex) |  |  |  | x
C.7 | Basis of Estimate |  |  | x
C.8 | Scenario planning |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  | x
D.2 | Reserve risks (including modifying factors) |  | x
D.3 | Grade engineering / control |  |  |  | x
D.4 | Prospect drilling standard / guideline | x
D.5 | Geological conditions (Geological model, structure, qualities) |  | x
D.6 | Hydrogeology | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  | x
E.2 | Shaft/ramp design & men and material logistics |  |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  | x
E.5 | Life-of-mine plan |  | x
E.6 | Waste management plan |  | x
E.7 | Ultimate pit limits designed | x
E.8 | Economic block values determination |  | x
E.9 | Beneficiation facilities LOM plan |  | x
E.10 | Materials handling LOM plan |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  | x
F.2 | Productivity / efficiency benchmarks |  | x
F.3 | Operating costs |  |  | x
F.4 | Production risks |  | x
F.5 | Catalogue of operating plans |  |  | x
F.6 | Haul roads |  | x
F.7 | Transportation strategy |  | x
F.8 | Contractual considerations |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | x
G.2 | Price risks |  |  |  | x
G.3 | Demand risks & replacement products / technologies |  | x
G.4 | Value-Analysis Process |  | x
G.5 | Hedging |  | x
G.6 | Competitor analysis |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  | x
H.2 | Assumption register |  |  | x
H.3 | Completion risks |  |  | x
H.4 | Project Design Criteria |  |  |  | x
H.5 | Scope of Work Overview |  |  |  | x
H.6 | Project Schedule |  |  |  | x
H.7 | Project Cost Estimate |  |  |  | x
H.8 | Investment Studies & Alternatives Assessments |  |  |  | x
H.9 | Key Team Member Coordination |  |  |  | x
H.10 | Evaluation of Compliance Requirements |  |  | x
H.11 | Lead / Discipline Scope of Work |  |  |  | x
H.12 | Housing and transport of employees |  |  |  | x
H.13 | Risk or impact on other projects / divisions |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  | x
I.2 | Site Characteristics Available vs. Required |  | x
I.3 | Project Scope definition |  |  |  | x
I.4 | WBS and WBS Dictionary |  |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan | x
J.2 | Land use plan post operations | x
J.3 | Social expectations register |  |  | x
J.4 | Relocation Action Plan | x
J.5 | Environmental expectations register |  | x
J.6 | Political expectations register |  |  | x
J.7 | Legal compliance register |  | x
J.8 | HSE risk register |  |  | x
J.9 | Community risk register |  |  | x
J.10 | Business risk register |  | x
J.11 | Developmental opportunity register |  | x
J.12 | Sustainability operating plan |  | x
J.13 | Stakeholder engagement plan |  |  |  | x
J.14 | Mine closure financial provision plan | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan | x
J.16 | Social investment plan |  | x
J.17 | Economic diversification plan |  | x
J.18 | Existing Environmental Conditions |  | x
J.19 | Environmental Process determined |  |  | x
J.20 | Environmental management plan |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  |  | x
K.2 | Site Surveys |  |  |  |  | x
K.3 | Governing Regulatory Requirements |  |  | x
K.4 | Utility Sources with Supply Conditions |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  |  | x
K.6 | Special Water and Waste Treatment Requirements |  |  | x
K.7 | Property Descriptions |  |  | x
K.8 | Right-of-Way Mapping & Site Issues |  |  |  | x
K.9 | Land Rights |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  |  |  | x
L.2 | Civil/Site Design |  |  | x
L.3 | Geotechnical investigation for structures |  |  | x
L.4 | Architectural Design |  |  | x
L.5 | Structural Design |  |  | x
L.6 | Mechanical Design |  |  | x
L.7 | Electrical Design |  |  |  | x
L.8 | Constructability Analysis |  |  |  | x
L.9 | Process Design |  |  |  | x
L.10 | Specifications |  |  |  |  | x
L.11 | Specialty Items List |  |  | x
L.12 | Instrument Index |  |  |  | x
L.13 | Control Philosophy & systems |  |  |  |  | x
L.14 | Logic Diagrams |  |  |  |  | x
L.15 | IM (information management) |  |  |  |  | x
L.16 | Control of Access |  |  | x
L.17 | Safety & Hazards |  |  | x
L.18 | Operations/Maintenance |  |  |  | x
L.19 | Ventilation Engineering |  | x
L.20 | Rock Engineering |  | x
L.21 | Water balances |  |  |  | x
L.22 | Energy efficiency / carbon footprint |  |  |  | x
L.23 | Tailings handling and storage |  |  | x
L.24 | Stormwater handling / surface hydrology |  |  | x
L.25 | Internal technical audits |  |  | x
L.26 | External technical audits |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  |  | x
M.3 | Technology trends |  |  |  | x
M.4 | Design to capacity |  |  | x
M.5 | Classes of facillity quality |  |  | x
M.6 | Energy optimisation |  |  |  | x
M.7 | Waste minimisation |  |  | x
M.8 | 3D / 4D design |  |  |  | x
M.9 | Cleaner Production |  |  |  | x
M.10 | Innovation and knowledge management planning |  |  |  | x
M.11 | Six Sigma | x
M.12 | Lean Manufacturing | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  |  |  | x
N.2 | Procurement Procedures and Plans |  |  |  | x
N.3 | Procurement Responsibility Matrix |  |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  | x
N.5 | Contracting strategy |  |  |  | x
N.6 | Procurement operation plan (POP) |  |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  |  | x
O.2 | Deliverables Defined |  |  |  | x
O.3 | Distribution Matrix |  |  |  | x
O.4 | Documentation/Deliverables |  |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  |  | x
P.2 | Project Cost Control |  |  |  | x
P.3 | Project Schedule Control |  |  |  | x
P.4 | Risk Management |  |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  | x
P.6 | Environmental Management |  |  | x
P.7 | Project Change Control |  |  |  | x
P.8 | Project Audits |  |  | x
P.9 | Decision register |  |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  |  | x
Q.2 | Project Organization |  |  |  | x
Q.3 | Responsibility matrix RACI |  |  |  |  | x
Q.4 | Document Management Plan |  |  |  |  | x
Q.5 | Communication management plan |  |  |  | x
Q.6 | Project Delivery Method |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  |  |  | x
Q.8 | Safety Procedures |  |  |  |  | x
Q.9 | Intercompany Agreements |  |  |  | x
Q.10 | Deliverables for Design and Construction |  |  | x
Q.11 | Labour and Skilled resources plan |  |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  | x
R.2 | Startup Requirements & plans |  |  |  |  | x
R.3 | Training Requirements |  |  |  |  | x
R.4 | Substantial Completion Requirements |  |  |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  |  | x
R.6 | Long term supply chain contracts |  |  |  | x
R.7 | Resourcing & staffing for operation |  |  |  |  | x
R.8 | Maintenance schedules |  |  |  | x
R.9 | Critical spares |  |  |  | x
R.10 | Startup consumables |  |  | x
R.11 | Operational systems and procedures to support each department |  |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J11
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  | x
A.2 | Project Charter and Mandate |  |  | x
A.3 | Governance and control (internal approval process defined) |  |  | x
A.5 | Project Strategy |  |  |  | x
A.6 | Strategic fit of project in organisation |  |  | x
A.7 | Due diligence |  |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  | x
B.2 | Geo-political risks |  |  |  | x
B.3 | Fiscal stability agreement |  |  | x
B.4 | Social License to Operate |  |  | x
B.5 | Violence and terrorism |  |  |  | x
B.6 | Ability to appoint expatriats |  |  |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  | x
B.9 | Custom duties & logistic routes |  |  |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  | x
C.3 | Business Plan |  |  | x
C.4 | Economic Analysis |  |  | x
C.5 | Affordability / Feasibility |  |  | x
C.6 | Contingencies (Capex & Opex) |  |  | x
C.7 | Basis of Estimate |  |  | x
C.8 | Scenario planning |  |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  | x
D.3 | Grade engineering / control |  |  | x
D.4 | Prospect drilling standard / guideline |  |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  |  |  | x
D.6 | Hydrogeology |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  | x
E.2 | Shaft/ramp design & men and material logistics |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  |  | x
E.5 | Life-of-mine plan |  | x
E.6 | Waste management plan |  | x
E.7 | Ultimate pit limits designed | x
E.8 | Economic block values determination |  |  | x
E.9 | Beneficiation facilities LOM plan |  | x
E.10 | Materials handling LOM plan |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  | x
F.2 | Productivity / efficiency benchmarks |  |  | x
F.3 | Operating costs |  |  | x
F.4 | Production risks |  |  |  | x
F.5 | Catalogue of operating plans |  |  | x
F.6 | Haul roads | x
F.7 | Transportation strategy |  |  | x
F.8 | Contractual considerations |  |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  | x
G.2 | Price risks |  |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  | x
G.4 | Value-Analysis Process |  |  | x
G.5 | Hedging |  |  |  |  | x
G.6 | Competitor analysis |  |  |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  | x
H.2 | Assumption register |  |  | x
H.3 | Completion risks |  |  | x
H.4 | Project Design Criteria |  |  | x
H.5 | Scope of Work Overview |  |  |  | x
H.6 | Project Schedule |  |  | x
H.7 | Project Cost Estimate |  |  |  | x
H.8 | Investment Studies & Alternatives Assessments |  |  |  | x
H.9 | Key Team Member Coordination |  |  | x
H.10 | Evaluation of Compliance Requirements |  |  | x
H.11 | Lead / Discipline Scope of Work |  |  |  |  | x
H.12 | Housing and transport of employees |  |  |  |  | x
H.13 | Risk or impact on other projects / divisions |  |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | x
I.2 | Site Characteristics Available vs. Required |  |  | x
I.3 | Project Scope definition |  |  | x
I.4 | WBS and WBS Dictionary |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  | x
J.2 | Land use plan post operations |  |  | x
J.3 | Social expectations register |  |  |  | x
J.4 | Relocation Action Plan |  |  |  | x
J.5 | Environmental expectations register |  |  | x
J.6 | Political expectations register |  |  |  | x
J.7 | Legal compliance register |  | x
J.8 | HSE risk register |  |  | x
J.9 | Community risk register |  |  |  | x
J.10 | Business risk register |  |  | x
J.11 | Developmental opportunity register |  |  |  | x
J.12 | Sustainability operating plan |  |  | x
J.13 | Stakeholder engagement plan |  |  | x
J.14 | Mine closure financial provision plan |  |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  | x
J.16 | Social investment plan |  |  |  | x
J.17 | Economic diversification plan |  |  |  | x
J.18 | Existing Environmental Conditions |  |  | x
J.19 | Environmental Process determined |  |  | x
J.20 | Environmental management plan |  |  |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  | x
K.2 | Site Surveys |  |  | x
K.3 | Governing Regulatory Requirements |  | x
K.4 | Utility Sources with Supply Conditions |  |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  | x
K.6 | Special Water and Waste Treatment Requirements |  |  | x
K.7 | Property Descriptions |  |  | x
K.8 | Right-of-Way Mapping & Site Issues |  |  |  | x
K.9 | Land Rights |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  | x
L.2 | Civil/Site Design |  |  | x
L.3 | Geotechnical investigation for structures |  |  | x
L.4 | Architectural Design |  |  |  | x
L.5 | Structural Design |  |  | x
L.6 | Mechanical Design |  |  | x
L.7 | Electrical Design |  |  | x
L.8 | Constructability Analysis |  |  |  | x
L.9 | Process Design |  |  | x
L.10 | Specifications |  |  | x
L.11 | Specialty Items List |  |  |  | x
L.12 | Instrument Index |  |  |  | x
L.13 | Control Philosophy & systems |  |  | x
L.14 | Logic Diagrams |  |  |  | x
L.15 | IM (information management) |  |  |  | x
L.16 | Control of Access |  |  |  | x
L.17 | Safety & Hazards |  |  | x
L.18 | Operations/Maintenance |  |  | x
L.19 | Ventilation Engineering |  |  | x
L.20 | Rock Engineering |  |  | x
L.21 | Water balances |  |  | x
L.22 | Energy efficiency / carbon footprint |  |  |  | x
L.23 | Tailings handling and storage |  |  |  | x
L.24 | Stormwater handling / surface hydrology |  |  | x
L.25 | Internal technical audits |  |  | x
L.26 | External technical audits |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  | x
M.3 | Technology trends |  |  |  | x
M.4 | Design to capacity |  |  | x
M.5 | Classes of facillity quality |  |  | x
M.6 | Energy optimisation |  |  | x
M.7 | Waste minimisation |  |  | x
M.8 | 3D / 4D design |  |  |  | x
M.9 | Cleaner Production |  |  |  | x
M.10 | Innovation and knowledge management planning |  |  | x
M.11 | Six Sigma |  |  |  | x
M.12 | Lean Manufacturing |  |  | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  |  | x
N.2 | Procurement Procedures and Plans |  |  | x
N.3 | Procurement Responsibility Matrix |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  | x
N.5 | Contracting strategy |  |  | x
N.6 | Procurement operation plan (POP) |  |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  |  | x
O.2 | Deliverables Defined |  |  | x
O.3 | Distribution Matrix |  |  | x
O.4 | Documentation/Deliverables |  |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  | x
P.2 | Project Cost Control |  |  | x
P.3 | Project Schedule Control |  |  | x
P.4 | Risk Management |  |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  | x
P.6 | Environmental Management |  |  |  | x
P.7 | Project Change Control |  |  | x
P.8 | Project Audits |  |  |  | x
P.9 | Decision register |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | x
Q.2 | Project Organization |  |  | x
Q.3 | Responsibility matrix RACI |  |  | x
Q.4 | Document Management Plan |  |  | x
Q.5 | Communication management plan |  |  | x
Q.6 | Project Delivery Method |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  | x
Q.8 | Safety Procedures |  |  | x
Q.9 | Intercompany Agreements |  |  |  | x
Q.10 | Deliverables for Design and Construction |  |  | x
Q.11 | Labour and Skilled resources plan |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  | x
R.2 | Startup Requirements & plans |  |  | x
R.3 | Training Requirements |  |  |  | x
R.4 | Substantial Completion Requirements |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  | x
R.6 | Long term supply chain contracts |  |  | x
R.7 | Resourcing & staffing for operation |  |  | x
R.8 | Maintenance schedules |  |  | x
R.9 | Critical spares |  |  | x
R.10 | Startup consumables |  |  | x
R.11 | Operational systems and procedures to support each department |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  |  |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J12
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | X
A.2 | Project Charter and Mandate |  |  |  | X
A.3 | Governance and control (internal approval process defined) | [5 empty] | X
A.5 | Project Strategy |  |  |  | X
A.6 | Strategic fit of project in organisation |  | X
A.7 | Due diligence |  | X
A.8 | Partnership, joint ventures and shareholder buy in |  |  |  |  | X
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  | X
B.2 | Geo-political risks |  | X
B.3 | Fiscal stability agreement |  |  | X
B.4 | Social License to Operate |  |  |  | X
B.5 | Violence and terrorism |  | X
B.6 | Ability to appoint expatriats |  | X
B.7 | Procurement of local and foreign materials, services and equipment |  |  | X
B.8 | Country infrastructure (power, roads, rail, water ports) |  | X
B.9 | Custom duties & logistic routes |  | X
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | X
C.2 | Financing secured (Internal, external, equity, debt) |  | X
C.3 | Business Plan |  |  | X
C.4 | Economic Analysis |  |  |  | X
C.5 | Affordability / Feasibility |  |  |  | X
C.6 | Contingencies (Capex & Opex) |  |  |  |  | X
C.7 | Basis of Estimate |  |  |  |  | X
C.8 | Scenario planning |  |  |  |  | X
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  |  |  | X
D.2 | Reserve risks (including modifying factors) |  |  |  |  | X
D.3 | Grade engineering / control |  |  |  | X
D.4 | Prospect drilling standard / guideline | [5 empty] | X
D.5 | Geological conditions (Geological model, structure, qualities) |  |  |  |  | X
D.6 | Hydrogeology |  |  |  |  | X
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  |  | X
E.2 | Shaft/ramp design & men and material logistics |  |  |  | X
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  | X
E.4 | Equipment selection to fit geological conditions and mining method |  |  | X
E.5 | Life-of-mine plan | [5 empty] | X
E.6 | Waste management plan |  |  |  | X
E.7 | Ultimate pit limits designed |  |  |  | X
E.8 | Economic block values determination |  |  |  |  | X
E.9 | Beneficiation facilities LOM plan |  |  |  | X
E.10 | Materials handling LOM plan |  | X
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  |  |  | X
F.2 | Productivity / efficiency benchmarks |  |  |  |  | X
F.3 | Operating costs |  |  |  | X
F.4 | Production risks | [5 empty] | X
F.5 | Catalogue of operating plans |  |  |  |  | X
F.6 | Haul roads |  | X
F.7 | Transportation strategy |  |  | X
F.8 | Contractual considerations |  |  | X
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | X
G.2 | Price risks |  |  | X
G.3 | Demand risks & replacement products / technologies |  |  | X
G.4 | Value-Analysis Process |  | X
G.5 | Hedging |  | X
G.6 | Competitor analysis |  |  | X
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  | X
H.2 | Assumption register |  |  |  | X
H.3 | Completion risks |  |  |  | X
H.4 | Project Design Criteria |  |  | X
H.5 | Scope of Work Overview |  |  | X
H.6 | Project Schedule |  |  | X
H.7 | Project Cost Estimate |  |  |  | X
H.8 | Investment Studies & Alternatives Assessments |  |  |  | X
H.9 | Key Team Member Coordination |  |  |  | X
H.10 | Evaluation of Compliance Requirements |  |  |  |  | X
H.11 | Lead / Discipline Scope of Work |  |  | X
H.12 | Housing and transport of employees |  |  | X
H.13 | Risk or impact on other projects / divisions |  | X
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | X
I.2 | Site Characteristics Available vs. Required |  |  |  | X
I.3 | Project Scope definition |  | X
I.4 | WBS and WBS Dictionary |  |  | X
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  | X
J.2 | Land use plan post operations |  |  | X
J.3 | Social expectations register |  | X
J.4 | Relocation Action Plan | X
J.5 | Environmental expectations register |  | X
J.6 | Political expectations register |  |  | X
J.7 | Legal compliance register |  |  | X
J.8 | HSE risk register |  | X
J.9 | Community risk register |  |  |  | X
J.10 | Business risk register |  |  |  |  | X
J.11 | Developmental opportunity register |  |  |  | X
J.12 | Sustainability operating plan |  |  |  | X
J.13 | Stakeholder engagement plan |  |  | X
J.14 | Mine closure financial provision plan |  | X
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  | X
J.16 | Social investment plan |  |  |  | X
J.17 | Economic diversification plan |  |  |  |  | X
J.18 | Existing Environmental Conditions |  | X
J.19 | Environmental Process determined
J.20 | Environmental management plan |  | X
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  | X
K.2 | Site Surveys |  |  | X
K.3 | Governing Regulatory Requirements |  | X
K.4 | Utility Sources with Supply Conditions |  | X
K.5 | Fire Protection, emergency procedure & Safety Considerations |  | X
K.6 | Special Water and Waste Treatment Requirements |  |  | X
K.7 | Property Descriptions |  | X
K.8 | Right-of-Way Mapping & Site Issues |  | X
K.9 | Land Rights |  | X
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  | X
L.2 | Civil/Site Design |  |  | X
L.3 | Geotechnical investigation for structures | [5 empty] | X
L.4 | Architectural Design |  |  | X
L.5 | Structural Design |  |  | X
L.6 | Mechanical Design |  |  | X
L.7 | Electrical Design |  |  | X
L.8 | Constructability Analysis |  |  |  | X
L.9 | Process Design |  |  | X
L.10 | Specifications |  |  | X
L.11 | Specialty Items List |  |  | X
L.12 | Instrument Index |  |  |  | X
L.13 | Control Philosophy & systems |  |  |  | X
L.14 | Logic Diagrams |  |  | X
L.15 | IM (information management) |  |  |  | X
L.16 | Control of Access |  |  | X
L.17 | Safety & Hazards |  |  | X
L.18 | Operations/Maintenance |  |  | X
L.19 | Ventilation Engineering | X
L.20 | Rock Engineering | X
L.21 | Water balances |  |  | X
L.22 | Energy efficiency / carbon footprint |  |  | X
L.23 | Tailings handling and storage |  |  | X
L.24 | Stormwater handling / surface hydrology |  |  | X
L.25 | Internal technical audits |  | X
L.26 | External technical audits |  | X
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  | X
M.2 | Design & Material Alternatives Considered/Rejected |  | X
M.3 | Technology trends |  | X
M.4 | Design to capacity |  | X
M.5 | Classes of facillity quality |  | X
M.6 | Energy optimisation |  |  |  | X
M.7 | Waste minimisation |  |  | X
M.8 | 3D / 4D design |  | X
M.9 | Cleaner Production |  | X
M.10 | Innovation and knowledge management planning |  | X
M.11 | Six Sigma |  | X
M.12 | Lean Manufacturing |  | X
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | X
N.2 | Procurement Procedures and Plans |  |  | X
N.3 | Procurement Responsibility Matrix |  |  | X
N.4 | Draft contracts & proforma bidders pack |  |  | X
N.5 | Contracting strategy |  |  | X
N.6 | Procurement operation plan (POP) |  | X
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  | X
O.2 | Deliverables Defined |  |  | X
O.3 | Distribution Matrix |  |  | X
O.4 | Documentation/Deliverables |  |  |  | X
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  | X
P.2 | Project Cost Control |  |  | X
P.3 | Project Schedule Control |  |  | X
P.4 | Risk Management |  |  |  | X
P.5 | Safety, Health, Hygiene and security Management |  | X
P.6 | Environmental Management |  |  | X
P.7 | Project Change Control |  |  |  |  | X
P.8 | Project Audits |  |  |  | X
P.9 | Decision register |  |  |  |  | X
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | X
Q.2 | Project Organization |  |  | X
Q.3 | Responsibility matrix RACI |  |  |  | X
Q.4 | Document Management Plan |  |  | X
Q.5 | Communication management plan |  |  | X
Q.6 | Project Delivery Method |  |  | X
Q.7 | Design / Construction Plan and Approach |  |  | X
Q.8 | Safety Procedures |  |  | X
Q.9 | Intercompany Agreements |  |  | X
Q.10 | Deliverables for Design and Construction |  |  | X
Q.11 | Labour and Skilled resources plan |  |  | X
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  | X
R.2 | Startup Requirements & plans |  |  | X
R.3 | Training Requirements |  |  | X
R.4 | Substantial Completion Requirements |  |  | X
R.5 | Deliverables for Project Commissioning / Closeout |  |  | X
R.6 | Long term supply chain contracts |  |  | X
R.7 | Resourcing & staffing for operation |  |  | X
R.8 | Maintenance schedules |  |  |  | X
R.9 | Critical spares |  |  | X
R.10 | Startup consumables |  |  | X
R.11 | Operational systems and procedures to support each department |  |  |  | X
R.12 | Environmental Management Plan for Operations (EMP) |  | X
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )

## J13
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  | x
A.2 | Project Charter and Mandate |  | x
A.3 | Governance and control (internal approval process defined) |  | x
A.5 | Project Strategy |  |  | x
A.6 | Strategic fit of project in organisation |  |  | x
A.7 | Due diligence |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  |  |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  | x
B.2 | Geo-political risks |  |  | x
B.3 | Fiscal stability agreement |  |  |  | x
B.4 | Social License to Operate |  |  |  | x
B.5 | Violence and terrorism |  |  |  | x
B.6 | Ability to appoint expatriats |  |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  | x
B.9 | Custom duties & logistic routes |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  |  |  | x
C.3 | Business Plan |  |  | x
C.4 | Economic Analysis |  |  | x
C.5 | Affordability / Feasibility |  |  | x
C.6 | Contingencies (Capex & Opex) |  |  | x
C.7 | Basis of Estimate |  |  | x
C.8 | Scenario planning |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  | x
D.3 | Grade engineering / control |  |  | x
D.4 | Prospect drilling standard / guideline |  |  |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  |  |  | x
D.6 | Hydrogeology |  |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  | x
E.2 | Shaft/ramp design & men and material logistics |  |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  | x
E.5 | Life-of-mine plan |  |  | x
E.6 | Waste management plan |  |  | x
E.7 | Ultimate pit limits designed |  |  | x
E.8 | Economic block values determination |  |  | x
E.9 | Beneficiation facilities LOM plan |  |  | x
E.10 | Materials handling LOM plan |  |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | x
F.2 | Productivity / efficiency benchmarks |  |  | x
F.3 | Operating costs |  |  | x
F.4 | Production risks |  |  |  | x
F.5 | Catalogue of operating plans |  |  |  | x
F.6 | Haul roads |  |  | x
F.7 | Transportation strategy |  |  | x
F.8 | Contractual considerations |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  | x
G.2 | Price risks |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  | x
G.4 | Value-Analysis Process |  |  |  | x
G.5 | Hedging |  |  |  | x
G.6 | Competitor analysis |  |  |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  | x
H.2 | Assumption register |  |  | x
H.3 | Completion risks |  |  | x
H.4 | Project Design Criteria |  |  | x
H.5 | Scope of Work Overview |  |  | x
H.6 | Project Schedule |  |  | x
H.7 | Project Cost Estimate |  |  | x
H.8 | Investment Studies & Alternatives Assessments |  |  |  | x
H.9 | Key Team Member Coordination |  |  | x
H.10 | Evaluation of Compliance Requirements |  |  | x
H.11 | Lead / Discipline Scope of Work |  |  | x
H.12 | Housing and transport of employees |  |  | x
H.13 | Risk or impact on other projects / divisions |  |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | x
I.2 | Site Characteristics Available vs. Required |  | x
I.3 | Project Scope definition |  | x
I.4 | WBS and WBS Dictionary |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  |  | x
J.2 | Land use plan post operations |  |  |  | x
J.3 | Social expectations register |  |  |  |  | x
J.4 | Relocation Action Plan |  |  | x
J.5 | Environmental expectations register |  |  |  | x
J.6 | Political expectations register |  |  |  |  | x
J.7 | Legal compliance register |  |  | x
J.8 | HSE risk register |  |  | x
J.9 | Community risk register |  |  | x
J.10 | Business risk register |  | x
J.11 | Developmental opportunity register |  |  |  | x
J.12 | Sustainability operating plan |  |  | x
J.13 | Stakeholder engagement plan |  |  |  | x
J.14 | Mine closure financial provision plan |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  | x
J.16 | Social investment plan |  |  | x
J.17 | Economic diversification plan |  |  |  | x
J.18 | Existing Environmental Conditions |  | x
J.19 | Environmental Process determined |  |  | x
J.20 | Environmental management plan |  |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  | x
K.2 | Site Surveys |  |  |  | x
K.3 | Governing Regulatory Requirements |  |  | x
K.4 | Utility Sources with Supply Conditions |  |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  | x
K.6 | Special Water and Waste Treatment Requirements |  |  | x
K.7 | Property Descriptions |  | x
K.8 | Right-of-Way Mapping & Site Issues |  | x
K.9 | Land Rights |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  | x
L.2 | Civil/Site Design |  |  |  | x
L.3 | Geotechnical investigation for structures |  | x
L.4 | Architectural Design |  |  |  | x
L.5 | Structural Design |  |  |  | x
L.6 | Mechanical Design |  |  |  | x
L.7 | Electrical Design |  |  |  | x
L.8 | Constructability Analysis |  |  |  | x
L.9 | Process Design |  |  | x
L.10 | Specifications |  |  |  |  | x
L.11 | Specialty Items List |  |  |  | x
L.12 | Instrument Index |  |  |  | x
L.13 | Control Philosophy & systems |  |  |  | x
L.14 | Logic Diagrams |  |  |  | x
L.15 | IM (information management) |  |  |  | x
L.16 | Control of Access |  |  |  |  | x
L.17 | Safety & Hazards |  |  |  | x
L.18 | Operations/Maintenance |  |  |  |  | x
L.19 | Ventilation Engineering |  |  |  | x
L.20 | Rock Engineering |  |  | x
L.21 | Water balances |  |  | x
L.22 | Energy efficiency / carbon footprint |  |  |  | x
L.23 | Tailings handling and storage |  |  |  | x
L.24 | Stormwater handling / surface hydrology |  |  |  | x
L.25 | Internal technical audits |  |  |  | x
L.26 | External technical audits |  |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  |  | x
M.3 | Technology trends |  |  | x
M.4 | Design to capacity |  |  | x
M.5 | Classes of facillity quality |  |  |  |  | x
M.6 | Energy optimisation |  |  |  |  | x
M.7 | Waste minimisation |  |  |  |  | x
M.8 | 3D / 4D design |  |  | x
M.9 | Cleaner Production |  |  |  | x
M.10 | Innovation and knowledge management planning |  |  |  | x
M.11 | Six Sigma | x
M.12 | Lean Manufacturing | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | x
N.2 | Procurement Procedures and Plans |  |  | x
N.3 | Procurement Responsibility Matrix |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  | x
N.5 | Contracting strategy |  | x
N.6 | Procurement operation plan (POP) |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  | x
O.2 | Deliverables Defined |  |  | x
O.3 | Distribution Matrix |  |  | x
O.4 | Documentation/Deliverables |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  | x
P.2 | Project Cost Control |  |  | x
P.3 | Project Schedule Control |  |  | x
P.4 | Risk Management |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  | x
P.6 | Environmental Management |  |  | x
P.7 | Project Change Control |  | x
P.8 | Project Audits |  |  | x
P.9 | Decision register |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | x
Q.2 | Project Organization |  | x
Q.3 | Responsibility matrix RACI |  | x
Q.4 | Document Management Plan |  | x
Q.5 | Communication management plan |  | x
Q.6 | Project Delivery Method |  | x
Q.7 | Design / Construction Plan and Approach |  |  | x
Q.8 | Safety Procedures |  |  | x
Q.9 | Intercompany Agreements | x
Q.10 | Deliverables for Design and Construction |  | x
Q.11 | Labour and Skilled resources plan |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  |  | x
R.2 | Startup Requirements & plans |  |  |  |  | x
R.3 | Training Requirements |  |  |  |  | x
R.4 | Substantial Completion Requirements |  |  |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  |  | x
R.6 | Long term supply chain contracts |  |  |  |  | x
R.7 | Resourcing & staffing for operation |  |  |  | x
R.8 | Maintenance schedules |  |  |  |  | x
R.9 | Critical spares |  |  |  |  | x
R.10 | Startup consumables |  |  |  |  | x
R.11 | Operational systems and procedures to support each department |  |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  |  |  |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J14
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | X
A.2 | Project Charter and Mandate |  | X
A.3 | Governance and control (internal approval process defined) |  |  | X
A.5 | Project Strategy |  |  | X
A.6 | Strategic fit of project in organisation |  |  |  | X
A.7 | Due diligence |  |  | X
A.8 | Partnership, joint ventures and shareholder buy in |  |  |  | X
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  |  | X
B.2 | Geo-political risks |  |  |  | X
B.3 | Fiscal stability agreement |  |  |  | X
B.4 | Social License to Operate |  |  |  | X
B.5 | Violence and terrorism |  |  |  | X
B.6 | Ability to appoint expatriats |  |  |  |  | X
B.7 | Procurement of local and foreign materials, services and equipment |  |  |  | X
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  | X
B.9 | Custom duties & logistic routes |  |  | X
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | X
C.2 | Financing secured (Internal, external, equity, debt) |  | X
C.3 | Business Plan |  |  | X
C.4 | Economic Analysis |  |  | X
C.5 | Affordability / Feasibility |  |  |  | X
C.6 | Contingencies (Capex & Opex) |  |  | X
C.7 | Basis of Estimate |  |  | X
C.8 | Scenario planning |  |  |  | X
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | X
D.2 | Reserve risks (including modifying factors) |  |  | X
D.3 | Grade engineering / control |  |  | X
D.4 | Prospect drilling standard / guideline |  |  | X
D.5 | Geological conditions (Geological model, structure, qualities) |  |  | X
D.6 | Hydrogeology |  |  | X
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  |  | X
E.2 | Shaft/ramp design & men and material logistics |  |  | X
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  | X
E.4 | Equipment selection to fit geological conditions and mining method |  |  | X
E.5 | Life-of-mine plan |  |  |  | X
E.6 | Waste management plan |  |  |  | X
E.7 | Ultimate pit limits designed |  |  |  | X
E.8 | Economic block values determination |  |  |  | X
E.9 | Beneficiation facilities LOM plan |  |  |  | X
E.10 | Materials handling LOM plan |  |  |  | X
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  |  | X
F.2 | Productivity / efficiency benchmarks |  |  |  | X
F.3 | Operating costs |  |  | X
F.4 | Production risks |  |  |  | X
F.5 | Catalogue of operating plans |  |  |  | X
F.6 | Haul roads |  |  | X
F.7 | Transportation strategy |  |  | X
F.8 | Contractual considerations |  |  | X
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  | X
G.2 | Price risks |  |  | X
G.3 | Demand risks & replacement products / technologies |  |  |  | X
G.4 | Value-Analysis Process |  |  |  | X
G.5 | Hedging |  |  | X
G.6 | Competitor analysis |  |  |  | X
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  | X
H.2 | Assumption register |  |  |  | X
H.3 | Completion risks |  |  |  | X
H.4 | Project Design Criteria |  |  | X
H.5 | Scope of Work Overview |  |  | X
H.6 | Project Schedule |  |  | X
H.7 | Project Cost Estimate |  | X
H.8 | Investment Studies & Alternatives Assessments |  |  |  | X
H.9 | Key Team Member Coordination |  |  | X
H.10 | Evaluation of Compliance Requirements |  |  | X
H.11 | Lead / Discipline Scope of Work |  |  | X
H.12 | Housing and transport of employees |  |  |  | X
H.13 | Risk or impact on other projects / divisions |  |  |  | X
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  | X
I.2 | Site Characteristics Available vs. Required |  |  |  | X
I.3 | Project Scope definition |  | X
I.4 | WBS and WBS Dictionary |  |  | X
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  |  |  | X
J.2 | Land use plan post operations |  |  |  |  | X
J.3 | Social expectations register |  |  |  |  | X
J.4 | Relocation Action Plan |  |  |  | X
J.5 | Environmental expectations register |  |  |  | X
J.6 | Political expectations register |  |  |  |  | X
J.7 | Legal compliance register |  |  |  | X
J.8 | HSE risk register |  |  |  | X
J.9 | Community risk register |  |  |  | X
J.10 | Business risk register |  |  |  | X
J.11 | Developmental opportunity register |  |  |  | X
J.12 | Sustainability operating plan |  |  |  | X
J.13 | Stakeholder engagement plan |  |  | X
J.14 | Mine closure financial provision plan |  |  |  | X
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  | X
J.16 | Social investment plan |  |  |  | X
J.17 | Economic diversification plan |  |  |  | X
J.18 | Existing Environmental Conditions |  |  | X
J.19 | Environmental Process determined |  |  | X
J.20 | Environmental management plan |  |  | X
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  | X
K.2 | Site Surveys |  |  |  | X
K.3 | Governing Regulatory Requirements |  |  | X
K.4 | Utility Sources with Supply Conditions |  |  | X
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  |  | X
K.6 | Special Water and Waste Treatment Requirements |  |  | X
K.7 | Property Descriptions |  |  | X
K.8 | Right-of-Way Mapping & Site Issues |  |  | X
K.9 | Land Rights |  | X
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  | X
L.2 | Civil/Site Design |  |  | X
L.3 | Geotechnical investigation for structures |  |  |  | X
L.4 | Architectural Design |  |  | X
L.5 | Structural Design |  |  | X
L.6 | Mechanical Design |  |  | X
L.7 | Electrical Design |  |  | X
L.8 | Constructability Analysis |  |  | X
L.9 | Process Design |  | X
L.10 | Specifications |  |  | X
L.11 | Specialty Items List |  |  | X
L.12 | Instrument Index |  |  | X
L.13 | Control Philosophy & systems |  |  | X
L.14 | Logic Diagrams |  |  | X
L.15 | IM (information management) |  |  |  | X
L.16 | Control of Access |  |  |  | X
L.17 | Safety & Hazards |  |  | X
L.18 | Operations/Maintenance |  |  | X
L.19 | Ventilation Engineering |  |  | X
L.20 | Rock Engineering |  |  |  | X
L.21 | Water balances |  |  | X
L.22 | Energy efficiency / carbon footprint |  |  | X
L.23 | Tailings handling and storage |  |  |  | X
L.24 | Stormwater handling / surface hydrology |  |  | X
L.25 | Internal technical audits |  |  | X
L.26 | External technical audits |  |  | X
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  |  | X
M.2 | Design & Material Alternatives Considered/Rejected |  |  | X
M.3 | Technology trends |  |  |  | X
M.4 | Design to capacity |  | X
M.5 | Classes of facillity quality |  |  | X
M.6 | Energy optimisation |  |  |  | X
M.7 | Waste minimisation |  |  | X
M.8 | 3D / 4D design |  |  |  | X
M.9 | Cleaner Production |  |  |  | X
M.10 | Innovation and knowledge management planning |  |  | X
M.11 | Six Sigma |  |  |  | X
M.12 | Lean Manufacturing |  |  | X
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | X
N.2 | Procurement Procedures and Plans |  |  | X
N.3 | Procurement Responsibility Matrix |  |  | X
N.4 | Draft contracts & proforma bidders pack |  |  | X
N.5 | Contracting strategy |  |  |  | X
N.6 | Procurement operation plan (POP) |  |  | X
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  |  |  | X
O.2 | Deliverables Defined |  |  | X
O.3 | Distribution Matrix |  |  |  | X
O.4 | Documentation/Deliverables |  |  | X
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  | X
P.2 | Project Cost Control |  |  | X
P.3 | Project Schedule Control |  |  | X
P.4 | Risk Management |  |  |  | X
P.5 | Safety, Health, Hygiene and security Management |  |  | X
P.6 | Environmental Management |  |  |  | X
P.7 | Project Change Control |  |  | X
P.8 | Project Audits |  |  |  | X
P.9 | Decision register |  |  |  | X
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | X
Q.2 | Project Organization |  |  | X
Q.3 | Responsibility matrix RACI |  |  | X
Q.4 | Document Management Plan |  |  | X
Q.5 | Communication management plan |  |  | X
Q.6 | Project Delivery Method |  |  | X
Q.7 | Design / Construction Plan and Approach |  |  | X
Q.8 | Safety Procedures |  |  |  | X
Q.9 | Intercompany Agreements |  |  |  | X
Q.10 | Deliverables for Design and Construction |  |  | X
Q.11 | Labour and Skilled resources plan |  |  |  | X
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  | X
R.2 | Startup Requirements & plans |  |  | X
R.3 | Training Requirements |  |  | X
R.4 | Substantial Completion Requirements |  |  | X
R.5 | Deliverables for Project Commissioning / Closeout |  |  | X
R.6 | Long term supply chain contracts |  |  |  | X
R.7 | Resourcing & staffing for operation |  |  |  | X
R.8 | Maintenance schedules |  |  | X
R.9 | Critical spares |  |  | X
R.10 | Startup consumables |  |  |  | X
R.11 | Operational systems and procedures to support each department |  |  |  | X
R.12 | Environmental Management Plan for Operations (EMP) |  |  |  | X
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J15
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  | x
A.2 | Project Charter and Mandate |  |  |  | x
A.3 | Governance and control (internal approval process defined) |  |  |  | x
A.5 | Project Strategy |  |  | x
A.6 | Strategic fit of project in organisation |  |  |  | x
A.7 | Due diligence |  |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  | x
B.2 | Geo-political risks |  | x
B.3 | Fiscal stability agreement |  |  | x
B.4 | Social License to Operate |  |  | x
B.5 | Violence and terrorism |  |  | x
B.6 | Ability to appoint expatriats |  |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  | x
B.9 | Custom duties & logistic routes |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  |  | x
C.3 | Business Plan |  |  | x
C.4 | Economic Analysis |  |  | x
C.5 | Affordability / Feasibility |  |  | x
C.6 | Contingencies (Capex & Opex) |  |  | x
C.7 | Basis of Estimate |  |  |  | x
C.8 | Scenario planning |  |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  |  | x
D.3 | Grade engineering / control |  |  |  | x
D.4 | Prospect drilling standard / guideline |  |  |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  |  |  | x
D.6 | Hydrogeology |  |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  |  | x
E.2 | Shaft/ramp design & men and material logistics |  |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  |  | x
E.5 | Life-of-mine plan |  |  |  | x
E.6 | Waste management plan |  |  |  | x
E.7 | Ultimate pit limits designed |  |  | x
E.8 | Economic block values determination |  |  | x
E.9 | Beneficiation facilities LOM plan |  |  | x
E.10 | Materials handling LOM plan |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  |  | x
F.2 | Productivity / efficiency benchmarks |  |  | x
F.3 | Operating costs |  |  |  | x
F.4 | Production risks |  |  |  | x
F.5 | Catalogue of operating plans |  |  | x
F.6 | Haul roads |  |  | x
F.7 | Transportation strategy |  |  | x
F.8 | Contractual considerations |  |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  |  | x
G.2 | Price risks |  |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  |  | x
G.4 | Value-Analysis Process |  |  | x
G.5 | Hedging |  |  |  | x
G.6 | Competitor analysis | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  | x
H.2 | Assumption register |  |  |  | x
H.3 | Completion risks |  |  |  | x
H.4 | Project Design Criteria |  |  |  | x
H.5 | Scope of Work Overview |  |  |  | x
H.6 | Project Schedule |  |  |  |  | x
H.7 | Project Cost Estimate |  |  | x
H.8 | Investment Studies & Alternatives Assessments | x
H.9 | Key Team Member Coordination |  |  |  | x
H.10 | Evaluation of Compliance Requirements |  |  |  | x
H.11 | Lead / Discipline Scope of Work |  |  | x
H.12 | Housing and transport of employees |  |  | x
H.13 | Risk or impact on other projects / divisions |  |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  | x
I.2 | Site Characteristics Available vs. Required |  |  | x
I.3 | Project Scope definition |  |  |  | x
I.4 | WBS and WBS Dictionary |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  |  | x
J.2 | Land use plan post operations |  |  |  | x
J.3 | Social expectations register |  |  | x
J.4 | Relocation Action Plan | x
J.5 | Environmental expectations register |  |  |  | x
J.6 | Political expectations register |  |  |  | x
J.7 | Legal compliance register |  |  |  | x
J.8 | HSE risk register |  |  |  | x
J.9 | Community risk register |  |  |  | x
J.10 | Business risk register |  |  |  | x
J.11 | Developmental opportunity register |  |  |  | x
J.12 | Sustainability operating plan |  |  |  | x
J.13 | Stakeholder engagement plan |  |  | x
J.14 | Mine closure financial provision plan |  |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  | x
J.16 | Social investment plan |  |  | x
J.17 | Economic diversification plan |  |  | x
J.18 | Existing Environmental Conditions |  |  | x
J.19 | Environmental Process determined |  |  | x
J.20 | Environmental management plan |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  | x
K.2 | Site Surveys |  |  | x
K.3 | Governing Regulatory Requirements |  |  | x
K.4 | Utility Sources with Supply Conditions |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  | x
K.6 | Special Water and Waste Treatment Requirements |  |  |  |  | x
K.7 | Property Descriptions |  |  |  | x
K.8 | Right-of-Way Mapping & Site Issues |  |  | x
K.9 | Land Rights |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  | x
L.2 | Civil/Site Design |  |  | x
L.3 | Geotechnical investigation for structures |  |  | x
L.4 | Architectural Design |  |  | x
L.5 | Structural Design |  |  | x
L.6 | Mechanical Design |  |  |  | x
L.7 | Electrical Design |  |  |  | x
L.8 | Constructability Analysis |  |  | x
L.9 | Process Design |  |  |  | x
L.10 | Specifications |  |  | x
L.11 | Specialty Items List |  |  |  | x
L.12 | Instrument Index |  |  |  | x
L.13 | Control Philosophy & systems |  |  |  | x
L.14 | Logic Diagrams |  |  |  | x
L.15 | IM (information management) |  |  |  | x
L.16 | Control of Access |  |  |  | x
L.17 | Safety & Hazards |  |  | x
L.18 | Operations/Maintenance |  |  |  | x
L.19 | Ventilation Engineering |  |  |  | x
L.20 | Rock Engineering |  |  |  | x
L.21 | Water balances |  |  |  |  | x
L.22 | Energy efficiency / carbon footprint |  |  |  | x
L.23 | Tailings handling and storage |  |  |  |  | x
L.24 | Stormwater handling / surface hydrology |  |  |  |  | x
L.25 | Internal technical audits |  |  | x
L.26 | External technical audits |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  | x
M.3 | Technology trends |  |  |  | x
M.4 | Design to capacity |  |  | x
M.5 | Classes of facillity quality |  |  |  | x
M.6 | Energy optimisation |  |  |  | x
M.7 | Waste minimisation |  |  |  | x
M.8 | 3D / 4D design |  |  |  | x
M.9 | Cleaner Production |  |  |  | x
M.10 | Innovation and knowledge management planning |  |  | x
M.11 | Six Sigma |  |  |  | x
M.12 | Lean Manufacturing |  |  |  | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  |  | x
N.2 | Procurement Procedures and Plans |  |  | x
N.3 | Procurement Responsibility Matrix |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  | x
N.5 | Contracting strategy |  | x
N.6 | Procurement operation plan (POP) |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  |  | x
O.2 | Deliverables Defined |  |  | x
O.3 | Distribution Matrix |  |  | x
O.4 | Documentation/Deliverables |  |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  | x
P.2 | Project Cost Control |  |  | x
P.3 | Project Schedule Control |  |  |  | x
P.4 | Risk Management |  |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  | x
P.6 | Environmental Management |  |  | x
P.7 | Project Change Control |  |  | x
P.8 | Project Audits |  |  |  | x
P.9 | Decision register |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | x
Q.2 | Project Organization |  |  | x
Q.3 | Responsibility matrix RACI |  |  | x
Q.4 | Document Management Plan |  |  | x
Q.5 | Communication management plan |  |  | x
Q.6 | Project Delivery Method |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  | x
Q.8 | Safety Procedures |  |  | x
Q.9 | Intercompany Agreements |  | x
Q.10 | Deliverables for Design and Construction |  |  | x
Q.11 | Labour and Skilled resources plan |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  | x
R.2 | Startup Requirements & plans |  |  |  | x
R.3 | Training Requirements |  |  |  | x
R.4 | Substantial Completion Requirements |  |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  |  | x
R.6 | Long term supply chain contracts |  |  |  | x
R.7 | Resourcing & staffing for operation |  |  |  | x
R.8 | Maintenance schedules |  |  |  | x
R.9 | Critical spares |  |  |  | x
R.10 | Startup consumables |  |  |  | x
R.11 | Operational systems and procedures to support each department |  |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  |  |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J16
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | x
A.2 | Project Charter and Mandate |  | x
A.3 | Governance and control (internal approval process defined) |  |  |  | x
A.5 | Project Strategy |  |  | x
A.6 | Strategic fit of project in organisation |  | x
A.7 | Due diligence |  |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  |  |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues | x
B.2 | Geo-political risks | x
B.3 | Fiscal stability agreement | x
B.4 | Social License to Operate |  |  | x
B.5 | Violence and terrorism |  |  |  | x
B.6 | Ability to appoint expatriats |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  | x
B.9 | Custom duties & logistic routes | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  | x
C.3 | Business Plan |  |  | x
C.4 | Economic Analysis |  |  |  |  | x
C.5 | Affordability / Feasibility |  | x
C.6 | Contingencies (Capex & Opex) |  |  | x
C.7 | Basis of Estimate |  |  |  | x
C.8 | Scenario planning | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  | x
D.3 | Grade engineering / control |  |  |  | x
D.4 | Prospect drilling standard / guideline |  |  |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  |  |  | x
D.6 | Hydrogeology |  |  |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  |  | x
E.2 | Shaft/ramp design & men and material logistics |  |  |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  |  |  | x
E.5 | Life-of-mine plan |  |  | x
E.6 | Waste management plan |  |  |  | x
E.7 | Ultimate pit limits designed |  |  |  | x
E.8 | Economic block values determination |  |  |  | x
E.9 | Beneficiation facilities LOM plan |  |  |  | x
E.10 | Materials handling LOM plan |  |  |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  | x
F.2 | Productivity / efficiency benchmarks |  |  | x
F.3 | Operating costs |  |  |  | x
F.4 | Production risks |  |  |  | x
F.5 | Catalogue of operating plans |  |  |  |  | x
F.6 | Haul roads |  |  |  | x
F.7 | Transportation strategy |  |  |  | x
F.8 | Contractual considerations |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  | x
G.2 | Price risks |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  |  | x
G.4 | Value-Analysis Process |  |  |  | x
G.5 | Hedging |  |  |  |  | x
G.6 | Competitor analysis |  |  |  |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  | x
H.2 | Assumption register |  |  |  | x
H.3 | Completion risks |  |  |  | x
H.4 | Project Design Criteria |  |  |  | x
H.5 | Scope of Work Overview |  |  |  | x
H.6 | Project Schedule |  | x
H.7 | Project Cost Estimate |  |  | x
H.8 | Investment Studies & Alternatives Assessments |  |  |  | x
H.9 | Key Team Member Coordination |  | x
H.10 | Evaluation of Compliance Requirements |  |  |  | x
H.11 | Lead / Discipline Scope of Work |  |  | x
H.12 | Housing and transport of employees |  |  | x
H.13 | Risk or impact on other projects / divisions |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  | x
I.2 | Site Characteristics Available vs. Required |  |  |  | x
I.3 | Project Scope definition |  |  | x
I.4 | WBS and WBS Dictionary |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  |  | x
J.2 | Land use plan post operations |  |  |  | x
J.3 | Social expectations register |  |  |  |  | x
J.4 | Relocation Action Plan |  |  |  |  | x
J.5 | Environmental expectations register |  |  |  | x
J.6 | Political expectations register |  |  |  |  | x
J.7 | Legal compliance register |  |  | x
J.8 | HSE risk register |  |  | x
J.9 | Community risk register |  |  |  |  | x
J.10 | Business risk register |  |  |  | x
J.11 | Developmental opportunity register |  |  |  |  | x
J.12 | Sustainability operating plan |  |  |  |  | x
J.13 | Stakeholder engagement plan |  |  | x
J.14 | Mine closure financial provision plan |  |  |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  |  | x
J.16 | Social investment plan |  |  |  |  | x
J.17 | Economic diversification plan |  |  |  |  | x
J.18 | Existing Environmental Conditions |  |  |  | x
J.19 | Environmental Process determined |  |  |  | x
J.20 | Environmental management plan |  |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  | x
K.2 | Site Surveys |  |  | x
K.3 | Governing Regulatory Requirements |  |  |  | x
K.4 | Utility Sources with Supply Conditions |  |  |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  |  | x
K.6 | Special Water and Waste Treatment Requirements |  |  | x
K.7 | Property Descriptions |  |  |  | x
K.8 | Right-of-Way Mapping & Site Issues |  |  |  |  | x
K.9 | Land Rights |  |  |  |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  | x
L.2 | Civil/Site Design |  |  | x
L.3 | Geotechnical investigation for structures |  |  | x
L.4 | Architectural Design |  |  |  | x
L.5 | Structural Design |  |  | x
L.6 | Mechanical Design |  |  | x
L.7 | Electrical Design |  |  | x
L.8 | Constructability Analysis |  |  | x
L.9 | Process Design |  |  | x
L.10 | Specifications |  |  |  | x
L.11 | Specialty Items List |  |  |  |  | x
L.12 | Instrument Index |  |  |  |  | x
L.13 | Control Philosophy & systems |  |  | x
L.14 | Logic Diagrams |  |  |  | x
L.15 | IM (information management) |  |  |  |  | x
L.16 | Control of Access |  |  |  | x
L.17 | Safety & Hazards |  |  | x
L.18 | Operations/Maintenance |  |  | x
L.19 | Ventilation Engineering |  |  |  | x
L.20 | Rock Engineering |  |  |  |  | x
L.21 | Water balances |  |  |  |  | x
L.22 | Energy efficiency / carbon footprint |  |  |  |  | x
L.23 | Tailings handling and storage |  |  | x
L.24 | Stormwater handling / surface hydrology |  |  |  | x
L.25 | Internal technical audits |  |  |  |  | x
L.26 | External technical audits | [5 empty] | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  |  |  | x
M.3 | Technology trends |  |  |  |  | x
M.4 | Design to capacity |  |  |  |  | x
M.5 | Classes of facillity quality |  |  |  |  | x
M.6 | Energy optimisation |  |  |  | x
M.7 | Waste minimisation |  |  | x
M.8 | 3D / 4D design |  |  |  |  | x
M.9 | Cleaner Production |  |  |  |  | x
M.10 | Innovation and knowledge management planning |  |  |  |  | x
M.11 | Six Sigma | x
M.12 | Lean Manufacturing | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  |  | x
N.2 | Procurement Procedures and Plans |  |  |  | x
N.3 | Procurement Responsibility Matrix |  |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  |  | x
N.5 | Contracting strategy |  |  | x
N.6 | Procurement operation plan (POP) |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  |  |  | x
O.2 | Deliverables Defined |  |  |  | x
O.3 | Distribution Matrix |  |  |  |  | x
O.4 | Documentation/Deliverables |  |  |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  |  | x
P.2 | Project Cost Control |  | x
P.3 | Project Schedule Control |  |  | x
P.4 | Risk Management |  |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  | x
P.6 | Environmental Management |  |  | x
P.7 | Project Change Control |  | x
P.8 | Project Audits |  |  |  |  | x
P.9 | Decision register |  |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | x
Q.2 | Project Organization |  | x
Q.3 | Responsibility matrix RACI |  |  | x
Q.4 | Document Management Plan |  |  |  |  | x
Q.5 | Communication management plan |  |  |  |  | x
Q.6 | Project Delivery Method |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  | x
Q.8 | Safety Procedures |  |  | x
Q.9 | Intercompany Agreements |  |  |  | x
Q.10 | Deliverables for Design and Construction |  |  | x
Q.11 | Labour and Skilled resources plan |  |  |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  | x
R.2 | Startup Requirements & plans |  |  | x
R.3 | Training Requirements |  |  |  |  | x
R.4 | Substantial Completion Requirements |  |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  | x
R.6 | Long term supply chain contracts |  |  | x
R.7 | Resourcing & staffing for operation |  |  |  | x
R.8 | Maintenance schedules |  |  |  |  | x
R.9 | Critical spares |  |  | x
R.10 | Startup consumables |  |  |  | x
R.11 | Operational systems and procedures to support each department |  |  |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  |  |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J17
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | X
A.2 | Project Charter and Mandate |  |  |  | X
A.3 | Governance and control (internal approval process defined) |  |  | X
A.5 | Project Strategy |  |  |  | X
A.6 | Strategic fit of project in organisation |  |  | X
A.7 | Due diligence |  |  | X
A.8 | Partnership, joint ventures and shareholder buy in |  | X
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  |  |  | X
B.2 | Geo-political risks |  |  |  | X
B.3 | Fiscal stability agreement |  |  |  | X
B.4 | Social License to Operate |  |  |  |  | X
B.5 | Violence and terrorism |  |  |  |  | X
B.6 | Ability to appoint expatriats |  |  |  | X
B.7 | Procurement of local and foreign materials, services and equipment |  |  | X
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  | X
B.9 | Custom duties & logistic routes |  |  | X
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  |  |  | X
C.2 | Financing secured (Internal, external, equity, debt) |  |  | X
C.3 | Business Plan |  |  | X
C.4 | Economic Analysis |  |  | X
C.5 | Affordability / Feasibility |  |  | X
C.6 | Contingencies (Capex & Opex) |  |  |  |  | X
C.7 | Basis of Estimate |  |  |  | X
C.8 | Scenario planning |  |  |  | X
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | X
D.2 | Reserve risks (including modifying factors) |  |  | X
D.3 | Grade engineering / control |  |  | X
D.4 | Prospect drilling standard / guideline |  |  | X
D.5 | Geological conditions (Geological model, structure, qualities) |  |  | X
D.6 | Hydrogeology |  |  | X
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  | X
E.2 | Shaft/ramp design & men and material logistics |  |  | X
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  | X
E.4 | Equipment selection to fit geological conditions and mining method |  |  | X
E.5 | Life-of-mine plan |  |  | X
E.6 | Waste management plan |  |  | X
E.7 | Ultimate pit limits designed |  |  | X
E.8 | Economic block values determination |  |  | X
E.9 | Beneficiation facilities LOM plan |  |  | X
E.10 | Materials handling LOM plan |  |  | X
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  | X
F.2 | Productivity / efficiency benchmarks |  |  | X
F.3 | Operating costs |  |  | X
F.4 | Production risks |  |  | X
F.5 | Catalogue of operating plans |  |  | X
F.6 | Haul roads |  |  | X
F.7 | Transportation strategy |  |  | X
F.8 | Contractual considerations |  |  | X
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  | X
G.2 | Price risks |  |  |  | X
G.3 | Demand risks & replacement products / technologies |  |  |  | X
G.4 | Value-Analysis Process |  |  |  | X
G.5 | Hedging |  |  |  | X
G.6 | Competitor analysis |  |  |  |  | X
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  |  |  | X
H.2 | Assumption register |  |  |  | X
H.3 | Completion risks |  |  |  |  | X
H.4 | Project Design Criteria |  |  |  |  | X
H.5 | Scope of Work Overview |  |  |  |  | X
H.6 | Project Schedule |  |  |  |  | X
H.7 | Project Cost Estimate |  |  |  |  | X
H.8 | Investment Studies & Alternatives Assessments |  |  |  | X
H.9 | Key Team Member Coordination |  |  | X
H.10 | Evaluation of Compliance Requirements |  |  | X
H.11 | Lead / Discipline Scope of Work |  |  | X
H.12 | Housing and transport of employees |  |  | X
H.13 | Risk or impact on other projects / divisions |  |  | X
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  |  | X
I.2 | Site Characteristics Available vs. Required |  |  |  | X
I.3 | Project Scope definition |  |  |  | X
I.4 | WBS and WBS Dictionary |  |  |  | X
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  |  | X
J.2 | Land use plan post operations |  |  |  | X
J.3 | Social expectations register |  |  |  | X
J.4 | Relocation Action Plan |  |  |  | X
J.5 | Environmental expectations register |  |  |  | X
J.6 | Political expectations register |  |  |  | X
J.7 | Legal compliance register |  |  |  | X
J.8 | HSE risk register |  |  |  | X
J.9 | Community risk register |  |  |  | X
J.10 | Business risk register |  |  |  | X
J.11 | Developmental opportunity register |  |  |  |  | X
J.12 | Sustainability operating plan |  |  |  |  | X
J.13 | Stakeholder engagement plan |  |  |  | X
J.14 | Mine closure financial provision plan |  |  |  | X
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  | X
J.16 | Social investment plan |  |  |  |  | X
J.17 | Economic diversification plan |  |  |  |  | X
J.18 | Existing Environmental Conditions |  |  |  | X
J.19 | Environmental Process determined |  |  |  | X
J.20 | Environmental management plan |  |  |  | X
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  |  | X
K.2 | Site Surveys |  |  |  | X
K.3 | Governing Regulatory Requirements |  |  |  | X
K.4 | Utility Sources with Supply Conditions |  |  |  | X
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  |  | X
K.6 | Special Water and Waste Treatment Requirements |  |  |  | X
K.7 | Property Descriptions |  |  |  | X
K.8 | Right-of-Way Mapping & Site Issues |  |  |  | X
K.9 | Land Rights |  |  |  | X
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  |  |  | X
L.2 | Civil/Site Design |  |  |  | X
L.3 | Geotechnical investigation for structures |  |  |  | X
L.4 | Architectural Design |  |  |  | X
L.5 | Structural Design |  |  |  | X
L.6 | Mechanical Design |  |  |  | X
L.7 | Electrical Design |  |  |  | X
L.8 | Constructability Analysis |  |  |  | X
L.9 | Process Design |  |  | X
L.10 | Specifications |  |  |  | X
L.11 | Specialty Items List |  |  | X
L.12 | Instrument Index |  |  | X
L.13 | Control Philosophy & systems |  |  | X
L.14 | Logic Diagrams |  |  | X
L.15 | IM (information management) |  |  |  | X
L.16 | Control of Access |  |  |  | X
L.17 | Safety & Hazards |  |  |  | X
L.18 | Operations/Maintenance |  |  |  | X
L.19 | Ventilation Engineering | X
L.20 | Rock Engineering |  |  | X
L.21 | Water balances |  |  | X
L.22 | Energy efficiency / carbon footprint |  |  |  | X
L.23 | Tailings handling and storage |  |  | X
L.24 | Stormwater handling / surface hydrology |  |  |  | X
L.25 | Internal technical audits |  |  |  | X
L.26 | External technical audits |  |  | X
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  |  | X
M.2 | Design & Material Alternatives Considered/Rejected |  |  |  | X
M.3 | Technology trends |  |  |  | X
M.4 | Design to capacity |  |  |  | X
M.5 | Classes of facillity quality |  |  |  | X
M.6 | Energy optimisation |  |  |  | X
M.7 | Waste minimisation |  |  |  | X
M.8 | 3D / 4D design |  |  |  | X
M.9 | Cleaner Production |  |  |  | X
M.10 | Innovation and knowledge management planning |  |  |  | X
M.11 | Six Sigma |  |  |  | X
M.12 | Lean Manufacturing |  |  |  | X
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  |  |  | X
N.2 | Procurement Procedures and Plans |  |  |  | X
N.3 | Procurement Responsibility Matrix |  |  | X
N.4 | Draft contracts & proforma bidders pack |  |  |  | X
N.5 | Contracting strategy |  |  |  | X
N.6 | Procurement operation plan (POP) |  |  |  | X
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  |  | X
O.2 | Deliverables Defined |  |  |  | X
O.3 | Distribution Matrix |  |  |  | X
O.4 | Documentation/Deliverables |  |  |  | X
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  |  | X
P.2 | Project Cost Control |  |  |  | X
P.3 | Project Schedule Control |  |  |  | X
P.4 | Risk Management |  |  |  | X
P.5 | Safety, Health, Hygiene and security Management |  |  |  | X
P.6 | Environmental Management |  |  |  | X
P.7 | Project Change Control |  |  |  | X
P.8 | Project Audits |  |  | X
P.9 | Decision register |  |  |  | X
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  |  | X
Q.2 | Project Organization |  |  |  | X
Q.3 | Responsibility matrix RACI |  |  |  | X
Q.4 | Document Management Plan |  |  |  | X
Q.5 | Communication management plan |  |  |  | X
Q.6 | Project Delivery Method |  |  |  | X
Q.7 | Design / Construction Plan and Approach |  |  |  | X
Q.8 | Safety Procedures |  |  |  | X
Q.9 | Intercompany Agreements |  |  |  | X
Q.10 | Deliverables for Design and Construction |  |  |  | X
Q.11 | Labour and Skilled resources plan |  |  |  |  | X
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  |  | X
R.2 | Startup Requirements & plans |  |  |  |  | X
R.3 | Training Requirements |  |  |  |  | X
R.4 | Substantial Completion Requirements |  |  |  | X
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  | X
R.6 | Long term supply chain contracts |  |  |  |  | X
R.7 | Resourcing & staffing for operation |  |  |  |  | X
R.8 | Maintenance schedules |  |  |  |  | X
R.9 | Critical spares |  |  |  |  | X
R.10 | Startup consumables |  |  |  |  | X
R.11 | Operational systems and procedures to support each department |  |  |  |  | X
R.12 | Environmental Management Plan for Operations (EMP) |  |  |  | X
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J18
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | x
A.2 | Project Charter and Mandate |  | x
A.3 | Governance and control (internal approval process defined) |  |  | x
A.5 | Project Strategy |  | x
A.6 | Strategic fit of project in organisation |  | x
A.7 | Due diligence |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  |  | x
B.2 | Geo-political risks |  |  |  | x
B.3 | Fiscal stability agreement |  |  |  | x
B.4 | Social License to Operate |  |  | x
B.5 | Violence and terrorism |  |  | x
B.6 | Ability to appoint expatriats |  |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  | x
B.9 | Custom duties & logistic routes |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  | x
C.3 | Business Plan |  | x
C.4 | Economic Analysis |  |  | x
C.5 | Affordability / Feasibility |  | x
C.6 | Contingencies (Capex & Opex) |  |  | x
C.7 | Basis of Estimate |  |  | x
C.8 | Scenario planning |  |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  | x
D.3 | Grade engineering / control |  |  |  | x
D.4 | Prospect drilling standard / guideline | x
D.5 | Geological conditions (Geological model, structure, qualities) | x
D.6 | Hydrogeology |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  | x
E.2 | Shaft/ramp design & men and material logistics |  |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  |  | x
E.5 | Life-of-mine plan |  |  | x
E.6 | Waste management plan |  |  | x
E.7 | Ultimate pit limits designed |  |  | x
E.8 | Economic block values determination |  |  | x
E.9 | Beneficiation facilities LOM plan |  |  |  |  | x
E.10 | Materials handling LOM plan |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  | x
F.2 | Productivity / efficiency benchmarks |  |  | x
F.3 | Operating costs |  |  | x
F.4 | Production risks |  |  |  |  | x
F.5 | Catalogue of operating plans |  |  |  | x
F.6 | Haul roads |  |  | x
F.7 | Transportation strategy |  |  | x
F.8 | Contractual considerations |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | x
G.2 | Price risks |  | x
G.3 | Demand risks & replacement products / technologies |  | x
G.4 | Value-Analysis Process |  | x
G.5 | Hedging |  | x
G.6 | Competitor analysis |  |  |  |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  | x
H.2 | Assumption register |  |  |  | x
H.3 | Completion risks |  |  | x
H.4 | Project Design Criteria |  | x
H.5 | Scope of Work Overview |  | x
H.6 | Project Schedule |  | x
H.7 | Project Cost Estimate |  | x
H.8 | Investment Studies & Alternatives Assessments |  | x
H.9 | Key Team Member Coordination |  | x
H.10 | Evaluation of Compliance Requirements |  | x
H.11 | Lead / Discipline Scope of Work |  | x
H.12 | Housing and transport of employees |  | x
H.13 | Risk or impact on other projects / divisions |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | x
I.2 | Site Characteristics Available vs. Required |  | x
I.3 | Project Scope definition |  | x
I.4 | WBS and WBS Dictionary |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan | [5 empty] | x
J.2 | Land use plan post operations | [5 empty] | x
J.3 | Social expectations register | [5 empty] | x
J.4 | Relocation Action Plan | [5 empty] | x
J.5 | Environmental expectations register |  | x
J.6 | Political expectations register |  |  |  |  | x
J.7 | Legal compliance register |  |  |  |  | x
J.8 | HSE risk register |  | x
J.9 | Community risk register |  |  |  | x
J.10 | Business risk register |  |  | x
J.11 | Developmental opportunity register |  |  |  |  | x
J.12 | Sustainability operating plan |  |  |  | x
J.13 | Stakeholder engagement plan |  |  |  | x
J.14 | Mine closure financial provision plan |  |  |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  |  | x
J.16 | Social investment plan | [5 empty] | x
J.17 | Economic diversification plan | [5 empty] | x
J.18 | Existing Environmental Conditions |  | x
J.19 | Environmental Process determined |  | x
J.20 | Environmental management plan |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  | x
K.2 | Site Surveys |  | x
K.3 | Governing Regulatory Requirements |  | x
K.4 | Utility Sources with Supply Conditions |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  | x
K.6 | Special Water and Waste Treatment Requirements |  | x
K.7 | Property Descriptions |  | x
K.8 | Right-of-Way Mapping & Site Issues |  | x
K.9 | Land Rights |  |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  | x
L.2 | Civil/Site Design |  | x
L.3 | Geotechnical investigation for structures |  | x
L.4 | Architectural Design |  | x
L.5 | Structural Design |  | x
L.6 | Mechanical Design |  | x
L.7 | Electrical Design |  | x
L.8 | Constructability Analysis |  | x
L.9 | Process Design |  | x
L.10 | Specifications |  | x
L.11 | Specialty Items List |  | x
L.12 | Instrument Index |  | x
L.13 | Control Philosophy & systems |  | x
L.14 | Logic Diagrams |  | x
L.15 | IM (information management) |  | x
L.16 | Control of Access |  | x
L.17 | Safety & Hazards |  | x
L.18 | Operations/Maintenance |  | x
L.19 | Ventilation Engineering | x
L.20 | Rock Engineering | x
L.21 | Water balances |  | x
L.22 | Energy efficiency / carbon footprint |  |  |  | x
L.23 | Tailings handling and storage |  |  | x
L.24 | Stormwater handling / surface hydrology |  | x
L.25 | Internal technical audits |  |  | x
L.26 | External technical audits |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  | x
M.3 | Technology trends |  | x
M.4 | Design to capacity |  |  | x
M.5 | Classes of facillity quality |  |  | x
M.6 | Energy optimisation |  |  |  |  | x
M.7 | Waste minimisation |  |  | x
M.8 | 3D / 4D design | [5 empty] | x
M.9 | Cleaner Production |  |  |  | x
M.10 | Innovation and knowledge management planning |  |  | x
M.11 | Six Sigma | [5 empty] | x
M.12 | Lean Manufacturing | [5 empty] | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | x
N.2 | Procurement Procedures and Plans |  | x
N.3 | Procurement Responsibility Matrix |  | x
N.4 | Draft contracts & proforma bidders pack |  | x
N.5 | Contracting strategy |  | x
N.6 | Procurement operation plan (POP) |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  | x
O.2 | Deliverables Defined |  | x
O.3 | Distribution Matrix |  | x
O.4 | Documentation/Deliverables |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  | x
P.2 | Project Cost Control |  | x
P.3 | Project Schedule Control |  | x
P.4 | Risk Management |  | x
P.5 | Safety, Health, Hygiene and security Management |  | x
P.6 | Environmental Management |  | x
P.7 | Project Change Control |  | x
P.8 | Project Audits |  |  | x
P.9 | Decision register |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  | x
Q.2 | Project Organization |  | x
Q.3 | Responsibility matrix RACI |  | x
Q.4 | Document Management Plan |  | x
Q.5 | Communication management plan |  | x
Q.6 | Project Delivery Method |  |  | x
Q.7 | Design / Construction Plan and Approach |  | x
Q.8 | Safety Procedures |  | x
Q.9 | Intercompany Agreements | x
Q.10 | Deliverables for Design and Construction |  | x
Q.11 | Labour and Skilled resources plan |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  | x
R.2 | Startup Requirements & plans |  | x
R.3 | Training Requirements |  | x
R.4 | Substantial Completion Requirements |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  | x
R.6 | Long term supply chain contracts |  | x
R.7 | Resourcing & staffing for operation |  | x
R.8 | Maintenance schedules |  | x
R.9 | Critical spares |  | x
R.10 | Startup consumables |  | x
R.11 | Operational systems and procedures to support each department |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J19
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  |  |  | x
A.2 | Project Charter and Mandate |  |  |  | x
A.3 | Governance and control (internal approval process defined) |  |  |  |  | x
A.5 | Project Strategy |  |  |  | x
A.6 | Strategic fit of project in organisation |  |  |  |  | x
A.7 | Due diligence |  |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  |  |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  | x
B.2 | Geo-political risks |  |  | x
B.3 | Fiscal stability agreement |  |  |  | x
B.4 | Social License to Operate |  |  |  | x
B.5 | Violence and terrorism |  |  | x
B.6 | Ability to appoint expatriats |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  |  |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  |  | x
B.9 | Custom duties & logistic routes |  |  |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) | [5 empty] | x
C.2 | Financing secured (Internal, external, equity, debt) | [5 empty] | x
C.3 | Business Plan |  |  |  | x
C.4 | Economic Analysis |  |  |  |  | x
C.5 | Affordability / Feasibility |  |  |  |  | x
C.6 | Contingencies (Capex & Opex) |  |  |  |  | x
C.7 | Basis of Estimate |  |  |  | x
C.8 | Scenario planning |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  |  |  | x
D.2 | Reserve risks (including modifying factors) | [5 empty] | x
D.3 | Grade engineering / control |  |  |  |  | x
D.4 | Prospect drilling standard / guideline | [5 empty] | x
D.5 | Geological conditions (Geological model, structure, qualities) | [5 empty] | x
D.6 | Hydrogeology | [5 empty] | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria | [5 empty] | x
E.2 | Shaft/ramp design & men and material logistics | [5 empty] | x
E.3 | Mining methods (drilling, blasting, loading, hauling) | [5 empty] | x
E.4 | Equipment selection to fit geological conditions and mining method | [5 empty] | x
E.5 | Life-of-mine plan | [5 empty] | x
E.6 | Waste management plan | [5 empty] | x
E.7 | Ultimate pit limits designed | [5 empty] | x
E.8 | Economic block values determination | [5 empty] | x
E.9 | Beneficiation facilities LOM plan | [5 empty] | x
E.10 | Materials handling LOM plan | [5 empty] | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  |  | x
F.2 | Productivity / efficiency benchmarks |  |  |  | x
F.3 | Operating costs |  |  |  | x
F.4 | Production risks |  |  | x
F.5 | Catalogue of operating plans |  |  |  | x
F.6 | Haul roads |  |  |  |  | x
F.7 | Transportation strategy |  |  |  |  | x
F.8 | Contractual considerations |  |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  |  | x
G.2 | Price risks |  |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  |  | x
G.4 | Value-Analysis Process |  |  |  | x
G.5 | Hedging |  |  | x
G.6 | Competitor analysis |  |  |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  |  | x
H.2 | Assumption register |  |  |  | x
H.3 | Completion risks |  |  | x
H.4 | Project Design Criteria |  |  |  | x
H.5 | Scope of Work Overview |  |  |  | x
H.6 | Project Schedule |  |  |  | x
H.7 | Project Cost Estimate |  |  |  | x
H.8 | Investment Studies & Alternatives Assessments |  |  |  | x
H.9 | Key Team Member Coordination |  |  |  |  | x
H.10 | Evaluation of Compliance Requirements |  |  |  | x
H.11 | Lead / Discipline Scope of Work |  |  |  | x
H.12 | Housing and transport of employees |  |  | x
H.13 | Risk or impact on other projects / divisions |  |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  |  |  | x
I.2 | Site Characteristics Available vs. Required |  |  |  |  | x
I.3 | Project Scope definition |  |  |  |  | x
I.4 | WBS and WBS Dictionary |  |  |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  |  |  | x
J.2 | Land use plan post operations |  |  | x
J.3 | Social expectations register |  |  | x
J.4 | Relocation Action Plan |  |  |  | x
J.5 | Environmental expectations register |  |  | x
J.6 | Political expectations register |  |  | x
J.7 | Legal compliance register |  |  |  |  | x
J.8 | HSE risk register |  |  |  |  | x
J.9 | Community risk register |  |  | x
J.10 | Business risk register |  |  |  | x
J.11 | Developmental opportunity register |  |  | x
J.12 | Sustainability operating plan |  |  |  | x
J.13 | Stakeholder engagement plan |  |  |  | x
J.14 | Mine closure financial provision plan |  |  |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  |  | x
J.16 | Social investment plan |  |  | x
J.17 | Economic diversification plan |  |  | x
J.18 | Existing Environmental Conditions |  |  |  | x
J.19 | Environmental Process determined
J.20 | Environmental management plan |  |  |  |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  |  |  | x
K.2 | Site Surveys |  |  |  |  | x
K.3 | Governing Regulatory Requirements |  |  |  |  | x
K.4 | Utility Sources with Supply Conditions |  |  |  |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  |  |  | x
K.6 | Special Water and Waste Treatment Requirements |  |  |  |  | x
K.7 | Property Descriptions |  |  |  |  | x
K.8 | Right-of-Way Mapping & Site Issues |  |  | x
K.9 | Land Rights |  |  |  |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  |  | x
L.2 | Civil/Site Design |  |  | x
L.3 | Geotechnical investigation for structures |  |  |  |  | x
L.4 | Architectural Design |  |  | x
L.5 | Structural Design |  |  |  | x
L.6 | Mechanical Design |  |  |  | x
L.7 | Electrical Design |  |  |  | x
L.8 | Constructability Analysis |  |  | x
L.9 | Process Design |  |  |  |  | x
L.10 | Specifications |  |  |  | x
L.11 | Specialty Items List |  |  |  | x
L.12 | Instrument Index |  |  |  | x
L.13 | Control Philosophy & systems |  |  |  | x
L.14 | Logic Diagrams |  |  |  | x
L.15 | IM (information management) |  |  |  | x
L.16 | Control of Access |  |  |  | x
L.17 | Safety & Hazards |  |  |  | x
L.18 | Operations/Maintenance |  |  |  | x
L.19 | Ventilation Engineering |  |  |  | x
L.20 | Rock Engineering |  |  |  | x
L.21 | Water balances |  |  |  |  | x
L.22 | Energy efficiency / carbon footprint |  |  |  |  | x
L.23 | Tailings handling and storage |  |  |  |  | x
L.24 | Stormwater handling / surface hydrology |  |  | x
L.25 | Internal technical audits |  |  |  |  | x
L.26 | External technical audits |  |  |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  |  |  | x
M.3 | Technology trends |  |  |  |  | x
M.4 | Design to capacity |  |  |  |  | x
M.5 | Classes of facillity quality |  |  |  | x
M.6 | Energy optimisation |  |  |  |  | x
M.7 | Waste minimisation |  |  |  |  | x
M.8 | 3D / 4D design
M.9 | Cleaner Production |  |  |  |  | x
M.10 | Innovation and knowledge management planning |  |  |  | x
M.11 | Six Sigma |  |  | x
M.12 | Lean Manufacturing |  |  | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  |  |  | x
N.2 | Procurement Procedures and Plans |  |  |  |  | x
N.3 | Procurement Responsibility Matrix |  |  |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  |  |  | x
N.5 | Contracting strategy |  |  |  |  | x
N.6 | Procurement operation plan (POP) |  |  |  |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  |  |  | x
O.2 | Deliverables Defined |  |  |  |  | x
O.3 | Distribution Matrix |  |  |  |  | x
O.4 | Documentation/Deliverables |  |  |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  |  |  | x
P.2 | Project Cost Control |  |  |  |  | x
P.3 | Project Schedule Control |  |  |  |  | x
P.4 | Risk Management |  |  |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  |  |  | x
P.6 | Environmental Management |  |  |  |  | x
P.7 | Project Change Control |  |  |  |  | x
P.8 | Project Audits |  |  |  |  | x
P.9 | Decision register |  |  |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  |  | x
Q.2 | Project Organization |  |  |  | x
Q.3 | Responsibility matrix RACI |  |  |  | x
Q.4 | Document Management Plan |  |  |  | x
Q.5 | Communication management plan |  |  |  | x
Q.6 | Project Delivery Method |  |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  |  | x
Q.8 | Safety Procedures |  |  | x
Q.9 | Intercompany Agreements |  |  |  | x
Q.10 | Deliverables for Design and Construction |  |  |  | x
Q.11 | Labour and Skilled resources plan |  |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  | x
R.2 | Startup Requirements & plans |  |  | x
R.3 | Training Requirements |  |  | x
R.4 | Substantial Completion Requirements |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  | x
R.6 | Long term supply chain contracts |  |  | x
R.7 | Resourcing & staffing for operation |  |  | x
R.8 | Maintenance schedules |  |  | x
R.9 | Critical spares |  |  | x
R.10 | Startup consumables |  |  | x
R.11 | Operational systems and procedures to support each department |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J20
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  | X
A.2 | Project Charter and Mandate |  |  | X
A.3 | Governance and control (internal approval process defined) |  |  |  | X
A.5 | Project Strategy |  |  | X
A.6 | Strategic fit of project in organisation |  | X
A.7 | Due diligence |  | X
A.8 | Partnership, joint ventures and shareholder buy in |  | X
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  | X
B.2 | Geo-political risks |  | X
B.3 | Fiscal stability agreement |  |  |  | X
B.4 | Social License to Operate |  | X
B.5 | Violence and terrorism |  |  |  |  | X
B.6 | Ability to appoint expatriats |  |  | X
B.7 | Procurement of local and foreign materials, services and equipment |  | X
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  |  |  | X
B.9 | Custom duties & logistic routes |  |  |  | X
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | X
C.2 | Financing secured (Internal, external, equity, debt) |  | X
C.3 | Business Plan |  |  | X
C.4 | Economic Analysis |  |  | X
C.5 | Affordability / Feasibility |  |  | X
C.6 | Contingencies (Capex & Opex) |  |  |  | X
C.7 | Basis of Estimate |  |  | X
C.8 | Scenario planning |  |  | X
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | X
D.2 | Reserve risks (including modifying factors) |  |  |  | X
D.3 | Grade engineering / control |  |  |  | X
D.4 | Prospect drilling standard / guideline |  |  | X
D.5 | Geological conditions (Geological model, structure, qualities) |  |  | X
D.6 | Hydrogeology |  |  | X
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  | X
E.2 | Shaft/ramp design & men and material logistics |  |  | X
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | X
E.4 | Equipment selection to fit geological conditions and mining method |  |  |  | X
E.5 | Life-of-mine plan |  |  | X
E.6 | Waste management plan |  |  |  | X
E.7 | Ultimate pit limits designed |  | X
E.8 | Economic block values determination |  |  | X
E.9 | Beneficiation facilities LOM plan |  |  |  | X
E.10 | Materials handling LOM plan |  |  |  |  | X
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | X
F.2 | Productivity / efficiency benchmarks |  |  | X
F.3 | Operating costs |  | X
F.4 | Production risks |  | X
F.5 | Catalogue of operating plans |  |  |  | X
F.6 | Haul roads |  |  |  | X
F.7 | Transportation strategy |  |  | X
F.8 | Contractual considerations |  |  |  | X
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  | X
G.2 | Price risks |  |  |  | X
G.3 | Demand risks & replacement products / technologies |  |  | X
G.4 | Value-Analysis Process |  |  |  | X
G.5 | Hedging |  | X
G.6 | Competitor analysis |  |  |  | X
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  | X
H.2 | Assumption register |  |  | X
H.3 | Completion risks |  | X
H.4 | Project Design Criteria |  |  |  | X
H.5 | Scope of Work Overview |  |  | X
H.6 | Project Schedule |  |  |  | X
H.7 | Project Cost Estimate |  | X
H.8 | Investment Studies & Alternatives Assessments |  |  | X
H.9 | Key Team Member Coordination |  |  |  | X
H.10 | Evaluation of Compliance Requirements |  |  |  |  | X
H.11 | Lead / Discipline Scope of Work |  | X
H.12 | Housing and transport of employees |  |  | X
H.13 | Risk or impact on other projects / divisions |  |  | X
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | X
I.2 | Site Characteristics Available vs. Required |  |  | X
I.3 | Project Scope definition |  | X
I.4 | WBS and WBS Dictionary |  |  | X
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  | X
J.2 | Land use plan post operations |  |  | X
J.3 | Social expectations register |  | X
J.4 | Relocation Action Plan |  | X
J.5 | Environmental expectations register |  |  |  | X
J.6 | Political expectations register |  |  |  | X
J.7 | Legal compliance register |  |  | X
J.8 | HSE risk register |  |  |  | X
J.9 | Community risk register |  | X
J.10 | Business risk register |  |  | X
J.11 | Developmental opportunity register |  | X
J.12 | Sustainability operating plan |  |  |  | X
J.13 | Stakeholder engagement plan |  |  | X
J.14 | Mine closure financial provision plan |  |  |  | X
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  | X
J.16 | Social investment plan |  |  | X
J.17 | Economic diversification plan |  |  |  | X
J.18 | Existing Environmental Conditions |  |  |  |  | X
J.19 | Environmental Process determined |  | X
J.20 | Environmental management plan |  |  | X
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  | X
K.2 | Site Surveys |  |  | X
K.3 | Governing Regulatory Requirements |  | X
K.4 | Utility Sources with Supply Conditions |  | X
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  | X
K.6 | Special Water and Waste Treatment Requirements |  |  | X
K.7 | Property Descriptions |  | X
K.8 | Right-of-Way Mapping & Site Issues |  | X
K.9 | Land Rights |  | X
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  | X
L.2 | Civil/Site Design |  | X
L.3 | Geotechnical investigation for structures |  |  |  | X
L.4 | Architectural Design |  |  | X
L.5 | Structural Design |  |  | X
L.6 | Mechanical Design |  | X
L.7 | Electrical Design |  | X
L.8 | Constructability Analysis |  |  |  | X
L.9 | Process Design |  |  |  | X
L.10 | Specifications |  |  | X
L.11 | Specialty Items List |  |  |  | X
L.12 | Instrument Index |  | X
L.13 | Control Philosophy & systems |  |  | X
L.14 | Logic Diagrams |  |  |  | X
L.15 | IM (information management) |  | X
L.16 | Control of Access |  | X
L.17 | Safety & Hazards |  |  | X
L.18 | Operations/Maintenance |  |  |  | X
L.19 | Ventilation Engineering |  |  |  | X
L.20 | Rock Engineering |  |  | X
L.21 | Water balances |  |  | X
L.22 | Energy efficiency / carbon footprint |  |  |  | X
L.23 | Tailings handling and storage |  | X
L.24 | Stormwater handling / surface hydrology |  |  | X
L.25 | Internal technical audits |  |  | X
L.26 | External technical audits |  | X
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  | X
M.2 | Design & Material Alternatives Considered/Rejected |  |  | X
M.3 | Technology trends |  | X
M.4 | Design to capacity |  |  |  | X
M.5 | Classes of facillity quality |  | X
M.6 | Energy optimisation |  | X
M.7 | Waste minimisation |  | X
M.8 | 3D / 4D design |  | X
M.9 | Cleaner Production |  |  |  | X
M.10 | Innovation and knowledge management planning |  |  | X
M.11 | Six Sigma |  |  | X
M.12 | Lean Manufacturing |  |  | X
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | X
N.2 | Procurement Procedures and Plans |  |  | X
N.3 | Procurement Responsibility Matrix |  | X
N.4 | Draft contracts & proforma bidders pack |  | X
N.5 | Contracting strategy |  | X
N.6 | Procurement operation plan (POP) |  |  | X
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  | X
O.2 | Deliverables Defined |  |  |  | X
O.3 | Distribution Matrix |  |  | X
O.4 | Documentation/Deliverables |  | X
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  | X
P.2 | Project Cost Control |  |  | X
P.3 | Project Schedule Control |  | X
P.4 | Risk Management |  | X
P.5 | Safety, Health, Hygiene and security Management |  |  | X
P.6 | Environmental Management |  |  | X
P.7 | Project Change Control |  | X
P.8 | Project Audits |  | X
P.9 | Decision register |  | X
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | X
Q.2 | Project Organization |  |  | X
Q.3 | Responsibility matrix RACI |  |  |  | X
Q.4 | Document Management Plan |  | X
Q.5 | Communication management plan |  |  | X
Q.6 | Project Delivery Method |  |  |  | X
Q.7 | Design / Construction Plan and Approach |  | X
Q.8 | Safety Procedures |  |  | X
Q.9 | Intercompany Agreements |  |  | X
Q.10 | Deliverables for Design and Construction |  |  |  | X
Q.11 | Labour and Skilled resources plan |  | X
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  | X
R.2 | Startup Requirements & plans |  |  | X
R.3 | Training Requirements |  |  |  | X
R.4 | Substantial Completion Requirements |  | X
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  |  | X
R.6 | Long term supply chain contracts |  |  |  | X
R.7 | Resourcing & staffing for operation |  |  |  | X
R.8 | Maintenance schedules |  |  | X
R.9 | Critical spares |  |  | X
R.10 | Startup consumables |  |  |  | X
R.11 | Operational systems and procedures to support each department |  | X
R.12 | Environmental Management Plan for Operations (EMP) |  |  |  |  | X
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J21
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | *
A.2 | Project Charter and Mandate |  | *
A.3 | Governance and control (internal approval process defined) |  | *
A.5 | Project Strategy |  | *
A.6 | Strategic fit of project in organisation |  | *
A.7 | Due diligence |  | *
A.8 | Partnership, joint ventures and shareholder buy in |  | *
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  | *
B.2 | Geo-political risks |  | *
B.3 | Fiscal stability agreement |  | *
B.4 | Social License to Operate |  | *
B.5 | Violence and terrorism |  |  | *
B.6 | Ability to appoint expatriats |  | *
B.7 | Procurement of local and foreign materials, services and equipment |  | *
B.8 | Country infrastructure (power, roads, rail, water ports) |  | *
B.9 | Custom duties & logistic routes |  | *
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | *
C.2 | Financing secured (Internal, external, equity, debt) |  | *
C.3 | Business Plan |  | *
C.4 | Economic Analysis |  | *
C.5 | Affordability / Feasibility |  | *
C.6 | Contingencies (Capex & Opex) |  | *
C.7 | Basis of Estimate |  |  | *
C.8 | Scenario planning |  | *
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  | *
D.2 | Reserve risks (including modifying factors) |  | *
D.3 | Grade engineering / control |  | *
D.4 | Prospect drilling standard / guideline |  | *
D.5 | Geological conditions (Geological model, structure, qualities) |  | *
D.6 | Hydrogeology
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  | *
E.2 | Shaft/ramp design & men and material logistics |  | *
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | *
E.4 | Equipment selection to fit geological conditions and mining method |  | *
E.5 | Life-of-mine plan |  | *
E.6 | Waste management plan |  | *
E.7 | Ultimate pit limits designed |  | *
E.8 | Economic block values determination |  | *
E.9 | Beneficiation facilities LOM plan |  | *
E.10 | Materials handling LOM plan |  | *
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | *
F.2 | Productivity / efficiency benchmarks |  | *
F.3 | Operating costs |  | *
F.4 | Production risks |  | * | *
F.5 | Catalogue of operating plans |  | *
F.6 | Haul roads |  | *
F.7 | Transportation strategy |  | *
F.8 | Contractual considerations |  | *
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | *
G.2 | Price risks |  | *
G.3 | Demand risks & replacement products / technologies |  | *
G.4 | Value-Analysis Process |  | *
G.5 | Hedging |  | *
G.6 | Competitor analysis |  | *
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  | *
H.2 | Assumption register |  | *
H.3 | Completion risks |  | *
H.4 | Project Design Criteria |  | *
H.5 | Scope of Work Overview |  | *
H.6 | Project Schedule |  | *
H.7 | Project Cost Estimate |  | *
H.8 | Investment Studies & Alternatives Assessments |  | *
H.9 | Key Team Member Coordination |  |  | *
H.10 | Evaluation of Compliance Requirements |  | *
H.11 | Lead / Discipline Scope of Work |  | *
H.12 | Housing and transport of employees |  | *
H.13 | Risk or impact on other projects / divisions |  | *
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | *
I.2 | Site Characteristics Available vs. Required |  |  | *
I.3 | Project Scope definition |  | *
I.4 | WBS and WBS Dictionary |  | *
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  | *
J.2 | Land use plan post operations |  | *
J.3 | Social expectations register |  | *
J.4 | Relocation Action Plan |  | *
J.5 | Environmental expectations register |  | *
J.6 | Political expectations register |  | *
J.7 | Legal compliance register |  | *
J.8 | HSE risk register |  | *
J.9 | Community risk register |  | *
J.10 | Business risk register |  | *
J.11 | Developmental opportunity register |  | *
J.12 | Sustainability operating plan |  | *
J.13 | Stakeholder engagement plan |  | *
J.14 | Mine closure financial provision plan |  | *
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  | *
J.16 | Social investment plan |  | *
J.17 | Economic diversification plan |  | *
J.18 | Existing Environmental Conditions |  | *
J.19 | Environmental Process determined |  | *
J.20 | Environmental management plan |  | *
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  | *
K.2 | Site Surveys |  | *
K.3 | Governing Regulatory Requirements |  | *
K.4 | Utility Sources with Supply Conditions |  | *
K.5 | Fire Protection, emergency procedure & Safety Considerations |  | *
K.6 | Special Water and Waste Treatment Requirements |  | *
K.7 | Property Descriptions |  | *
K.8 | Right-of-Way Mapping & Site Issues |  | *
K.9 | Land Rights |  | *
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  | *
L.2 | Civil/Site Design |  |  |  | *
L.3 | Geotechnical investigation for structures |  | *
L.4 | Architectural Design |  |  |  | *
L.5 | Structural Design |  |  | *
L.6 | Mechanical Design |  |  | *
L.7 | Electrical Design |  |  | *
L.8 | Constructability Analysis |  |  |  | *
L.9 | Process Design |  |  | *
L.10 | Specifications |  |  |  | *
L.11 | Specialty Items List |  |  |  | *
L.12 | Instrument Index |  |  | *
L.13 | Control Philosophy & systems |  |  | *
L.14 | Logic Diagrams |  |  | *
L.15 | IM (information management) |  |  | *
L.16 | Control of Access |  |  | *
L.17 | Safety & Hazards |  |  | *
L.18 | Operations/Maintenance |  |  | *
L.19 | Ventilation Engineering |  |  | *
L.20 | Rock Engineering |  |  | *
L.21 | Water balances |  |  | *
L.22 | Energy efficiency / carbon footprint |  |  | *
L.23 | Tailings handling and storage |  |  | *
L.24 | Stormwater handling / surface hydrology |  |  | *
L.25 | Internal technical audits |  |  | *
L.26 | External technical audits |  |  | *
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  | *
M.2 | Design & Material Alternatives Considered/Rejected |  | *
M.3 | Technology trends |  | *
M.4 | Design to capacity |  | *
M.5 | Classes of facillity quality |  | *
M.6 | Energy optimisation |  | *
M.7 | Waste minimisation |  | *
M.8 | 3D / 4D design |  | *
M.9 | Cleaner Production |  | *
M.10 | Innovation and knowledge management planning |  | *
M.11 | Six Sigma |  | *
M.12 | Lean Manufacturing |  | *
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | *
N.2 | Procurement Procedures and Plans |  | *
N.3 | Procurement Responsibility Matrix |  | *
N.4 | Draft contracts & proforma bidders pack |  | *
N.5 | Contracting strategy |  | *
N.6 | Procurement operation plan (POP) |  | *
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  | *
O.2 | Deliverables Defined |  | *
O.3 | Distribution Matrix |  | *
O.4 | Documentation/Deliverables |  | *
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  | *
P.2 | Project Cost Control |  | *
P.3 | Project Schedule Control |  | *
P.4 | Risk Management |  | *
P.5 | Safety, Health, Hygiene and security Management |  | *
P.6 | Environmental Management |  | *
P.7 | Project Change Control |  | *
P.8 | Project Audits |  | *
P.9 | Decision register |  | *
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  | *
Q.2 | Project Organization |  | *
Q.3 | Responsibility matrix RACI |  | *
Q.4 | Document Management Plan |  | *
Q.5 | Communication management plan |  | *
Q.6 | Project Delivery Method |  | *
Q.7 | Design / Construction Plan and Approach |  | *
Q.8 | Safety Procedures |  | *
Q.9 | Intercompany Agreements |  | *
Q.10 | Deliverables for Design and Construction |  | *
Q.11 | Labour and Skilled resources plan |  | *
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  | *
R.2 | Startup Requirements & plans |  | *
R.3 | Training Requirements |  | *
R.4 | Substantial Completion Requirements |  | *
R.5 | Deliverables for Project Commissioning / Closeout |  |  | *
R.6 | Long term supply chain contracts |  | *
R.7 | Resourcing & staffing for operation |  | *
R.8 | Maintenance schedules |  | *
R.9 | Critical spares |  | *
R.10 | Startup consumables |  | *
R.11 | Operational systems and procedures to support each department |  | *
R.12 | Environmental Management Plan for Operations (EMP) |  | *
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J22
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  |  | x
A.2 | Project Charter and Mandate |  |  |  |  | x
A.3 | Governance and control (internal approval process defined) |  |  |  | x
A.5 | Project Strategy |  | x
A.6 | Strategic fit of project in organisation |  | x
A.7 | Due diligence |  |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  |  |  |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  | x
B.2 | Geo-political risks |  |  |  | x
B.3 | Fiscal stability agreement |  |  |  |  | x
B.4 | Social License to Operate |  |  | x
B.5 | Violence and terrorism |  |  |  |  | x
B.6 | Ability to appoint expatriats |  |  |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  |  |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  |  |  | x
B.9 | Custom duties & logistic routes |  |  |  |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  | x
C.3 | Business Plan |  | x
C.4 | Economic Analysis |  |  | x
C.5 | Affordability / Feasibility |  |  | x
C.6 | Contingencies (Capex & Opex) |  |  | x
C.7 | Basis of Estimate |  |  | x
C.8 | Scenario planning |  |  |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  | x
D.2 | Reserve risks (including modifying factors) |  | x
D.3 | Grade engineering / control |  | x
D.4 | Prospect drilling standard / guideline |  |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  | x
D.6 | Hydrogeology |  |  |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  |  | x
E.2 | Shaft/ramp design & men and material logistics |  |  |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  |  | x
E.5 | Life-of-mine plan |  |  |  | x
E.6 | Waste management plan |  |  |  | x
E.7 | Ultimate pit limits designed |  | x
E.8 | Economic block values determination |  | x
E.9 | Beneficiation facilities LOM plan |  | x
E.10 | Materials handling LOM plan |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  |  | x
F.2 | Productivity / efficiency benchmarks |  |  | x
F.3 | Operating costs |  | x
F.4 | Production risks |  |  |  |  | x
F.5 | Catalogue of operating plans |  |  |  | x
F.6 | Haul roads |  |  |  | x
F.7 | Transportation strategy |  |  | x
F.8 | Contractual considerations |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | x
G.2 | Price risks |  | x
G.3 | Demand risks & replacement products / technologies |  | x
G.4 | Value-Analysis Process |  | x
G.5 | Hedging | x
G.6 | Competitor analysis |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  |  | x
H.2 | Assumption register | x
H.3 | Completion risks |  |  |  |  | x
H.4 | Project Design Criteria |  |  |  | x
H.5 | Scope of Work Overview
H.6 | Project Schedule |  |  |  |  | x
H.7 | Project Cost Estimate |  |  | x
H.8 | Investment Studies & Alternatives Assessments |  |  |  | x
H.9 | Key Team Member Coordination |  |  |  |  | x
H.10 | Evaluation of Compliance Requirements |  |  |  | x
H.11 | Lead / Discipline Scope of Work |  |  |  | x
H.12 | Housing and transport of employees |  |  | x
H.13 | Risk or impact on other projects / divisions |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  |  | x
I.2 | Site Characteristics Available vs. Required |  |  |  | x
I.3 | Project Scope definition | x
I.4 | WBS and WBS Dictionary |  |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan | x
J.2 | Land use plan post operations |  |  |  |  | x
J.3 | Social expectations register |  |  |  |  | x
J.4 | Relocation Action Plan |  |  | x
J.5 | Environmental expectations register | x
J.6 | Political expectations register | x
J.7 | Legal compliance register | x
J.8 | HSE risk register |  |  |  | x
J.9 | Community risk register |  |  | x
J.10 | Business risk register | x
J.11 | Developmental opportunity register | x
J.12 | Sustainability operating plan |  |  | x
J.13 | Stakeholder engagement plan |  | x
J.14 | Mine closure financial provision plan |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  |  | x
J.16 | Social investment plan |  |  |  | x
J.17 | Economic diversification plan | x
J.18 | Existing Environmental Conditions |  |  |  | x
J.19 | Environmental Process determined |  |  |  | x
J.20 | Environmental management plan |  |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  |  | x
K.2 | Site Surveys |  | x
K.3 | Governing Regulatory Requirements |  |  |  | x
K.4 | Utility Sources with Supply Conditions |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations | [5 empty] | x
K.6 | Special Water and Waste Treatment Requirements | [5 empty] | x
K.7 | Property Descriptions |  |  |  |  | x
K.8 | Right-of-Way Mapping & Site Issues |  | x
K.9 | Land Rights |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  |  |  | x
L.2 | Civil/Site Design |  |  | x
L.3 | Geotechnical investigation for structures | [5 empty] | x
L.4 | Architectural Design |  |  |  | x
L.5 | Structural Design |  |  |  | x
L.6 | Mechanical Design |  |  |  | x
L.7 | Electrical Design |  |  | x
L.8 | Constructability Analysis |  |  |  | x
L.9 | Process Design |  | x
L.10 | Specifications |  |  |  | x
L.11 | Specialty Items List | x
L.12 | Instrument Index | x
L.13 | Control Philosophy & systems | x
L.14 | Logic Diagrams | x
L.15 | IM (information management) |  |  |  |  | x
L.16 | Control of Access |  | x
L.17 | Safety & Hazards |  |  |  |  | x
L.18 | Operations/Maintenance |  |  |  | x
L.19 | Ventilation Engineering |  |  |  |  | x
L.20 | Rock Engineering |  |  |  |  | x
L.21 | Water balances | [5 empty] | x
L.22 | Energy efficiency / carbon footprint |  | x
L.23 | Tailings handling and storage |  | x
L.24 | Stormwater handling / surface hydrology | [5 empty] | x
L.25 | Internal technical audits |  |  |  |  | x
L.26 | External technical audits | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  |  |  | x
M.3 | Technology trends | [5 empty] | x
M.4 | Design to capacity |  | x
M.5 | Classes of facillity quality |  |  | x
M.6 | Energy optimisation |  |  |  |  | x
M.7 | Waste minimisation |  |  |  |  | x
M.8 | 3D / 4D design |  | x
M.9 | Cleaner Production |  |  |  | x
M.10 | Innovation and knowledge management planning |  |  |  |  | x
M.11 | Six Sigma | x
M.12 | Lean Manufacturing | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  |  | x
N.2 | Procurement Procedures and Plans |  |  | x
N.3 | Procurement Responsibility Matrix |  | x
N.4 | Draft contracts & proforma bidders pack |  |  |  |  | x
N.5 | Contracting strategy |  |  | x
N.6 | Procurement operation plan (POP) |  |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  | x
O.2 | Deliverables Defined |  | x
O.3 | Distribution Matrix |  |  | x
O.4 | Documentation/Deliverables |  |  |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control | [5 empty] | x
P.2 | Project Cost Control |  |  | x
P.3 | Project Schedule Control |  |  |  |  | x
P.4 | Risk Management | [5 empty] | x
P.5 | Safety, Health, Hygiene and security Management | [5 empty] | x
P.6 | Environmental Management | [5 empty] | x
P.7 | Project Change Control | [5 empty] | x
P.8 | Project Audits | [5 empty] | x
P.9 | Decision register | [5 empty] | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | x
Q.2 | Project Organization |  |  | x
Q.3 | Responsibility matrix RACI |  |  | x
Q.4 | Document Management Plan | [5 empty] | x
Q.5 | Communication management plan |  | x
Q.6 | Project Delivery Method |  |  |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  |  |  | x
Q.8 | Safety Procedures | [5 empty] | x
Q.9 | Intercompany Agreements | x
Q.10 | Deliverables for Design and Construction |  |  |  | x
Q.11 | Labour and Skilled resources plan | [5 empty] | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  |  | x
R.2 | Startup Requirements & plans |  |  |  |  | x
R.3 | Training Requirements | [5 empty] | x
R.4 | Substantial Completion Requirements |  |  |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  |  | x
R.6 | Long term supply chain contracts |  | x
R.7 | Resourcing & staffing for operation |  |  |  |  | x
R.8 | Maintenance schedules |  |  |  |  | x
R.9 | Critical spares |  | x
R.10 | Startup consumables |  | x
R.11 | Operational systems and procedures to support each department | [5 empty] | x
R.12 | Environmental Management Plan for Operations (EMP) | [5 empty] | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J23
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  | X
A.2 | Project Charter and Mandate |  |  | X
A.3 | Governance and control (internal approval process defined) |  | X
A.5 | Project Strategy |  |  | X
A.6 | Strategic fit of project in organisation |  | X
A.7 | Due diligence |  |  | X
A.8 | Partnership, joint ventures and shareholder buy in |  | X
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  |  | X
B.2 | Geo-political risks |  |  |  | X
B.3 | Fiscal stability agreement |  |  |  | X
B.4 | Social License to Operate |  |  | X
B.5 | Violence and terrorism |  | X
B.6 | Ability to appoint expatriats |  |  | X
B.7 | Procurement of local and foreign materials, services and equipment |  |  |  | X
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  |  | X
B.9 | Custom duties & logistic routes |  |  |  | X
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | X
C.2 | Financing secured (Internal, external, equity, debt) |  |  |  | X
C.3 | Business Plan |  |  | X
C.4 | Economic Analysis |  |  | X
C.5 | Affordability / Feasibility |  |  | X
C.6 | Contingencies (Capex & Opex) |  |  | X
C.7 | Basis of Estimate |  |  | X
C.8 | Scenario planning |  |  |  | X
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | X
D.2 | Reserve risks (including modifying factors) |  |  |  | X
D.3 | Grade engineering / control |  |  |  | X
D.4 | Prospect drilling standard / guideline |  |  | X
D.5 | Geological conditions (Geological model, structure, qualities) |  | X
D.6 | Hydrogeology |  |  | X
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  | X
E.2 | Shaft/ramp design & men and material logistics |  |  | X
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  |  | X
E.4 | Equipment selection to fit geological conditions and mining method |  |  |  | X
E.5 | Life-of-mine plan |  |  |  | X
E.6 | Waste management plan |  |  | X
E.7 | Ultimate pit limits designed | X
E.8 | Economic block values determination |  | X
E.9 | Beneficiation facilities LOM plan |  | X
E.10 | Materials handling LOM plan |  | X
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  | X
F.2 | Productivity / efficiency benchmarks |  |  | X
F.3 | Operating costs |  |  |  | X
F.4 | Production risks |  |  |  | X
F.5 | Catalogue of operating plans |  |  | X
F.6 | Haul roads | X
F.7 | Transportation strategy |  |  | X
F.8 | Contractual considerations |  |  | X
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | X
G.2 | Price risks |  |  |  | X
G.3 | Demand risks & replacement products / technologies |  |  |  | X
G.4 | Value-Analysis Process |  |  |  | X
G.5 | Hedging |  |  |  | X
G.6 | Competitor analysis |  |  |  | X
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  | X
H.2 | Assumption register |  |  | X
H.3 | Completion risks |  |  |  | X
H.4 | Project Design Criteria |  |  | X
H.5 | Scope of Work Overview |  |  | X
H.6 | Project Schedule |  |  | X
H.7 | Project Cost Estimate |  |  | X
H.8 | Investment Studies & Alternatives Assessments |  |  | X
H.9 | Key Team Member Coordination |  | X
H.10 | Evaluation of Compliance Requirements |  | X
H.11 | Lead / Discipline Scope of Work |  |  | X
H.12 | Housing and transport of employees |  |  | X
H.13 | Risk or impact on other projects / divisions |  |  | X
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  | X
I.2 | Site Characteristics Available vs. Required |  |  | X
I.3 | Project Scope definition |  |  | X
I.4 | WBS and WBS Dictionary |  |  |  | X
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  |  |  | X
J.2 | Land use plan post operations |  |  |  |  | X
J.3 | Social expectations register |  |  |  | X
J.4 | Relocation Action Plan | X
J.5 | Environmental expectations register |  |  | X
J.6 | Political expectations register |  |  | X
J.7 | Legal compliance register |  |  | X
J.8 | HSE risk register |  |  | X
J.9 | Community risk register |  |  | X
J.10 | Business risk register |  |  | X
J.11 | Developmental opportunity register |  |  |  | X
J.12 | Sustainability operating plan |  |  |  | X
J.13 | Stakeholder engagement plan |  |  |  | X
J.14 | Mine closure financial provision plan |  |  |  | X
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  |  | X
J.16 | Social investment plan |  |  |  | X
J.17 | Economic diversification plan |  |  |  |  | X
J.18 | Existing Environmental Conditions |  |  |  | X
J.19 | Environmental Process determined |  |  |  | X
J.20 | Environmental management plan |  |  |  | X
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  | X
K.2 | Site Surveys |  | X
K.3 | Governing Regulatory Requirements |  | X
K.4 | Utility Sources with Supply Conditions |  |  | X
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  | X
K.6 | Special Water and Waste Treatment Requirements |  |  | X
K.7 | Property Descriptions |  |  | X
K.8 | Right-of-Way Mapping & Site Issues |  |  | X
K.9 | Land Rights |  | X
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  | X
L.2 | Civil/Site Design |  | X
L.3 | Geotechnical investigation for structures |  | X
L.4 | Architectural Design |  | X
L.5 | Structural Design |  | X
L.6 | Mechanical Design |  | X
L.7 | Electrical Design |  | X
L.8 | Constructability Analysis |  |  | X
L.9 | Process Design |  |  | X
L.10 | Specifications |  |  | X
L.11 | Specialty Items List |  |  | X
L.12 | Instrument Index |  |  | X
L.13 | Control Philosophy & systems |  |  | X
L.14 | Logic Diagrams |  |  | X
L.15 | IM (information management) |  |  | X
L.16 | Control of Access |  |  |  | X
L.17 | Safety & Hazards |  |  |  | X
L.18 | Operations/Maintenance |  |  |  | X
L.19 | Ventilation Engineering |  |  | X
L.20 | Rock Engineering |  |  | X
L.21 | Water balances |  |  | X
L.22 | Energy efficiency / carbon footprint |  |  | X
L.23 | Tailings handling and storage |  | X
L.24 | Stormwater handling / surface hydrology |  | X
L.25 | Internal technical audits |  |  | X
L.26 | External technical audits |  |  | X
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  | X
M.2 | Design & Material Alternatives Considered/Rejected |  |  | X
M.3 | Technology trends |  |  |  | X
M.4 | Design to capacity |  |  | X
M.5 | Classes of facillity quality |  |  |  | X
M.6 | Energy optimisation |  |  |  |  | X
M.7 | Waste minimisation |  |  |  | X
M.8 | 3D / 4D design |  |  |  | X
M.9 | Cleaner Production |  |  | X
M.10 | Innovation and knowledge management planning |  |  |  |  | X
M.11 | Six Sigma | X
M.12 | Lean Manufacturing | X
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | X
N.2 | Procurement Procedures and Plans |  | X
N.3 | Procurement Responsibility Matrix |  | X
N.4 | Draft contracts & proforma bidders pack |  | X
N.5 | Contracting strategy |  | X
N.6 | Procurement operation plan (POP) |  | X
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  | X
O.2 | Deliverables Defined |  |  | X
O.3 | Distribution Matrix |  |  |  | X
O.4 | Documentation/Deliverables |  |  |  | X
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  | X
P.2 | Project Cost Control |  |  | X
P.3 | Project Schedule Control |  |  | X
P.4 | Risk Management |  |  | X
P.5 | Safety, Health, Hygiene and security Management |  |  | X
P.6 | Environmental Management |  |  |  | X
P.7 | Project Change Control |  |  | X
P.8 | Project Audits |  | X
P.9 | Decision register |  |  | X
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  | X
Q.2 | Project Organization |  |  |  | X
Q.3 | Responsibility matrix RACI |  |  | X
Q.4 | Document Management Plan |  |  | X
Q.5 | Communication management plan |  |  |  | X
Q.6 | Project Delivery Method |  |  | X
Q.7 | Design / Construction Plan and Approach |  |  | X
Q.8 | Safety Procedures |  | X
Q.9 | Intercompany Agreements | X
Q.10 | Deliverables for Design and Construction |  |  | X
Q.11 | Labour and Skilled resources plan |  |  | X
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  | X
R.2 | Startup Requirements & plans |  |  |  | X
R.3 | Training Requirements |  |  |  | X
R.4 | Substantial Completion Requirements |  | X
R.5 | Deliverables for Project Commissioning / Closeout |  | X
R.6 | Long term supply chain contracts |  |  | X
R.7 | Resourcing & staffing for operation |  |  |  | X
R.8 | Maintenance schedules |  |  |  | X
R.9 | Critical spares |  |  | X
R.10 | Startup consumables |  |  | X
R.11 | Operational systems and procedures to support each department |  |  |  | X
R.12 | Environmental Management Plan for Operations (EMP) |  |  | X
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J24
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  |  | x
A.2 | Project Charter and Mandate |  |  |  | x
A.3 | Governance and control (internal approval process defined) |  |  |  | x
A.5 | Project Strategy |  |  | x
A.6 | Strategic fit of project in organisation |  |  |  |  | x
A.7 | Due diligence |  |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  |  |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  | x
B.2 | Geo-political risks |  |  |  |  | x
B.3 | Fiscal stability agreement |  |  |  | x
B.4 | Social License to Operate |  |  | x
B.5 | Violence and terrorism |  | x
B.6 | Ability to appoint expatriats |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  |  |  | x
B.9 | Custom duties & logistic routes |  |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  |  | x
C.3 | Business Plan |  |  |  | x
C.4 | Economic Analysis |  |  |  | x
C.5 | Affordability / Feasibility |  |  | x
C.6 | Contingencies (Capex & Opex) |  |  |  | x
C.7 | Basis of Estimate |  |  | x
C.8 | Scenario planning |  |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  |  | x
D.3 | Grade engineering / control |  |  | x
D.4 | Prospect drilling standard / guideline |  |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  |  | x
D.6 | Hydrogeology |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  |  | x
E.2 | Shaft/ramp design & men and material logistics |  |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  |  | x
E.5 | Life-of-mine plan |  |  |  | x
E.6 | Waste management plan |  |  |  | x
E.7 | Ultimate pit limits designed |  |  | x
E.8 | Economic block values determination |  |  | x
E.9 | Beneficiation facilities LOM plan |  |  |  | x
E.10 | Materials handling LOM plan |  |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  | x
F.2 | Productivity / efficiency benchmarks |  |  |  | x
F.3 | Operating costs |  |  |  | x
F.4 | Production risks |  |  |  | x
F.5 | Catalogue of operating plans |  |  |  | x
F.6 | Haul roads |  |  | x
F.7 | Transportation strategy |  |  | x
F.8 | Contractual considerations |  |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  | x
G.2 | Price risks |  |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  |  | x
G.4 | Value-Analysis Process |  |  |  | x
G.5 | Hedging |  |  |  | x
G.6 | Competitor analysis |  |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  |  | x
H.2 | Assumption register |  |  |  | x
H.3 | Completion risks |  |  |  | x
H.4 | Project Design Criteria |  |  |  | x
H.5 | Scope of Work Overview |  |  | x
H.6 | Project Schedule |  |  | x
H.7 | Project Cost Estimate |  |  |  | x
H.8 | Investment Studies & Alternatives Assessments |  |  |  | x
H.9 | Key Team Member Coordination |  |  |  | x
H.10 | Evaluation of Compliance Requirements |  |  | x
H.11 | Lead / Discipline Scope of Work |  |  | x
H.12 | Housing and transport of employees |  |  | x
H.13 | Risk or impact on other projects / divisions |  |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  | x
I.2 | Site Characteristics Available vs. Required |  |  | x
I.3 | Project Scope definition |  |  | x
I.4 | WBS and WBS Dictionary |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  |  | x
J.2 | Land use plan post operations |  |  | x
J.3 | Social expectations register |  |  | x
J.4 | Relocation Action Plan |  |  |  | x
J.5 | Environmental expectations register |  |  | x
J.6 | Political expectations register |  |  |  | x
J.7 | Legal compliance register |  |  |  | x
J.8 | HSE risk register |  |  |  | x
J.9 | Community risk register |  |  | x
J.10 | Business risk register |  |  |  | x
J.11 | Developmental opportunity register |  |  | x
J.12 | Sustainability operating plan |  |  |  | x
J.13 | Stakeholder engagement plan |  |  | x
J.14 | Mine closure financial provision plan |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  | x
J.16 | Social investment plan |  |  |  | x
J.17 | Economic diversification plan |  |  |  | x
J.18 | Existing Environmental Conditions |  |  | x
J.19 | Environmental Process determined |  |  |  | x
J.20 | Environmental management plan |  |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  |  | x
K.2 | Site Surveys |  |  |  | x
K.3 | Governing Regulatory Requirements |  |  |  |  | x
K.4 | Utility Sources with Supply Conditions |  |  |  |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  |  |  | x
K.6 | Special Water and Waste Treatment Requirements |  |  |  |  | x
K.7 | Property Descriptions |  |  |  | x
K.8 | Right-of-Way Mapping & Site Issues |  |  |  |  | x
K.9 | Land Rights |  |  |  |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  |  | x
L.2 | Civil/Site Design |  |  |  | x
L.3 | Geotechnical investigation for structures |  |  |  | x
L.4 | Architectural Design |  |  |  | x
L.5 | Structural Design |  |  |  | x
L.6 | Mechanical Design |  |  |  | x
L.7 | Electrical Design |  |  |  | x
L.8 | Constructability Analysis |  |  |  |  | x
L.9 | Process Design |  |  | x
L.10 | Specifications |  |  |  | x
L.11 | Specialty Items List |  |  |  |  | x
L.12 | Instrument Index |  |  |  | x
L.13 | Control Philosophy & systems |  |  |  | x
L.14 | Logic Diagrams |  |  |  | x
L.15 | IM (information management) |  |  |  | x
L.16 | Control of Access |  |  |  | x
L.17 | Safety & Hazards |  |  |  |  | x
L.18 | Operations/Maintenance |  |  |  | x
L.19 | Ventilation Engineering |  |  |  | x
L.20 | Rock Engineering |  |  |  | x
L.21 | Water balances |  |  |  | x
L.22 | Energy efficiency / carbon footprint |  |  |  | x
L.23 | Tailings handling and storage |  |  |  | x
L.24 | Stormwater handling / surface hydrology |  |  |  | x
L.25 | Internal technical audits |  |  |  | x
L.26 | External technical audits |  |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  |  | x
M.3 | Technology trends |  |  | x
M.4 | Design to capacity |  |  | x
M.5 | Classes of facillity quality |  |  | x
M.6 | Energy optimisation |  |  |  | x
M.7 | Waste minimisation |  |  |  | x
M.8 | 3D / 4D design |  |  |  | x
M.9 | Cleaner Production |  |  |  | x
M.10 | Innovation and knowledge management planning |  |  |  | x
M.11 | Six Sigma |  |  |  |  | x
M.12 | Lean Manufacturing |  |  |  |  | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  |  |  | x
N.2 | Procurement Procedures and Plans |  |  |  | x
N.3 | Procurement Responsibility Matrix |  |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  |  | x
N.5 | Contracting strategy |  |  |  | x
N.6 | Procurement operation plan (POP) |  |  |  |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  |  | x
O.2 | Deliverables Defined |  |  |  | x
O.3 | Distribution Matrix |  |  |  | x
O.4 | Documentation/Deliverables |  |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  |  | x
P.2 | Project Cost Control |  |  |  | x
P.3 | Project Schedule Control |  |  |  | x
P.4 | Risk Management |  |  |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  |  |  | x
P.6 | Environmental Management |  |  |  | x
P.7 | Project Change Control |  |  |  | x
P.8 | Project Audits |  |  |  |  | x
P.9 | Decision register |  |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  |  | x
Q.2 | Project Organization |  |  |  |  | x
Q.3 | Responsibility matrix RACI |  |  |  |  | x
Q.4 | Document Management Plan |  |  |  | x
Q.5 | Communication management plan |  |  |  | x
Q.6 | Project Delivery Method |  |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  |  | x
Q.8 | Safety Procedures |  |  |  |  | x
Q.9 | Intercompany Agreements |  |  |  | x
Q.10 | Deliverables for Design and Construction |  |  |  | x
Q.11 | Labour and Skilled resources plan |  |  |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  |  | x
R.2 | Startup Requirements & plans |  |  |  |  | x
R.3 | Training Requirements |  |  |  | x
R.4 | Substantial Completion Requirements |  |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  | x
R.6 | Long term supply chain contracts |  |  |  | x
R.7 | Resourcing & staffing for operation |  |  |  |  | x
R.8 | Maintenance schedules |  |  |  |  | x
R.9 | Critical spares |  |  |  |  | x
R.10 | Startup consumables |  |  |  |  | x
R.11 | Operational systems and procedures to support each department |  |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  |  |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J25
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | X
A.2 | Project Charter and Mandate |  | X
A.3 | Governance and control (internal approval process defined) | X
A.5 | Project Strategy |  | X
A.6 | Strategic fit of project in organisation |  | X
A.7 | Due diligence |  | X
A.8 | Partnership, joint ventures and shareholder buy in |  | X
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  | X
B.2 | Geo-political risks | X
B.3 | Fiscal stability agreement |  | X
B.4 | Social License to Operate | X
B.5 | Violence and terrorism | X
B.6 | Ability to appoint expatriats | X
B.7 | Procurement of local and foreign materials, services and equipment | X
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  | X
B.9 | Custom duties & logistic routes |  | X
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) | X
C.2 | Financing secured (Internal, external, equity, debt) |  | X
C.3 | Business Plan |  | X
C.4 | Economic Analysis |  | X
C.5 | Affordability / Feasibility |  | X
C.6 | Contingencies (Capex & Opex) | X
C.7 | Basis of Estimate | X
C.8 | Scenario planning |  | X
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  | X
D.2 | Reserve risks (including modifying factors) |  | X
D.3 | Grade engineering / control |  | X
D.4 | Prospect drilling standard / guideline | X
D.5 | Geological conditions (Geological model, structure, qualities) |  |  | X
D.6 | Hydrogeology |  | X
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  | X
E.2 | Shaft/ramp design & men and material logistics |  | X
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | X
E.4 | Equipment selection to fit geological conditions and mining method |  | X
E.5 | Life-of-mine plan |  | X
E.6 | Waste management plan |  | X
E.7 | Ultimate pit limits designed |  | X
E.8 | Economic block values determination |  | X
E.9 | Beneficiation facilities LOM plan |  | X
E.10 | Materials handling LOM plan |  | X
Total | CATEGORY E (Maximum = ) |  | X
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | X
F.2 | Productivity / efficiency benchmarks |  |  | X
F.3 | Operating costs |  |  | X
F.4 | Production risks |  |  | X
F.5 | Catalogue of operating plans |  |  | X
F.6 | Haul roads |  | X
F.7 | Transportation strategy |  | X
F.8 | Contractual considerations |  | X
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | X
G.2 | Price risks |  |  | X
G.3 | Demand risks & replacement products / technologies |  |  | X
G.4 | Value-Analysis Process |  |  | X
G.5 | Hedging |  |  | X
G.6 | Competitor analysis
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  | X
H.2 | Assumption register |  | X
H.3 | Completion risks |  | X
H.4 | Project Design Criteria |  | X
H.5 | Scope of Work Overview |  | X
H.6 | Project Schedule |  | X
H.7 | Project Cost Estimate |  | X
H.8 | Investment Studies & Alternatives Assessments |  | X
H.9 | Key Team Member Coordination |  | X
H.10 | Evaluation of Compliance Requirements |  | X
H.11 | Lead / Discipline Scope of Work |  | X
H.12 | Housing and transport of employees |  | X
H.13 | Risk or impact on other projects / divisions |  | X
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | X
I.2 | Site Characteristics Available vs. Required |  | X
I.3 | Project Scope definition | X
I.4 | WBS and WBS Dictionary | X
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  |  | X
J.2 | Land use plan post operations |  |  | X
J.3 | Social expectations register |  |  | X
J.4 | Relocation Action Plan |  |  |  | X
J.5 | Environmental expectations register |  |  | X
J.6 | Political expectations register |  | X
J.7 | Legal compliance register |  |  | X
J.8 | HSE risk register |  | X
J.9 | Community risk register |  |  | X
J.10 | Business risk register |  | X
J.11 | Developmental opportunity register |  |  | X
J.12 | Sustainability operating plan |  |  | X
J.13 | Stakeholder engagement plan |  | X
J.14 | Mine closure financial provision plan |  |  |  | X
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  | X
J.16 | Social investment plan |  |  | X
J.17 | Economic diversification plan |  |  | X
J.18 | Existing Environmental Conditions |  |  | X
J.19 | Environmental Process determined |  |  | X
J.20 | Environmental management plan |  |  | X
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout | X
K.2 | Site Surveys | X
K.3 | Governing Regulatory Requirements |  | X
K.4 | Utility Sources with Supply Conditions | X
K.5 | Fire Protection, emergency procedure & Safety Considerations |  | X
K.6 | Special Water and Waste Treatment Requirements |  | X
K.7 | Property Descriptions |  | X
K.8 | Right-of-Way Mapping & Site Issues |  | X
K.9 | Land Rights | X
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  | X
L.2 | Civil/Site Design |  | X
L.3 | Geotechnical investigation for structures |  | X
L.4 | Architectural Design |  | X
L.5 | Structural Design |  | X
L.6 | Mechanical Design |  | X
L.7 | Electrical Design |  | X
L.8 | Constructability Analysis |  | X
L.9 | Process Design |  | X
L.10 | Specifications |  | X
L.11 | Specialty Items List |  | X
L.12 | Instrument Index |  | X
L.13 | Control Philosophy & systems |  | X
L.14 | Logic Diagrams |  | X
L.15 | IM (information management) |  | X
L.16 | Control of Access |  | X
L.17 | Safety & Hazards |  | X
L.18 | Operations/Maintenance |  | X
L.19 | Ventilation Engineering |  | X
L.20 | Rock Engineering |  | X
L.21 | Water balances |  | X
L.22 | Energy efficiency / carbon footprint |  | X
L.23 | Tailings handling and storage |  | X
L.24 | Stormwater handling / surface hydrology |  | X
L.25 | Internal technical audits |  | X
L.26 | External technical audits |  | X
Total | CATEGORY L (Maximum = ) |  | X
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  | X
M.2 | Design & Material Alternatives Considered/Rejected |  | X
M.3 | Technology trends |  | X
M.4 | Design to capacity |  | X
M.5 | Classes of facillity quality |  | X
M.6 | Energy optimisation |  | X
M.7 | Waste minimisation |  | X
M.8 | 3D / 4D design |  | X
M.9 | Cleaner Production |  | X
M.10 | Innovation and knowledge management planning |  | X
M.11 | Six Sigma | [5 empty] | X
M.12 | Lean Manufacturing |  | X
Total | CATEGORY M (Maximum = ) |  | X
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | X
N.2 | Procurement Procedures and Plans |  | X
N.3 | Procurement Responsibility Matrix |  | X
N.4 | Draft contracts & proforma bidders pack |  | X
N.5 | Contracting strategy |  | X
N.6 | Procurement operation plan (POP) |  | X
Total | CATEGORY N (Maximum = ) |  | X
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  | X
O.2 | Deliverables Defined |  | X
O.3 | Distribution Matrix |  | X
O.4 | Documentation/Deliverables |  | X
Total | CATEGORY O (Maximum = ) |  | X
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  | X
P.2 | Project Cost Control |  | X
P.3 | Project Schedule Control |  | X
P.4 | Risk Management |  | X
P.5 | Safety, Health, Hygiene and security Management |  | X
P.6 | Environmental Management |  | X
P.7 | Project Change Control |  | X
P.8 | Project Audits |  | X
P.9 | Decision register |  | X
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  | X
Q.2 | Project Organization |  | X
Q.3 | Responsibility matrix RACI |  | X
Q.4 | Document Management Plan |  | X
Q.5 | Communication management plan |  | X
Q.6 | Project Delivery Method |  | X
Q.7 | Design / Construction Plan and Approach |  | X
Q.8 | Safety Procedures |  | X
Q.9 | Intercompany Agreements |  | X
Q.10 | Deliverables for Design and Construction |  | X
Q.11 | Labour and Skilled resources plan |  | X
Total | CATEGORY Q (Maximum = ) |  | X
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  | X
R.2 | Startup Requirements & plans |  | X
R.3 | Training Requirements |  | X
R.4 | Substantial Completion Requirements |  | X
R.5 | Deliverables for Project Commissioning / Closeout |  | X
R.6 | Long term supply chain contracts |  | X
R.7 | Resourcing & staffing for operation |  | X
R.8 | Maintenance schedules |  | X
R.9 | Critical spares |  | X
R.10 | Startup consumables |  | X
R.11 | Operational systems and procedures to support each department |  | X
R.12 | Environmental Management Plan for Operations (EMP) |  | X
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J26
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  |  |  |  | x
A.2 | Project Charter and Mandate |  |  |  | x
A.3 | Governance and control (internal approval process defined) |  |  |  |  | x
A.5 | Project Strategy |  |  |  |  | x
A.6 | Strategic fit of project in organisation |  |  |  | x
A.7 | Due diligence |  |  |  |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  |  |  |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  |  |  | x
B.2 | Geo-political risks |  |  | x
B.3 | Fiscal stability agreement |  |  | x
B.4 | Social License to Operate |  |  | x
B.5 | Violence and terrorism |  |  | x
B.6 | Ability to appoint expatriats |  |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  |  | x
B.9 | Custom duties & logistic routes |  |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  |  | x
C.3 | Business Plan |  |  | x
C.4 | Economic Analysis |  |  | x
C.5 | Affordability / Feasibility |  |  |  |  | x
C.6 | Contingencies (Capex & Opex) |  |  |  |  | x
C.7 | Basis of Estimate |  |  |  |  | x
C.8 | Scenario planning |  |  |  |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  | x
D.3 | Grade engineering / control |  |  | x
D.4 | Prospect drilling standard / guideline |  |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  |  | x
D.6 | Hydrogeology |  |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  |  | x
E.2 | Shaft/ramp design & men and material logistics |  |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  |  | x
E.5 | Life-of-mine plan |  |  | x
E.6 | Waste management plan |  |  | x
E.7 | Ultimate pit limits designed |  |  | x
E.8 | Economic block values determination |  |  | x
E.9 | Beneficiation facilities LOM plan |  |  |  | x
E.10 | Materials handling LOM plan |  |  |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  |  |  | x
F.2 | Productivity / efficiency benchmarks |  |  |  | x
F.3 | Operating costs |  |  |  | x
F.4 | Production risks |  |  |  | x
F.5 | Catalogue of operating plans |  |  |  | x
F.6 | Haul roads |  |  | x
F.7 | Transportation strategy |  |  | x
F.8 | Contractual considerations |  |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  |  | x
G.2 | Price risks |  |  |  |  | x
G.3 | Demand risks & replacement products / technologies |  |  |  |  | x
G.4 | Value-Analysis Process |  |  |  | x
G.5 | Hedging |  |  |  |  | x
G.6 | Competitor analysis |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  |  |  |  | x
H.2 | Assumption register |  |  |  |  | x
H.3 | Completion risks |  |  |  |  | x
H.4 | Project Design Criteria |  |  |  |  | x
H.5 | Scope of Work Overview |  |  |  |  | x
H.6 | Project Schedule |  |  |  |  | x
H.7 | Project Cost Estimate |  |  |  |  | x
H.8 | Investment Studies & Alternatives Assessments |  |  |  | x
H.9 | Key Team Member Coordination |  |  |  |  | x
H.10 | Evaluation of Compliance Requirements |  |  |  |  | x
H.11 | Lead / Discipline Scope of Work |  |  |  |  | x
H.12 | Housing and transport of employees |  |  |  |  | x
H.13 | Risk or impact on other projects / divisions |  |  |  |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  |  |  |  | x
I.2 | Site Characteristics Available vs. Required |  |  |  |  | x
I.3 | Project Scope definition |  |  |  |  | x
I.4 | WBS and WBS Dictionary |  |  |  |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  | x
J.2 | Land use plan post operations |  |  | x
J.3 | Social expectations register |  |  | x
J.4 | Relocation Action Plan |  |  | x
J.5 | Environmental expectations register |  |  | x
J.6 | Political expectations register |  |  | x
J.7 | Legal compliance register |  | x
J.8 | HSE risk register |  |  |  | x
J.9 | Community risk register |  |  |  | x
J.10 | Business risk register |  |  |  | x
J.11 | Developmental opportunity register |  |  |  | x
J.12 | Sustainability operating plan |  |  |  | x
J.13 | Stakeholder engagement plan |  |  |  | x
J.14 | Mine closure financial provision plan |  |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  |  | x
J.16 | Social investment plan |  |  |  | x
J.17 | Economic diversification plan |  |  |  | x
J.18 | Existing Environmental Conditions |  |  |  | x
J.19 | Environmental Process determined |  |  |  | x
J.20 | Environmental management plan |  |  |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  |  |  |  | x
K.2 | Site Surveys |  |  |  |  | x
K.3 | Governing Regulatory Requirements |  |  |  | x
K.4 | Utility Sources with Supply Conditions |  |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  |  | x
K.6 | Special Water and Waste Treatment Requirements |  |  | x
K.7 | Property Descriptions
K.8 | Right-of-Way Mapping & Site Issues
K.9 | Land Rights
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  |  |  |  | x
L.2 | Civil/Site Design |  |  |  |  | x
L.3 | Geotechnical investigation for structures | [5 empty] | x
L.4 | Architectural Design |  |  |  |  | x
L.5 | Structural Design |  |  |  |  | x
L.6 | Mechanical Design |  |  |  |  | x
L.7 | Electrical Design |  |  |  |  | x
L.8 | Constructability Analysis | [5 empty] | x
L.9 | Process Design |  |  |  | x
L.10 | Specifications |  |  |  |  | x
L.11 | Specialty Items List |  |  |  |  | x
L.12 | Instrument Index |  |  |  |  | x
L.13 | Control Philosophy & systems |  |  |  |  | x
L.14 | Logic Diagrams |  |  |  |  | x
L.15 | IM (information management) |  |  |  |  | x
L.16 | Control of Access |  |  |  |  | x
L.17 | Safety & Hazards |  |  |  |  | x
L.18 | Operations/Maintenance |  |  |  |  | x
L.19 | Ventilation Engineering |  |  |  |  | x
L.20 | Rock Engineering |  |  |  |  | x
L.21 | Water balances |  |  |  |  | x
L.22 | Energy efficiency / carbon footprint |  |  |  |  | x
L.23 | Tailings handling and storage |  |  |  |  | x
L.24 | Stormwater handling / surface hydrology |  |  |  |  | x
L.25 | Internal technical audits |  |  |  |  | x
L.26 | External technical audits |  |  |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  |  |  |  | x
M.2 | Design & Material Alternatives Considered/Rejected |  |  |  |  | x
M.3 | Technology trends |  |  |  |  | x
M.4 | Design to capacity |  |  |  |  | x
M.5 | Classes of facillity quality |  |  |  |  | x
M.6 | Energy optimisation |  |  |  |  | x
M.7 | Waste minimisation |  |  |  | x
M.8 | 3D / 4D design |  |  |  |  | x
M.9 | Cleaner Production |  |  |  |  | x
M.10 | Innovation and knowledge management planning |  |  |  |  | x
M.11 | Six Sigma |  |  |  |  | x
M.12 | Lean Manufacturing |  |  |  |  | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  |  |  | x
N.2 | Procurement Procedures and Plans |  |  |  |  | x
N.3 | Procurement Responsibility Matrix |  |  |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  |  | x
N.5 | Contracting strategy |  |  |  | x
N.6 | Procurement operation plan (POP) |  |  |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  |  |  | x
O.2 | Deliverables Defined |  |  |  |  | x
O.3 | Distribution Matrix |  |  |  |  | x
O.4 | Documentation/Deliverables |  |  |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  |  | x
P.2 | Project Cost Control |  |  |  |  | x
P.3 | Project Schedule Control |  |  |  |  | x
P.4 | Risk Management |  |  |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  |  | x
P.6 | Environmental Management |  |  | x
P.7 | Project Change Control | [5 empty] | x
P.8 | Project Audits |  |  |  |  | x
P.9 | Decision register |  |  |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  |  |  | x
Q.2 | Project Organization |  |  |  |  | x
Q.3 | Responsibility matrix RACI |  |  |  |  | x
Q.4 | Document Management Plan |  |  |  | x
Q.5 | Communication management plan |  |  |  |  | x
Q.6 | Project Delivery Method |  |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  |  |  | x
Q.8 | Safety Procedures |  |  |  | x
Q.9 | Intercompany Agreements |  |  | x
Q.10 | Deliverables for Design and Construction |  |  |  |  | x
Q.11 | Labour and Skilled resources plan |  |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  |  |  |  | x
R.2 | Startup Requirements & plans |  |  |  |  | x
R.3 | Training Requirements |  |  |  |  | x
R.4 | Substantial Completion Requirements |  |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  |  |  | x
R.6 | Long term supply chain contracts |  |  |  | x
R.7 | Resourcing & staffing for operation |  |  |  |  | x
R.8 | Maintenance schedules |  |  |  |  | x
R.9 | Critical spares |  |  |  | x
R.10 | Startup consumables |  |  |  | x
R.11 | Operational systems and procedures to support each department |  |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  |  |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition

## J27
PDRI for Mining Projects
SECTION I - BASIS OF PROJECT DECISION
CATEGORY Element
A | PROJECT STRATEGY | 0 | 1 | 2 | 3 | 4 | 5
A.1 | Project Justification |  | x
A.2 | Project Charter and Mandate |  | x
A.3 | Governance and control (internal approval process defined) |  | x
A.5 | Project Strategy |  | x
A.6 | Strategic fit of project in organisation |  | x
A.7 | Due diligence |  | x
A.8 | Partnership, joint ventures and shareholder buy in |  | x
Total | CATEGORY A (Maximum = )
B | COUNTRY RISK | 0 | 1 | 2 | 3 | 4 | 5
B.1 | Social Issues |  | x
B.2 | Geo-political risks |  | x
B.3 | Fiscal stability agreement |  | x
B.4 | Social License to Operate |  | x
B.5 | Violence and terrorism |  | x
B.6 | Ability to appoint expatriats |  | x
B.7 | Procurement of local and foreign materials, services and equipment |  | x
B.8 | Country infrastructure (power, roads, rail, water ports) |  | x
B.9 | Custom duties & logistic routes |  | x
Total | CATEGORY B (Maximum = )
C | PROJECT FEASIBILITY | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Resouces secured (including land and mineral rights) |  | x
C.2 | Financing secured (Internal, external, equity, debt) |  | x
C.3 | Business Plan |  | x
C.4 | Economic Analysis |  | x
C.5 | Affordability / Feasibility |  | x
C.6 | Contingencies (Capex & Opex) |  | x
C.7 | Basis of Estimate |  | x
C.8 | Scenario planning |  | x
Total | CATEGORY C (Maximum = )
D | RESOURCE AND RESERVE STATEMENT | 0 | 1 | 2 | 3 | 4 | 5
D.1 | Metallurgical yield |  |  | x
D.2 | Reserve risks (including modifying factors) |  |  | x
D.3 | Grade engineering / control |  |  | x
D.4 | Prospect drilling standard / guideline |  |  | x
D.5 | Geological conditions (Geological model, structure, qualities) |  |  | x
D.6 | Hydrogeology |  | x
Total | CATEGORY D (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Mine design criteria |  | x
E.2 | Shaft/ramp design & men and material logistics |  | x
E.3 | Mining methods (drilling, blasting, loading, hauling) |  | x
E.4 | Equipment selection to fit geological conditions and mining method |  | x
E.5 | Life-of-mine plan |  | x
E.6 | Waste management plan |  | x
E.7 | Ultimate pit limits designed |  | x
E.8 | Economic block values determination |  | x
E.9 | Beneficiation facilities LOM plan |  | x
E.10 | Materials handling LOM plan |  | x
Total | CATEGORY E (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
F.1 | Operating Philosophy (Outsourcing vs internal vs combination) |  | x
F.2 | Productivity / efficiency benchmarks |  | x
F.3 | Operating costs |  | x
F.4 | Production risks |  | x
F.5 | Catalogue of operating plans |  | x
F.6 | Haul roads |  | x
F.7 | Transportation strategy |  | x
F.8 | Contractual considerations |  | x
Total | CATEGORY F (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
G.1 | Market Strategy & Sales Agreements |  | x
G.2 | Price risks |  | x
G.3 | Demand risks & replacement products / technologies |  | x
G.4 | Value-Analysis Process |  | x
G.5 | Hedging |  | x
G.6 | Competitor analysis |  | x
Total | CATEGORY G (Maximum = )
Total | SECTION I (Maximum = )
SECTION II - PROJECT DETAILS
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
H.1 | Expected Project Life Cycle |  | x
H.2 | Assumption register |  | x
H.3 | Completion risks |  | x
H.4 | Project Design Criteria |  | x
H.5 | Scope of Work Overview |  | x
H.6 | Project Schedule |  | x
H.7 | Project Cost Estimate |  | x
H.8 | Investment Studies & Alternatives Assessments |  | x
H.9 | Key Team Member Coordination |  | x
H.10 | Evaluation of Compliance Requirements |  |  |  | x
H.11 | Lead / Discipline Scope of Work |  | x
H.12 | Housing and transport of employees |  |  |  | x
H.13 | Risk or impact on other projects / divisions |  | x
Total | CATEGORY H (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
I.1 | Project Objectives Statement |  | x
I.2 | Site Characteristics Available vs. Required |  | x
I.3 | Project Scope definition |  | x
I.4 | WBS and WBS Dictionary |  | x
Total | CATEGORY I (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
J.1 | Unique mine closure plan |  |  | x
J.2 | Land use plan post operations |  | x
J.3 | Social expectations register |  |  | x
J.4 | Relocation Action Plan | x
J.5 | Environmental expectations register |  |  | x
J.6 | Political expectations register |  |  | x
J.7 | Legal compliance register |  |  | x
J.8 | HSE risk register |  |  |  | x
J.9 | Community risk register |  |  | x
J.10 | Business risk register |  |  | x
J.11 | Developmental opportunity register |  |  | x
J.12 | Sustainability operating plan |  |  | x
J.13 | Stakeholder engagement plan |  |  | x
J.14 | Mine closure financial provision plan |  |  | x
J.15 | Closure plan review and updates scheduled during Life of Mine plan |  |  | x
J.16 | Social investment plan |  |  | x
J.17 | Economic diversification plan |  |  |  | x
J.18 | Existing Environmental Conditions |  | x
J.19 | Environmental Process determined |  |  | x
J.20 | Environmental management plan |  |  | x
Total | CATEGORY J (Maximum = )
Total | SECTION II (Maximum = )
SECTION III - DESIGN FOR CONSTRUCTION
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
K.1 | Site Layout |  | x
K.2 | Site Surveys |  | x
K.3 | Governing Regulatory Requirements |  | x
K.4 | Utility Sources with Supply Conditions |  | x
K.5 | Fire Protection, emergency procedure & Safety Considerations |  | x
K.6 | Special Water and Waste Treatment Requirements |  | x
K.7 | Property Descriptions |  | x
K.8 | Right-of-Way Mapping & Site Issues |  | x
K.9 | Land Rights |  | x
Total | CATEGORY K (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
L.1 | Design Criteria |  | x
L.2 | Civil/Site Design |  | x
L.3 | Geotechnical investigation for structures |  |  |  | x
L.4 | Architectural Design |  | x
L.5 | Structural Design |  | x
L.6 | Mechanical Design |  | x
L.7 | Electrical Design |  | x
L.8 | Constructability Analysis |  | x
L.9 | Process Design |  | x
L.10 | Specifications |  |  |  | x
L.11 | Specialty Items List |  |  | x
L.12 | Instrument Index |  | x
L.13 | Control Philosophy & systems |  | x
L.14 | Logic Diagrams |  | x
L.15 | IM (information management) |  |  | x
L.16 | Control of Access |  | x
L.17 | Safety & Hazards |  |  |  | x
L.18 | Operations/Maintenance |  |  | x
L.19 | Ventilation Engineering |  |  | x
L.20 | Rock Engineering |  | x
L.21 | Water balances |  | x
L.22 | Energy efficiency / carbon footprint |  | x
L.23 | Tailings handling and storage |  |  | x
L.24 | Stormwater handling / surface hydrology |  |  | x
L.25 | Internal technical audits |  |  | x
L.26 | External technical audits |  |  | x
Total | CATEGORY L (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
M.1 | Process Simplification |  | 1
M.2 | Design & Material Alternatives Considered/Rejected |  | 1
M.3 | Technology trends |  | 1
M.4 | Design to capacity |  |  | 1
M.5 | Classes of facillity quality |  |  | x
M.6 | Energy optimisation |  |  | x
M.7 | Waste minimisation |  | x
M.8 | 3D / 4D design |  |  |  | x
M.9 | Cleaner Production |  |  | x
M.10 | Innovation and knowledge management planning |  |  | x
M.11 | Six Sigma |  |  |  | x
M.12 | Lean Manufacturing |  |  | x
Total | CATEGORY M (Maximum = )
Total | SECTION III (Maximum = )
SECTION IV - EXECUTION APPROACH
Definition Level
|  | 0 | 1 | 2 | 3 | 4 | 5
N.1 | Identify Long Lead/Critical Equipment and Materials |  | x
N.2 | Procurement Procedures and Plans |  | x
N.3 | Procurement Responsibility Matrix |  |  |  | x
N.4 | Draft contracts & proforma bidders pack |  |  | x
N.5 | Contracting strategy |  |  | x
N.6 | Procurement operation plan (POP) |  |  | x
Total | CATEGORY N (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
O.1 | CADD/Model Requirements |  |  | x
O.2 | Deliverables Defined |  |  | x
O.3 | Distribution Matrix |  |  | x
O.4 | Documentation/Deliverables |  |  | x
Total | CATEGORY O (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
P.1 | Project Quality Assurance and Control |  |  | x
P.2 | Project Cost Control |  | x
P.3 | Project Schedule Control |  |  | x
P.4 | Risk Management |  |  | x
P.5 | Safety, Health, Hygiene and security Management |  |  |  | x
P.6 | Environmental Management |  |  | x
P.7 | Project Change Control |  | x
P.8 | Project Audits |  |  | x
P.9 | Decision register |  |  | x
Total | CATEGORY P (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
Q.1 | Engineering / Construction Plan & Approach |  | x
Q.2 | Project Organization |  |  | x
Q.3 | Responsibility matrix RACI |  |  | x
Q.4 | Document Management Plan |  |  | x
Q.5 | Communication management plan |  |  | x
Q.6 | Project Delivery Method |  |  | x
Q.7 | Design / Construction Plan and Approach |  |  | x
Q.8 | Safety Procedures |  |  |  | x
Q.9 | Intercompany Agreements | x
Q.10 | Deliverables for Design and Construction |  | x
Q.11 | Labour and Skilled resources plan |  |  | x
Total | CATEGORY Q (Maximum = )
|  | 0 | 1 | 2 | 3 | 4 | 5
R.1 | Commissioning plan |  | x
R.2 | Startup Requirements & plans |  |  | x
R.3 | Training Requirements |  |  | x
R.4 | Substantial Completion Requirements |  |  | x
R.5 | Deliverables for Project Commissioning / Closeout |  |  | x
R.6 | Long term supply chain contracts |  | x
R.7 | Resourcing & staffing for operation |  | x
R.8 | Maintenance schedules |  | x
R.9 | Critical spares |  | x
R.10 | Startup consumables |  | x
R.11 | Operational systems and procedures to support each department |  |  | x
R.12 | Environmental Management Plan for Operations (EMP) |  | x
Total | CATEGORY R (Maximum = )
Total | SECTION IV (Maximum = )
Note on C177: Level 0: Element not applicable
Note on D177: Level 1: Element completely defined
Note on E177: Level 2: Element has minor deficiencies
Note on F177: Level 3: Element has some deficiencies
Note on G177: Level 4: Element has major deficiencies
Note on H177: Level 5: Element has poor or incomplete definition
Note on C185: Level 0: Element not applicable
Note on D185: Level 1: Element completely defined
Note on E185: Level 2: Element has minor deficiencies
Note on F185: Level 3: Element has some deficiencies
Note on G185: Level 4: Element has major deficiencies
Note on H185: Level 5: Element has poor or incomplete definition
Note on C191: Level 0: Element not applicable
Note on D191: Level 1: Element completely defined
Note on E191: Level 2: Element has minor deficiencies
Note on F191: Level 3: Element has some deficiencies
Note on G191: Level 4: Element has major deficiencies
Note on H191: Level 5: Element has poor or incomplete definition
Note on C202: Level 0: Element not applicable
Note on D202: Level 1: Element completely defined
Note on E202: Level 2: Element has minor deficiencies
Note on F202: Level 3: Element has some deficiencies
Note on G202: Level 4: Element has major deficiencies
Note on H202: Level 5: Element has poor or incomplete definition
Note on C215: Level 0: Element not applicable
Note on D215: Level 1: Element completely defined
Note on E215: Level 2: Element has minor deficiencies
Note on F215: Level 3: Element has some deficiencies
Note on G215: Level 4: Element has major deficiencies
Note on H215: Level 5: Element has poor or incomplete definition